## Summary
| Test Case # | # of Test Scripts | Test Case Name | Name of Tester
| 1 | 20 | Division Admin
| 2 | 22 | eBusiness Admin |  | Total Test Scripts | 158
| 3 | 13 | Security Admin |  | Passed
| 4 | 18 | CSR |  | Failed
| 5 | 14 | Promotion Admin |  | Remaining to Test
| 6 | 18 | Catalog Admin
| 7 | 12 | Manage My Items Admin
| 8 | 23 | Support Desk
| 9 | 18 | Integration Admin
TOTAL | 9 | 158

## Instructions
Coming Soon….
Naming Conventions - Chris
How to use Summary Tab - Chris
How to Use Test Case Tab - Barb
Test Case Tab - Using the Table - Barry
HEADER: Populate header information including Use Case, DDD, and Requirement info to provide traceability. Also be sure to identify any required PreConditions such as test cases which should already have been completed before starting the current test case. Notes may be used for any instructions which may be relevant to the tester.
STEP #:
USER INPUT:
EXPECTED RESULTS:
ACTUAL RESULTS / COMMENTS:
PASS / FAIL:
DATE EXECUTED:
JIRA #: Any significant failure should be documented in JIRA. "Significant" may be characterized as " ". Any departure from the expected result must be captured in the Actual Results / Comments field, but full details of "Significant" failures must be documented in JIRA for appropriate follow-up and assignment for resolution. Enter the numeric portion of the JIRA ticket in the JIRA # cell. This spreadsheet assumes all JIRA tickets will be associated with the XNGT (xpedx.com Next Gen Test Phase) project and assign that JIRA prefix. If the relevant JIRA ticket should be associated with another JIRA project, simply type in the entire JIRA ticket ID. (e.g. PCI Compliance might be PCI-123).
Other Considerations:
• Consider allocating dedicated space to identify predecessor Test Cases.
• Word wrap doesn't function in columns B-C because of merged cells. (Column D works fine.) We could resolve by moving TestCase#, UseCase #, etc to the far right where lower cells are unlikely to require word wrap.
• Consider a Status to identify follow-up needed. (Suspend?) Unexpected results may not indicate failure, but might justify conversation with the business, or disclose previously unforseen design considerations. Follow-up for any step might keep the overall test in a "Suspended" status. This would require complete documentation in JIRA.
Add ExecutedBY field
User Types (Roles)
External: Buyer (Can checkout, view invoices, view reports, view prices)
External: Customer Administrator (Has all Buyer privileges AND can maintain subordinate users)
User Profile Flags: Can checkout; Can view invoices online; Can view reports; Can view prices. (All are checked by default)

## 1. Division Admin
Test Case # | 1 | Test Case Name: | Manage External Customers and Users |  | Tester Name:
Use Case # |  | Preconditions: | ID needs to be setup with Divison Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is able to manage external customers and users
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Customer Search |  | Can search for customers |  | Not Started
2 | Manage customer profile link displays |  | Manage customer profile link can be selected |  | Not Started
3 | Corporate and Manage customer rules tabs are available |  | Can select and manage data on these two tabs |  | Not Started
4 | Cannot create customers |  | • |  | Not Started
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 1.01 | Test Case Name: | Manage Internal Users
Use Case # |  | Preconditions: | ID needs to be setup with Division Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage internal users
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Cannot Manage User Profile for internal users |  | Link to Manage User Profile is inactive for internal users |  | Not Started
2 | Can Manage Customer Profile for external users |  | Link to Manage Customer Profile is active for external users |  | Not Started
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 1.02 | Test Case Name: | Manage/Create Order
Use Case # |  | Preconditions: | ID needs to be setup with Division Admin only User_Role. Determine which divisions user can maintain
DDD ID:
Req. # |  | Notes: | User is able to read, create and manage orders at division level
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Menu options available |  | Create Order option available on left hand side |  | Not Started
2 | Can create new orders |  | • |  | Not Started
3 | Can search for orders |  | • |  | Not Started
4 | Can manage orders in correct status |  | • |  | Not Started
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 1.03 | Test Case Name: | Manage Division Profile
Use Case # |  | Preconditions: | ID needs to be setup with Division Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage the Division Profile
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | The Division Search link is not active |  | • Link is not active |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | • | `
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 1.04 | Test Case Name: | Manage Promotions & Coupons through SBC
Use Case # |  | Preconditions: | ID needs to be setup with Division Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage Promotions and Coupons through SBC
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Try to logon to SBC |  | User should not be able to access Promotions or Coupons SBC |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 1.05 | Test Case Name: | Manage Entitlements through SBC
Use Case # |  | Preconditions: | ID needs to be setup with Division Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage Entitlements through SBC
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Try to logon to SBC |  | User should not be able to access Entitlements in SBC |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 1.06 | Test Case Name: | Manage News
Use Case # |  | Preconditions: | ID needs to be setup with Division Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is able to read and update News
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Manage Articles Link is visible and clickable |  | Manage Article tab appears |  | Not Started
2 | Can search news articles |  | • |  | Not Started
3 | Can create news articles |  | • |  | Not Started
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 1.07 | Test Case Name: | Reset Passwords
Use Case # |  | Preconditions: | ID needs to be setup with Division Admin only User_Role, Divisions need to be defined for user
DDD ID:
Req. # |  | Notes: | User is able to reset passwords
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Reset user password should display when viewing user detail |  | Should be able to use reset password option on the tasks menu or should be able to go into manage customer profile to reset password |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 1.08 | Test Case Name: | Narrow by Catalog
Use Case # |  | Preconditions: | ID needs to be setup with Division Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able set the catalog narrow by search in SBC
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Try to logon to SBC |  | User should not be able to access narrow by search in SBC |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 1.09 | Test Case Name: | Manage My Items
Use Case # |  | Preconditions: | ID needs to be setup with Division Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage My Items List
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Manage My Items list link is not viewable/clickable on quick access tab under Item Search |  | Link is not accessible |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 1.1 | Test Case Name: | Integration related fields
Use Case # |  | Preconditions: | ID needs to be setup with Division Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage Integration Related Fields on User/Customer Profile
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Customer Integration Data Maintenance tab |  | Should not display or allow updates |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Note on B2: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E7: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F7: Select from List. - Blank - Pass - Fail - Not Started
Note on G7: Enter Month / Day. Year defaults to current year unless entered.
Note on H7: Enter numeric portion of JIRA ticket.
Note on B19: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E24: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F24: Select from List. - Blank - Pass - Fail - Not Started
Note on G24: Enter Month / Day. Year defaults to current year unless entered.
Note on H24: Enter numeric portion of JIRA ticket.
Note on B36: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E41: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F41: Select from List. - Blank - Pass - Fail - Not Started
Note on G41: Enter Month / Day. Year defaults to current year unless entered.
Note on H41: Enter numeric portion of JIRA ticket.
Note on B53: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E58: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F58: Select from List. - Blank - Pass - Fail - Not Started
Note on G58: Enter Month / Day. Year defaults to current year unless entered.
Note on H58: Enter numeric portion of JIRA ticket.
Note on B70: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E75: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F75: Select from List. - Blank - Pass - Fail - Not Started
Note on G75: Enter Month / Day. Year defaults to current year unless entered.
Note on H75: Enter numeric portion of JIRA ticket.
Note on B86: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E91: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F91: Select from List. - Blank - Pass - Fail - Not Started
Note on G91: Enter Month / Day. Year defaults to current year unless entered.
Note on H91: Enter numeric portion of JIRA ticket.
Note on B103: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E108: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F108: Select from List. - Blank - Pass - Fail - Not Started
Note on G108: Enter Month / Day. Year defaults to current year unless entered.
Note on H108: Enter numeric portion of JIRA ticket.
Note on B120: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E125: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F125: Select from List. - Blank - Pass - Fail - Not Started
Note on G125: Enter Month / Day. Year defaults to current year unless entered.
Note on H125: Enter numeric portion of JIRA ticket.
Note on B136: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E141: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F141: Select from List. - Blank - Pass - Fail - Not Started
Note on G141: Enter Month / Day. Year defaults to current year unless entered.
Note on H141: Enter numeric portion of JIRA ticket.
Note on B154: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E159: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F159: Select from List. - Blank - Pass - Fail - Not Started
Note on G159: Enter Month / Day. Year defaults to current year unless entered.
Note on H159: Enter numeric portion of JIRA ticket.
Note on B171: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E176: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F176: Select from List. - Blank - Pass - Fail - Not Started
Note on G176: Enter Month / Day. Year defaults to current year unless entered.
Note on H176: Enter numeric portion of JIRA ticket.

## 2. eBusiness Admin
Test Case # | 2 | Test Case Name: | Manage External Customers and Users |  | Tester Name:
Use Case # |  | Preconditions: | ID needs to be setup with eBusiness Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is able to manage external customers and users
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Customer Search |  | Can search for customers |  | Not Started
2 | Manage customer profile link displays |  | Manage customer profile link can be selected |  | Not Started
3 | Corporate and Manage customer rules tabs are available |  | Can select and manage data on these two tabs |  | Not Started
4 | Cannot create customers |  | • |  | Not Started
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 2.01 | Test Case Name: | Manage Internal Users
Use Case # |  | Preconditions: | ID needs to be setup with eBusiness Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage internal users
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Cannot Manage User Profile for internal users |  | Link to Manage User Profile is inactive for internal users |  | Not Started
2 | Can Manage Customer Profile for external users |  | Link to Manage Customer Profile is active for external users |  | Not Started
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 2.02 | Test Case Name: | Manage/Create Order
Use Case # |  | Preconditions: | ID needs to be setup with eBusiness Admin only User_Role. Determine which divisions user can maintain
DDD ID:
Req. # |  | Notes: | User is able to read, create and manage orders at division level
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Menu options available |  | Create Order option available on left hand side |  | Not Started
2 | Can create new orders |  | • |  | Not Started
3 | Can search for orders |  | • |  | Not Started
4 | Can manage orders in correct status |  | • |  | Not Started
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 2.03 | Test Case Name: | Manage Division Profile
Use Case # |  | Preconditions: | ID needs to be setup with eBusiness Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage the Division Profile
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | The Division Search link is not active |  | Division Search link is grey and not clickable |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | • | `
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 2.04 | Test Case Name: | Manage Promotions & Coupons through SBC
Use Case # |  | Preconditions: | ID needs to be setup with eBusiness Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage Promotions and Coupons through SBC
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Try to logon to SBC |  | User should not be able to access Promotions or Coupons SBC |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 2.05 | Test Case Name: | Manage Entitlements through SBC
Use Case # |  | Preconditions: | ID needs to be setup with eBusiness Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is able to access SBC to manage Entitlements
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | User is able to logon to SBC |  | Customer Entitlements is visible and cllickable |  | Not Started
2 | User is able to set up new entitlement |  | • |  | Not Started
3 | User is able to find entitlements |  | • |  | Not Started
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 2.06 | Test Case Name: | Manage News
Use Case # |  | Preconditions: | ID needs to be setup with eBusiness Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is able to read and update News
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Manage Articles Link is visible and clickable |  | Manage Article tab appears |  | Not Started
2 | Can search news articles |  | • |  | Not Started
3 | Can create news articles |  | • |  | Not Started
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 2.07 | Test Case Name: | Reset Passwords
Use Case # |  | Preconditions: | ID needs to be setup with eBusiness Admin only User_Role, Divisions need to be defined for user
DDD ID:
Req. # |  | Notes: | User is able to reset passwords
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Reset user password should display when viewing user detail |  | Should be able to use reset password option on the tasks menu or should be able to go into manage customer profile to reset password |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 2.08 | Test Case Name: | Narrow by Catalog
Use Case # |  | Preconditions: | ID needs to be setup with eBusiness Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able set the catalog narrow by in SBC
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | User logs on to SBC |  | User is able to log on to SBC |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 2.09 | Test Case Name: | Manage My Items
Use Case # |  | Preconditions: | ID needs to be setup with eBusiness Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage My Items List
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Manage My Items list link is not viewable/clickable on quick access tab under Item Search |  | Link is not accessible |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 2.1 | Test Case Name: | Integration related fields
Use Case # |  | Preconditions: | ID needs to be setup with eBusiness Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage Integration Related Fields on User/Customer Profile
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Customer Integration Data Maintenance tab |  | Should not display or allow updates |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Note on B2: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E7: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F7: Select from List. - Blank - Pass - Fail - Not Started
Note on G7: Enter Month / Day. Year defaults to current year unless entered.
Note on H7: Enter numeric portion of JIRA ticket.
Note on B19: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E24: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F24: Select from List. - Blank - Pass - Fail - Not Started
Note on G24: Enter Month / Day. Year defaults to current year unless entered.
Note on H24: Enter numeric portion of JIRA ticket.
Note on B36: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E41: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F41: Select from List. - Blank - Pass - Fail - Not Started
Note on G41: Enter Month / Day. Year defaults to current year unless entered.
Note on H41: Enter numeric portion of JIRA ticket.
Note on B53: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E58: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F58: Select from List. - Blank - Pass - Fail - Not Started
Note on G58: Enter Month / Day. Year defaults to current year unless entered.
Note on H58: Enter numeric portion of JIRA ticket.
Note on B70: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E75: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F75: Select from List. - Blank - Pass - Fail - Not Started
Note on G75: Enter Month / Day. Year defaults to current year unless entered.
Note on H75: Enter numeric portion of JIRA ticket.
Note on B86: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E91: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F91: Select from List. - Blank - Pass - Fail - Not Started
Note on G91: Enter Month / Day. Year defaults to current year unless entered.
Note on H91: Enter numeric portion of JIRA ticket.
Note on B103: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E108: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F108: Select from List. - Blank - Pass - Fail - Not Started
Note on G108: Enter Month / Day. Year defaults to current year unless entered.
Note on H108: Enter numeric portion of JIRA ticket.
Note on B120: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E125: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F125: Select from List. - Blank - Pass - Fail - Not Started
Note on G125: Enter Month / Day. Year defaults to current year unless entered.
Note on H125: Enter numeric portion of JIRA ticket.
Note on B136: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E141: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F141: Select from List. - Blank - Pass - Fail - Not Started
Note on G141: Enter Month / Day. Year defaults to current year unless entered.
Note on H141: Enter numeric portion of JIRA ticket.
Note on B154: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E159: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F159: Select from List. - Blank - Pass - Fail - Not Started
Note on G159: Enter Month / Day. Year defaults to current year unless entered.
Note on H159: Enter numeric portion of JIRA ticket.
Note on B171: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E176: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F176: Select from List. - Blank - Pass - Fail - Not Started
Note on G176: Enter Month / Day. Year defaults to current year unless entered.
Note on H176: Enter numeric portion of JIRA ticket.

## 3. Security Admin
Test Case # | 3 | Test Case Name: | Manage External Customers and Users |  | Tester Name:
Use Case # |  | Preconditions: | ID needs to be setup with Security Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage external customers and users
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Customer Search |  | Cannot search for customers |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 3.01 | Test Case Name: | Manage Internal Users
Use Case # |  | Preconditions: | ID needs to be setup with Security Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is able to manage internal users
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Can change password, create user, modify user |  | User Management tab on left side is active |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 3.02 | Test Case Name: | Manage/Create Order
Use Case # |  | Preconditions: | ID needs to be setup with Security Admin only User_Role. Determine which divisions user can maintain
DDD ID:
Req. # |  | Notes: | User is not able to read, create or manage orders at division level
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Cannot create an order |  | Create Order is not available on left hand side |  | Not Started
2 | Cannot search for orders |  | If user clicks on order history tab while in customer profile, error occurs |  | Not Started
3 | User should not have access to Order Search |  | • |  | Not Started
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 3.03 | Test Case Name: | Manage Division Profile
Use Case # |  | Preconditions: | ID needs to be setup with Security Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage the Division Profile
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | The Division Search link is not active |  | Division Search link is grey and not clickable |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | • | `
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 3.04 | Test Case Name: | Manage Promotions & Coupons through SBC
Use Case # |  | Preconditions: | ID needs to be setup with Security Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage Promotions and Coupons through SBC
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Try to logon to SBC |  | User should not be able to access Promotions or Coupons SBC |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 3.05 | Test Case Name: | Manage Entitlements through SBC
Use Case # |  | Preconditions: | ID needs to be setup with Security Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage Entitlements through SBC
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Try to logon to SBC |  | User should not be able to access Entitlements in SBC |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 3.06 | Test Case Name: | Manage News
Use Case # |  | Preconditions: | ID needs to be setup with Security Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to access News
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Cannot search or create news articles |  | Manage articles is grey and cannot be clicked |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 3.07 | Test Case Name: | Reset Passwords
Use Case # |  | Preconditions: | ID needs to be setup with Security Admin only User_Role, Divisions need to be defined for user
DDD ID:
Req. # |  | Notes: | User is not able to reset passwords
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Reset user password does not display when viewing user detail |  | Reset User Password is not a given option. |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 3.08 | Test Case Name: | Narrow by Catalog
Use Case # |  | Preconditions: | ID needs to be setup with Security Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able set the catalog narrow by search in SBC
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Try to logon to SBC |  | User should not be able to access narrow by search in SBC |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 3.09 | Test Case Name: | Manage My Items
Use Case # |  | Preconditions: | ID needs to be setup with Security Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage My Items List
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Manage My Items list link is not viewable/clickable on quick access tab under Item Search |  | Link is not accessible |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 3.1 | Test Case Name: | Integration related fields
Use Case # |  | Preconditions: | ID needs to be setup with Security Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage Integration Related Fields on User/Customer Profile
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Customer Integration Data Maintenance tab |  | Should not display or allow updates |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Note on B2: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E7: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F7: Select from List. - Blank - Pass - Fail - Not Started
Note on G7: Enter Month / Day. Year defaults to current year unless entered.
Note on H7: Enter numeric portion of JIRA ticket.
Note on B19: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E24: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F24: Select from List. - Blank - Pass - Fail - Not Started
Note on G24: Enter Month / Day. Year defaults to current year unless entered.
Note on H24: Enter numeric portion of JIRA ticket.
Note on B36: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E41: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F41: Select from List. - Blank - Pass - Fail - Not Started
Note on G41: Enter Month / Day. Year defaults to current year unless entered.
Note on H41: Enter numeric portion of JIRA ticket.
Note on B53: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E58: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F58: Select from List. - Blank - Pass - Fail - Not Started
Note on G58: Enter Month / Day. Year defaults to current year unless entered.
Note on H58: Enter numeric portion of JIRA ticket.
Note on B70: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E75: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F75: Select from List. - Blank - Pass - Fail - Not Started
Note on G75: Enter Month / Day. Year defaults to current year unless entered.
Note on H75: Enter numeric portion of JIRA ticket.
Note on B86: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E91: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F91: Select from List. - Blank - Pass - Fail - Not Started
Note on G91: Enter Month / Day. Year defaults to current year unless entered.
Note on H91: Enter numeric portion of JIRA ticket.
Note on B103: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E108: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F108: Select from List. - Blank - Pass - Fail - Not Started
Note on G108: Enter Month / Day. Year defaults to current year unless entered.
Note on H108: Enter numeric portion of JIRA ticket.
Note on B120: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E125: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F125: Select from List. - Blank - Pass - Fail - Not Started
Note on G125: Enter Month / Day. Year defaults to current year unless entered.
Note on H125: Enter numeric portion of JIRA ticket.
Note on B136: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E141: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F141: Select from List. - Blank - Pass - Fail - Not Started
Note on G141: Enter Month / Day. Year defaults to current year unless entered.
Note on H141: Enter numeric portion of JIRA ticket.
Note on B154: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E159: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F159: Select from List. - Blank - Pass - Fail - Not Started
Note on G159: Enter Month / Day. Year defaults to current year unless entered.
Note on H159: Enter numeric portion of JIRA ticket.
Note on B171: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E176: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F176: Select from List. - Blank - Pass - Fail - Not Started
Note on G176: Enter Month / Day. Year defaults to current year unless entered.
Note on H176: Enter numeric portion of JIRA ticket.

## 4. CSR
Test Case # | 4 | Test Case Name: | Manage External Customers and Users |  | Tester Name:
Use Case # |  | Preconditions: | ID needs to be setup with CSR Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is able to manage external customers and users
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Customer Search |  | Can search for customers |  | Not Started
2 | Manage customer profile link displays |  | Manage customer profile link can be selected |  | Not Started
3 | Corporate and Manage customer rules tabs are available |  | Can select and manage data on these two tabs |  | Not Started
4 | Cannot create customers |  | • |  | Not Started
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 4.01 | Test Case Name: | Manage Internal Users
Use Case # |  | Preconditions: | ID needs to be setup with CSR Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage internal users
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Cannot Manage User Profile for internal users |  | Link to Manage User Profile is inactive for internal users |  | Not Started
2 | Can Manage Customer Profile for external users |  | Link to Manage Customer Profile is active for external users |  | Not Started
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 4.02 | Test Case Name: | Manage/Create Order
Use Case # |  | Preconditions: | ID needs to be setup with CSR Admin only User_Role. Determine which divisions user can maintain
DDD ID:
Req. # |  | Notes: | User is able to read, create and manage orders at division level
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Menu options available |  | Create Order option available on left hand side |  | Not Started
2 | Can create new orders |  | • |  | Not Started
3 | Can search for orders |  | • |  | Not Started
4 | Can manage orders in correct status |  | • |  | Not Started
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 4.03 | Test Case Name: | Manage Division Profile
Use Case # |  | Preconditions: | ID needs to be setup with CSR Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage the Division Profile
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | The Division Search link is not active |  | Division Search tab is not active |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | • | `
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 4.04 | Test Case Name: | Manage Promotions & Coupons through SBC
Use Case # |  | Preconditions: | ID needs to be setup with CSR Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage Promotions and Coupons through SBC
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Try to logon to SBC |  | User should not be able to access Promotions or Coupons SBC |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 4.05 | Test Case Name: | Manage Entitlements through SBC
Use Case # |  | Preconditions: | ID needs to be setup with CSR Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manange Entitlements through SBC
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Try to logon to SBC |  | User should not be able to access Entitlements in SBC |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 4.06 | Test Case Name: | Manage News
Use Case # |  | Preconditions: | ID needs to be setup with CSR Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to access News
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Cannot search or create news articles |  | Manage Article tab is not active |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 4.07 | Test Case Name: | Reset Passwords
Use Case # |  | Preconditions: | ID needs to be setup with CSR Admin only User_Role, Divisions need to be defined for user
DDD ID:
Req. # |  | Notes: | User is able to reset passwords
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Reset user password should display when viewing user detail |  | Should be able to use reset password option on the tasks menu or should be able to go into manage customer profile to reset password |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 4.08 | Test Case Name: | Narrow by Catalog
Use Case # |  | Preconditions: | ID needs to be setup with CSR Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able set the catalog narrow by search in SBC
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Try to logon to SBC |  | User should not be able to access narrow by search in SBC |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 4.09 | Test Case Name: | Manage My Items
Use Case # |  | Preconditions: | ID needs to be setup with CSR Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage My Items List
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Manage My Items list link is not viewable/clickable on quick access tab under Item Search |  | Link is not accessible |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 4.1 | Test Case Name: | Integration related fields
Use Case # |  | Preconditions: | ID needs to be setup with CSR Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage Integration Related Fields on User/Customer Profile
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Customer Integration Data Maintenance tab |  | Should not display or allow updates |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Note on B2: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E7: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F7: Select from List. - Blank - Pass - Fail - Not Started
Note on G7: Enter Month / Day. Year defaults to current year unless entered.
Note on H7: Enter numeric portion of JIRA ticket.
Note on B19: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E24: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F24: Select from List. - Blank - Pass - Fail - Not Started
Note on G24: Enter Month / Day. Year defaults to current year unless entered.
Note on H24: Enter numeric portion of JIRA ticket.
Note on B36: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E41: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F41: Select from List. - Blank - Pass - Fail - Not Started
Note on G41: Enter Month / Day. Year defaults to current year unless entered.
Note on H41: Enter numeric portion of JIRA ticket.
Note on B53: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E58: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F58: Select from List. - Blank - Pass - Fail - Not Started
Note on G58: Enter Month / Day. Year defaults to current year unless entered.
Note on H58: Enter numeric portion of JIRA ticket.
Note on B70: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E75: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F75: Select from List. - Blank - Pass - Fail - Not Started
Note on G75: Enter Month / Day. Year defaults to current year unless entered.
Note on H75: Enter numeric portion of JIRA ticket.
Note on B86: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E91: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F91: Select from List. - Blank - Pass - Fail - Not Started
Note on G91: Enter Month / Day. Year defaults to current year unless entered.
Note on H91: Enter numeric portion of JIRA ticket.
Note on B103: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E108: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F108: Select from List. - Blank - Pass - Fail - Not Started
Note on G108: Enter Month / Day. Year defaults to current year unless entered.
Note on H108: Enter numeric portion of JIRA ticket.
Note on B120: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E125: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F125: Select from List. - Blank - Pass - Fail - Not Started
Note on G125: Enter Month / Day. Year defaults to current year unless entered.
Note on H125: Enter numeric portion of JIRA ticket.
Note on B136: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E141: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F141: Select from List. - Blank - Pass - Fail - Not Started
Note on G141: Enter Month / Day. Year defaults to current year unless entered.
Note on H141: Enter numeric portion of JIRA ticket.
Note on B154: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E159: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F159: Select from List. - Blank - Pass - Fail - Not Started
Note on G159: Enter Month / Day. Year defaults to current year unless entered.
Note on H159: Enter numeric portion of JIRA ticket.
Note on B171: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E176: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F176: Select from List. - Blank - Pass - Fail - Not Started
Note on G176: Enter Month / Day. Year defaults to current year unless entered.
Note on H176: Enter numeric portion of JIRA ticket.

## 5. Promotion Admin
Test Case # | 5 | Test Case Name: | Manage External Customers and Users |  | Tester Name:
Use Case # |  | Preconditions: | ID needs to be setup with Promotion Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage external customers and users
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Customer Search |  | Cannot search for customers |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 5.01 | Test Case Name: | Manage Internal Users
Use Case # |  | Preconditions: | ID needs to be setup with Promotion Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage internal users
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Cannot Manage User Profile for internal users |  | Link to Manage User Profile is inactive for internal users |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 5.02 | Test Case Name: | Manage/Create Order
Use Case # |  | Preconditions: | ID needs to be setup with Promotion Admin only User_Role. Determine which divisions user can maintain
DDD ID:
Req. # |  | Notes: | User is not able to read, create or manage orders at division level
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Cannot create an order |  | Create Order is not available on left hand side |  | Not Started
2 | Cannot search for orders |  | If user clicks on find order, error occurs |  | Not Started
3 | User should not have access to Order Search |  | • |  | Not Started
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 5.03 | Test Case Name: | Manage Division Profile
Use Case # |  | Preconditions: | ID needs to be setup with Promotion Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage the Division Profile
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | The Division Search link is not active |  | Division Search tab is not active |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | • | `
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 5.04 | Test Case Name: | Manage Promotions & Coupons through SBC
Use Case # |  | Preconditions: | ID needs to be setup with Promotion Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is able to manage Promotions and Coupons through SBC
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | User logs on to SBC |  | User is able to log on to SBC |  | Not Started
2 | User successfully adds a coupon by clicking New Coupon |  | User is able to access the New Coupon function in SBC |  | Not Started
3 | User successfully finds a coupon by clicking Find Coupon |  | User is able to access all Coupon functions in SBC |  | Not Started
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 5.05 | Test Case Name: | Manage Entitlements through SBC
Use Case # |  | Preconditions: | ID needs to be setup with Promotion Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage Entitlements through SBC
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | User logs on to SBC |  | User is not able to access Entitlements in SBC |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 5.06 | Test Case Name: | Manage News
Use Case # |  | Preconditions: | ID needs to be setup with Promotion Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to access News
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Cannot search or create news articles |  | Manage Article tab is not active |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 5.07 | Test Case Name: | Reset Passwords
Use Case # |  | Preconditions: | ID needs to be setup with Promotion Admin only User_Role, Divisions need to be defined for user
DDD ID:
Req. # |  | Notes: | User is not able to reset passwords
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Reset user password does not display when viewing user detail |  | Reset User Password is not a given option. |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 5.08 | Test Case Name: | Narrow by Catalog
Use Case # |  | Preconditions: | ID needs to be setup with Promotion Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able set the catalog narrow by search in SBC
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | User logs on to SBC |  | User should not be able to access narrow by search in SBC |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 5.09 | Test Case Name: | Manage My Items
Use Case # |  | Preconditions: | ID needs to be setup with Promotion Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage My Items List
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Manage My Items list link is not viewable/clickable on quick access tab under Item Search |  | Link is not accessible |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 5.1 | Test Case Name: | Integration related fields
Use Case # |  | Preconditions: | ID needs to be setup with Promotion Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage Integration Related Fields on User/Customer Profile
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Customer Integration Data Maintenance tab |  | Should not display or allow updates |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Note on B2: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E7: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F7: Select from List. - Blank - Pass - Fail - Not Started
Note on G7: Enter Month / Day. Year defaults to current year unless entered.
Note on H7: Enter numeric portion of JIRA ticket.
Note on B19: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E24: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F24: Select from List. - Blank - Pass - Fail - Not Started
Note on G24: Enter Month / Day. Year defaults to current year unless entered.
Note on H24: Enter numeric portion of JIRA ticket.
Note on B36: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E41: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F41: Select from List. - Blank - Pass - Fail - Not Started
Note on G41: Enter Month / Day. Year defaults to current year unless entered.
Note on H41: Enter numeric portion of JIRA ticket.
Note on B53: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E58: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F58: Select from List. - Blank - Pass - Fail - Not Started
Note on G58: Enter Month / Day. Year defaults to current year unless entered.
Note on H58: Enter numeric portion of JIRA ticket.
Note on B70: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E75: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F75: Select from List. - Blank - Pass - Fail - Not Started
Note on G75: Enter Month / Day. Year defaults to current year unless entered.
Note on H75: Enter numeric portion of JIRA ticket.
Note on B86: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E91: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F91: Select from List. - Blank - Pass - Fail - Not Started
Note on G91: Enter Month / Day. Year defaults to current year unless entered.
Note on H91: Enter numeric portion of JIRA ticket.
Note on B103: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E108: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F108: Select from List. - Blank - Pass - Fail - Not Started
Note on G108: Enter Month / Day. Year defaults to current year unless entered.
Note on H108: Enter numeric portion of JIRA ticket.
Note on B120: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E125: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F125: Select from List. - Blank - Pass - Fail - Not Started
Note on G125: Enter Month / Day. Year defaults to current year unless entered.
Note on H125: Enter numeric portion of JIRA ticket.
Note on B136: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E141: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F141: Select from List. - Blank - Pass - Fail - Not Started
Note on G141: Enter Month / Day. Year defaults to current year unless entered.
Note on H141: Enter numeric portion of JIRA ticket.
Note on B154: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E159: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F159: Select from List. - Blank - Pass - Fail - Not Started
Note on G159: Enter Month / Day. Year defaults to current year unless entered.
Note on H159: Enter numeric portion of JIRA ticket.
Note on B171: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E176: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F176: Select from List. - Blank - Pass - Fail - Not Started
Note on G176: Enter Month / Day. Year defaults to current year unless entered.
Note on H176: Enter numeric portion of JIRA ticket.

## 6. Catalog Admin
Test Case # | 6 | Test Case Name: | Manage External Customers and Users |  | Tester Name:
Use Case # |  | Preconditions: | ID needs to be setup with Catalog Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage external customers and users
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Customer Search |  | Cannot search for customers |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 6.01 | Test Case Name: | Manage Internal Users
Use Case # |  | Preconditions: | ID needs to be setup with Catalog Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage internal users
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Cannot Manage User Profile for internal users |  | Link to Manage User Profile is inactive for internal users |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 6.02 | Test Case Name: | Manage/Create Order
Use Case # |  | Preconditions: | ID needs to be setup with Catalog Admin only User_Role. Determine which divisions user can maintain
DDD ID:
Req. # |  | Notes: | User is not able to read, create or manage orders at division level
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Cannot create an order |  | Create Order is not available on left hand side |  | Not Started
2 | Cannot search for orders |  | If user clicks on find order, error occurs |  | Not Started
3 | User should not have access to Order Search |  | • |  | Not Started
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 6.03 | Test Case Name: | Manage Division Profile
Use Case # |  | Preconditions: | ID needs to be setup with Catalog Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage the Division Profile
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | The Division Search link is not active |  | Division Search tab is not active |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | • | `
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 6.04 | Test Case Name: | Manage Promotions & Coupons through SBC
Use Case # |  | Preconditions: | ID needs to be setup with Catalog Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage Promotions and Coupons through SBC
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Try to logon to SBC |  | User should not be able to access Promotions or Coupons SBC |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 6.05 | Test Case Name: | Manage Entitlements through SBC
Use Case # |  | Preconditions: | ID needs to be setup with Catalog Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is able to access SBC to manage Entitlements
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | User is able to logon to SBC |  | Customer Entitlements is visible |  | Not Started
2 | User is able to set up new entitlement |  | • |  | Not Started
3 | User is able to find entitlements |  | • |  | Not Started
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 6.06 | Test Case Name: | Manage News
Use Case # |  | Preconditions: | ID needs to be setup with Catalog Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to access News
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Cannot search or create news articles |  | Manage Articles tab is not active |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 6.07 | Test Case Name: | Reset Passwords
Use Case # |  | Preconditions: | ID needs to be setup with Catalog Admin only User_Role, Divisions need to be defined for user
DDD ID:
Req. # |  | Notes: | User is not able to reset passwords
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Reset user password does not display when viewing user detail |  | Reset User Password is not a given option. |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 6.08 | Test Case Name: | Narrow by Catalog
Use Case # |  | Preconditions: | ID needs to be setup with Catalog Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is able set the catalog narrow by search in SBC
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | User logs on to SBC |  | • |  | Not Started
2 | User clicks "Manage Catalogs" |  | • |  | Not Started
3 | User selects the catalog they want to manage |  | • |  | Not Started
4 | User selects a category from the Catalog Hierarchy |  | • |  | Not Started
5 | User clicks "Manage Attribute Assignment" link (the system will show all attributes for that category) |  | The "Selling Usages" - "For Filter" checkbox indicates whether that attribute is a Narrow By for the selected category level |  | Not Started
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 6.09 | Test Case Name: | Manage My Items
Use Case # |  | Preconditions: | ID needs to be setup with Catalog Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage My Items List
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Manage My Items list link is not viewable/clickable on quick access tab under Item Search |  | Link is not accessible |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 6.1 | Test Case Name: | Integration related fields
Use Case # |  | Preconditions: | ID needs to be setup with Catalog Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage Integration Related Fields on User/Customer Profile
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Customer Integration Data Maintenance tab |  | Does not display or allow updates |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Note on B2: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E7: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F7: Select from List. - Blank - Pass - Fail - Not Started
Note on G7: Enter Month / Day. Year defaults to current year unless entered.
Note on H7: Enter numeric portion of JIRA ticket.
Note on B19: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E24: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F24: Select from List. - Blank - Pass - Fail - Not Started
Note on G24: Enter Month / Day. Year defaults to current year unless entered.
Note on H24: Enter numeric portion of JIRA ticket.
Note on B36: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E41: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F41: Select from List. - Blank - Pass - Fail - Not Started
Note on G41: Enter Month / Day. Year defaults to current year unless entered.
Note on H41: Enter numeric portion of JIRA ticket.
Note on B53: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E58: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F58: Select from List. - Blank - Pass - Fail - Not Started
Note on G58: Enter Month / Day. Year defaults to current year unless entered.
Note on H58: Enter numeric portion of JIRA ticket.
Note on B70: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E75: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F75: Select from List. - Blank - Pass - Fail - Not Started
Note on G75: Enter Month / Day. Year defaults to current year unless entered.
Note on H75: Enter numeric portion of JIRA ticket.
Note on B86: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E91: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F91: Select from List. - Blank - Pass - Fail - Not Started
Note on G91: Enter Month / Day. Year defaults to current year unless entered.
Note on H91: Enter numeric portion of JIRA ticket.
Note on B103: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E108: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F108: Select from List. - Blank - Pass - Fail - Not Started
Note on G108: Enter Month / Day. Year defaults to current year unless entered.
Note on H108: Enter numeric portion of JIRA ticket.
Note on B120: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E125: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F125: Select from List. - Blank - Pass - Fail - Not Started
Note on G125: Enter Month / Day. Year defaults to current year unless entered.
Note on H125: Enter numeric portion of JIRA ticket.
Note on B136: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E141: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F141: Select from List. - Blank - Pass - Fail - Not Started
Note on G141: Enter Month / Day. Year defaults to current year unless entered.
Note on H141: Enter numeric portion of JIRA ticket.
Note on B154: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E159: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F159: Select from List. - Blank - Pass - Fail - Not Started
Note on G159: Enter Month / Day. Year defaults to current year unless entered.
Note on H159: Enter numeric portion of JIRA ticket.
Note on B171: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E176: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F176: Select from List. - Blank - Pass - Fail - Not Started
Note on G176: Enter Month / Day. Year defaults to current year unless entered.
Note on H176: Enter numeric portion of JIRA ticket.

## 7. Manage My Items Admin
Test Case # | 7 | Test Case Name: | Manage External Customers and Users |  | Tester Name:
Use Case # |  | Preconditions: | ID needs to be setup with Manage My Items Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage external customers and users
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Customer Search |  | Cannot search for customers |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 7.01 | Test Case Name: | Manage Internal Users
Use Case # |  | Preconditions: | ID needs to be setup with Manage My Items Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage internal users
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Cannot Manage User Profile for internal users |  | Link to Manage User Profile is inactive for internal users |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 7.02 | Test Case Name: | Manage/Create Order
Use Case # |  | Preconditions: | ID needs to be setup with Manage My Items Admin only User_Role. Determine which divisions user can maintain
DDD ID:
Req. # |  | Notes: | User is not able to read, create or manage orders at division level
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Cannot create an order |  | Create Order is not available on left hand side |  | Not Started
2 | Cannot search for orders |  | If user clicks on find order, error occurs |  | Not Started
3 | User should not have access to Order Search |  | • |  | Not Started
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 7.03 | Test Case Name: | Manage Division Profile
Use Case # |  | Preconditions: | ID needs to be setup with Manage My Items Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage the Division Profile
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | The Division Search link is not active |  | Division Search tab is not active |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | • | `
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 7.04 | Test Case Name: | Manage Promotions & Coupons through SBC
Use Case # |  | Preconditions: | ID needs to be setup with Manage My Items Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage Promotions and Coupons through SBC
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Try to logon to SBC |  | User should not be able to access Promotions or Coupons SBC |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 7.05 | Test Case Name: | Manage Entitlements through SBC
Use Case # |  | Preconditions: | ID needs to be setup with Manage My Items Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to access SBC to manage Entitlements
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Try to logon to SBC |  | User is not able to access Entitlements in SBC |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 7.06 | Test Case Name: | Manage News
Use Case # |  | Preconditions: | ID needs to be setup with Manage My Items Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to access News
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Cannot search or create news articles |  | Manage Articles tab is not active |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 7.07 | Test Case Name: | Reset Passwords
Use Case # |  | Preconditions: | ID needs to be setup with Manage My Items Admin only User_Role, Divisions need to be defined for user
DDD ID:
Req. # |  | Notes: | User is not able to reset passwords
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Reset user password does not display when viewing user detail |  | Reset User Password is not a given option. |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 7.08 | Test Case Name: | Narrow by Catalog
Use Case # |  | Preconditions: | ID needs to be setup with Manage My Items Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able set the catalog narrow by search in SBC
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Try to logon to SBC |  | User should not be able to access narrow by search in SBC |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 7.09 | Test Case Name: | Manage My Items
Use Case # |  | Preconditions: | ID needs to be setup with Manage My Items Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is able to manage My Items List
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | This user can click "Manage My Items" |  | User Should have access to all features within manage my items |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 7.1 | Test Case Name: | Integration related fields
Use Case # |  | Preconditions: | ID needs to be setup with Manage My Items Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage Integration Related Fields on User/Customer Profile
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Customer Integration Data Maintenance tab |  | Should not display or allow updates |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Note on B2: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E7: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F7: Select from List. - Blank - Pass - Fail - Not Started
Note on G7: Enter Month / Day. Year defaults to current year unless entered.
Note on H7: Enter numeric portion of JIRA ticket.
Note on B19: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E24: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F24: Select from List. - Blank - Pass - Fail - Not Started
Note on G24: Enter Month / Day. Year defaults to current year unless entered.
Note on H24: Enter numeric portion of JIRA ticket.
Note on B36: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E41: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F41: Select from List. - Blank - Pass - Fail - Not Started
Note on G41: Enter Month / Day. Year defaults to current year unless entered.
Note on H41: Enter numeric portion of JIRA ticket.
Note on B53: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E58: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F58: Select from List. - Blank - Pass - Fail - Not Started
Note on G58: Enter Month / Day. Year defaults to current year unless entered.
Note on H58: Enter numeric portion of JIRA ticket.
Note on B70: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E75: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F75: Select from List. - Blank - Pass - Fail - Not Started
Note on G75: Enter Month / Day. Year defaults to current year unless entered.
Note on H75: Enter numeric portion of JIRA ticket.
Note on B86: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E91: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F91: Select from List. - Blank - Pass - Fail - Not Started
Note on G91: Enter Month / Day. Year defaults to current year unless entered.
Note on H91: Enter numeric portion of JIRA ticket.
Note on B103: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E108: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F108: Select from List. - Blank - Pass - Fail - Not Started
Note on G108: Enter Month / Day. Year defaults to current year unless entered.
Note on H108: Enter numeric portion of JIRA ticket.
Note on B120: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E125: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F125: Select from List. - Blank - Pass - Fail - Not Started
Note on G125: Enter Month / Day. Year defaults to current year unless entered.
Note on H125: Enter numeric portion of JIRA ticket.
Note on B136: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E141: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F141: Select from List. - Blank - Pass - Fail - Not Started
Note on G141: Enter Month / Day. Year defaults to current year unless entered.
Note on H141: Enter numeric portion of JIRA ticket.
Note on B154: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E159: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F159: Select from List. - Blank - Pass - Fail - Not Started
Note on G159: Enter Month / Day. Year defaults to current year unless entered.
Note on H159: Enter numeric portion of JIRA ticket.
Note on B171: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E176: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F176: Select from List. - Blank - Pass - Fail - Not Started
Note on G176: Enter Month / Day. Year defaults to current year unless entered.
Note on H176: Enter numeric portion of JIRA ticket.

## 8. Support Desk
Test Case # | 8 | Test Case Name: | Manage External Customers and Users |  | Tester Name:
Use Case # |  | Preconditions: | ID needs to be setup with Support Desk only User_Role
DDD ID:
Req. # |  | Notes: | User is able to manage external customers and users
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Customer Search |  | Can search for customers |  | Not Started
2 | Manage customer profile link displays |  | Manage customer profile link can be selected |  | Not Started
3 | Corporate and Manage customer rules tabs are available |  | Can select and manage data on these two tabs |  | Not Started
4 | Cannot create customers |  | • |  | Not Started
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 8.01 | Test Case Name: | Manage Internal Users
Use Case # |  | Preconditions: | ID needs to be setup with Support Desk only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage internal users
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Cannot Manage User Profile for internal users |  | Link to Manage User Profile is inactive for internal users |  | Not Started
2 | Can Manage Customer Profile for external users |  | Link to Manage Customer Profile is active for external users |  | Not Started
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 8.02 | Test Case Name: | Manage/Create Order
Use Case # |  | Preconditions: | ID needs to be setup with Support Desk only User_Role. Determine which divisions user can maintain
DDD ID:
Req. # |  | Notes: | User is able to read, create and manage orders at division level
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Menu options available |  | Create Order option available on left hand side |  | Not Started
2 | Can create new orders |  | • |  | Not Started
3 | Can search for orders |  | • |  | Not Started
4 | Can manage orders in correct status |  | • |  | Not Started
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 8.03 | Test Case Name: | Manage Division Profile
Use Case # |  | Preconditions: | ID needs to be setup with Support Desk only User_Role
DDD ID:
Req. # |  | Notes: | User is able to manage the Division Profile
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Can click Division Link |  |  |  | Not Started
2 | Can search by Brand or Division |  |  |  | Not Started
3 |  |  | •
4 |  |  | •
5 |  |  | •
6 |  |  | •
7 | • |  | • | `
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 8.04 | Test Case Name: | Manage Promotions & Coupons through SBC
Use Case # |  | Preconditions: | ID needs to be setup with Support Desk only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage Promotions and Coupons through SBC
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Try to logon to SBC |  | User should not be able to access Promotions or Coupons SBC |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 8.05 | Test Case Name: | Manage Entitlements through SBC
Use Case # |  | Preconditions: | ID needs to be setup with Support Desk only User_Role
DDD ID:
Req. # |  | Notes: | User is able to access SBC to manage Entitlements
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | User is able to logon to SBC |  | Customer Entitlements is visible |  | Not Started
2 | User is able to set up new entitlement |  | • |  | Not Started
3 | User is able to find entitlements |  | • |  | Not Started
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 8.06 | Test Case Name: | Manage News
Use Case # |  | Preconditions: | ID needs to be setup with Support Desk only User_Role
DDD ID:
Req. # |  | Notes: | User is able to read and update News
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Manage Articles Link is visible and clickable |  | Manage Article tab appears |  | Not Started
2 | Can search news articles |  | • |  | Not Started
3 | Can create news articles |  | • |  | Not Started
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 8.07 | Test Case Name: | Reset Passwords
Use Case # |  | Preconditions: | ID needs to be setup with Support Desk only User_Role, Divisions need to be defined for user
DDD ID:
Req. # |  | Notes: | User is able to reset passwords
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Reset user password should display when viewing user detail |  | Should be able to use reset password option on the tasks menu or should be able to go into manage customer profile to reset password |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 8.08 | Test Case Name: | Narrow by Catalog
Use Case # |  | Preconditions: | ID needs to be setup with Support Desk only User_Role
DDD ID:
Req. # |  | Notes: | User is not able set the catalog narrow by search in SBC
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Try to logon to SBC |  | User can log on to SBC |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 8.09 | Test Case Name: | Manage My Items
Use Case # |  | Preconditions: | ID needs to be setup with Support Desk only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage My Items List
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Manage My Items list link is not viewable/clickable on quick access tab under Item Search |  | Link is not accessible |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 8.1 | Test Case Name: | Integration related fields
Use Case # |  | Preconditions: | ID needs to be setup with Support Desk only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage Integration Related Fields on User/Customer Profile
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Customer Integration Data Maintenance tab |  | Does not display or allow updates |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Note on B2: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E7: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F7: Select from List. - Blank - Pass - Fail - Not Started
Note on G7: Enter Month / Day. Year defaults to current year unless entered.
Note on H7: Enter numeric portion of JIRA ticket.
Note on B19: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E24: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F24: Select from List. - Blank - Pass - Fail - Not Started
Note on G24: Enter Month / Day. Year defaults to current year unless entered.
Note on H24: Enter numeric portion of JIRA ticket.
Note on B36: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E41: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F41: Select from List. - Blank - Pass - Fail - Not Started
Note on G41: Enter Month / Day. Year defaults to current year unless entered.
Note on H41: Enter numeric portion of JIRA ticket.
Note on B53: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E58: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F58: Select from List. - Blank - Pass - Fail - Not Started
Note on G58: Enter Month / Day. Year defaults to current year unless entered.
Note on H58: Enter numeric portion of JIRA ticket.
Note on B70: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E75: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F75: Select from List. - Blank - Pass - Fail - Not Started
Note on G75: Enter Month / Day. Year defaults to current year unless entered.
Note on H75: Enter numeric portion of JIRA ticket.
Note on B86: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E91: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F91: Select from List. - Blank - Pass - Fail - Not Started
Note on G91: Enter Month / Day. Year defaults to current year unless entered.
Note on H91: Enter numeric portion of JIRA ticket.
Note on B103: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E108: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F108: Select from List. - Blank - Pass - Fail - Not Started
Note on G108: Enter Month / Day. Year defaults to current year unless entered.
Note on H108: Enter numeric portion of JIRA ticket.
Note on B120: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E125: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F125: Select from List. - Blank - Pass - Fail - Not Started
Note on G125: Enter Month / Day. Year defaults to current year unless entered.
Note on H125: Enter numeric portion of JIRA ticket.
Note on B136: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E141: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F141: Select from List. - Blank - Pass - Fail - Not Started
Note on G141: Enter Month / Day. Year defaults to current year unless entered.
Note on H141: Enter numeric portion of JIRA ticket.
Note on B154: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E159: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F159: Select from List. - Blank - Pass - Fail - Not Started
Note on G159: Enter Month / Day. Year defaults to current year unless entered.
Note on H159: Enter numeric portion of JIRA ticket.
Note on B171: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E176: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F176: Select from List. - Blank - Pass - Fail - Not Started
Note on G176: Enter Month / Day. Year defaults to current year unless entered.
Note on H176: Enter numeric portion of JIRA ticket.

## 9. Integration Admin
Test Case # | 9 | Test Case Name: | Manage External Customers and Users |  | Tester Name:
Use Case # |  | Preconditions: | ID needs to be setup with Integration Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is able to manage external customers and users
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Customer Search |  | Can search for customers |  | Not Started
2 | Manage customer profile link displays |  | Manage customer profile link can be selected |  | Not Started
3 | Corporate and Manage customer rules tabs are available |  | Can select and manage data on these two tabs |  | Not Started
4 | Cannot create customers |  | • |  | Not Started
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 9.01 | Test Case Name: | Manage Internal Users
Use Case # |  | Preconditions: | ID needs to be setup with Integration Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage internal users
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Cannot Manage User Profile for internal users |  | Link to Manage User Profile is inactive for internal users |  | Not Started
2 | Can Manage Customer Profile for external users |  | Link to Manage Customer Profile is active for external users |  | Not Started
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 9.02 | Test Case Name: | Manage/Create Order
Use Case # |  | Preconditions: | ID needs to be setup with Integration Admin only User_Role. Determine which divisions user can maintain
DDD ID:
Req. # |  | Notes: | User is able to search for orders
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Can search for orders |  | Can access Reference Order Search |  | Not Started
2 | Can search for orders |  | Can access Customer Search |  | Not Started
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 9.03 | Test Case Name: | Manage Division Profile
Use Case # |  | Preconditions: | ID needs to be setup with Integration Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage the Division Profile
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | The Division Search link is not active |  | Division Search tab is not active |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | • | `
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 9.04 | Test Case Name: | Manage Promotions & Coupons through SBC
Use Case # |  | Preconditions: | ID needs to be setup with Integration Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage Promotions and Coupons through SBC
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Try to logon to SBC |  | User should not be able to access Promotions or Coupons SBC |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 9.05 | Test Case Name: | Manage Entitlements through SBC
Use Case # |  | Preconditions: | ID needs to be setup with Integration Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to access SBC to manage Entitlements
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Try to logon to SBC |  | User is not able to access Entitlements in SBC |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 9.06 | Test Case Name: | Manage News
Use Case # |  | Preconditions: | ID needs to be setup with Integration Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to access News
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Cannot search or create news articles |  | Manage Article tab does not appear |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 9.07 | Test Case Name: | Reset Passwords
Use Case # |  | Preconditions: | ID needs to be setup with Integration Admin only User_Role, Divisions need to be defined for user
DDD ID:
Req. # |  | Notes: | User is not able to reset passwords
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Reset user password does not display when viewing user detail |  | Reset User Password is not a given option. |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 9.08 | Test Case Name: | Narrow by Catalog
Use Case # |  | Preconditions: | ID needs to be setup with Integration Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able set the catalog narrow by search in SBC
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Try to logon to SBC |  | User should not be able to access narrow by search in SBC |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 9.09 | Test Case Name: | Manage My Items
Use Case # |  | Preconditions: | ID needs to be setup with Integration Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is not able to manage My Items List
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Manage My Items list link is not viewable/clickable on quick access tab under Item Search |  | Link is not accessible |  | Not Started
2 | • |  | •
3 | • |  | •
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Test Case # | 9.1 | Test Case Name: | Integration related fields
Use Case # |  | Preconditions: | ID needs to be setup with Integration Admin only User_Role
DDD ID:
Req. # |  | Notes: | User is able to manage Integration Related Fields on User/Customer Profile
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Customer Search |  | Can search for customers |  | Not Started
2 | Manage customer profile link displays |  | Manage customer profile link can be selected |  | Not Started
3 | Customer Integration Data Maintenance tab is available |  | Fields can be read and updated |  | Not Started
4 | • |  | •
5 | • |  | •
6 | • |  | •
7 | • |  | •
8 | • |  | •
9 | • |  | • |  | Not Started
Note on B2: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E7: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F7: Select from List. - Blank - Pass - Fail - Not Started
Note on G7: Enter Month / Day. Year defaults to current year unless entered.
Note on H7: Enter numeric portion of JIRA ticket.
Note on B19: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E24: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F24: Select from List. - Blank - Pass - Fail - Not Started
Note on G24: Enter Month / Day. Year defaults to current year unless entered.
Note on H24: Enter numeric portion of JIRA ticket.
Note on B36: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E41: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F41: Select from List. - Blank - Pass - Fail - Not Started
Note on G41: Enter Month / Day. Year defaults to current year unless entered.
Note on H41: Enter numeric portion of JIRA ticket.
Note on B53: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E58: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F58: Select from List. - Blank - Pass - Fail - Not Started
Note on G58: Enter Month / Day. Year defaults to current year unless entered.
Note on H58: Enter numeric portion of JIRA ticket.
Note on B70: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E75: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F75: Select from List. - Blank - Pass - Fail - Not Started
Note on G75: Enter Month / Day. Year defaults to current year unless entered.
Note on H75: Enter numeric portion of JIRA ticket.
Note on B86: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E91: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F91: Select from List. - Blank - Pass - Fail - Not Started
Note on G91: Enter Month / Day. Year defaults to current year unless entered.
Note on H91: Enter numeric portion of JIRA ticket.
Note on B103: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E108: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F108: Select from List. - Blank - Pass - Fail - Not Started
Note on G108: Enter Month / Day. Year defaults to current year unless entered.
Note on H108: Enter numeric portion of JIRA ticket.
Note on B120: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E125: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F125: Select from List. - Blank - Pass - Fail - Not Started
Note on G125: Enter Month / Day. Year defaults to current year unless entered.
Note on H125: Enter numeric portion of JIRA ticket.
Note on B136: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E141: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F141: Select from List. - Blank - Pass - Fail - Not Started
Note on G141: Enter Month / Day. Year defaults to current year unless entered.
Note on H141: Enter numeric portion of JIRA ticket.
Note on B154: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E159: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F159: Select from List. - Blank - Pass - Fail - Not Started
Note on G159: Enter Month / Day. Year defaults to current year unless entered.
Note on H159: Enter numeric portion of JIRA ticket.
Note on B171: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E176: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F176: Select from List. - Blank - Pass - Fail - Not Started
Note on G176: Enter Month / Day. Year defaults to current year unless entered.
Note on H176: Enter numeric portion of JIRA ticket.

## 0. Dropdown Values (hidden)
Pass
Fail
Not Started