## Instructions (hidden)
Coming Soon….
Naming Conventions - Chris
How to use Summary Tab - Chris
How to Use Test Case Tab - Barb
Test Case Tab - Using the Table - Barry
HEADER: Populate header information including Use Case, DDD, and Requirement info to provide traceability. Also be sure to identify any required PreConditions such as test cases which should already have been completed before starting the current test case. Notes may be used for any instructions which may be relevant to the tester.
STEP #:
USER INPUT:
EXPECTED RESULTS:
ACTUAL RESULTS / COMMENTS:
PASS / FAIL:
DATE EXECUTED:
JIRA #: Any significant failure should be documented in JIRA. "Significant" may be characterized as " ". Any departure from the expected result must be captured in the Actual Results / Comments field, but full details of "Significant" failures must be documented in JIRA for appropriate follow-up and assignment for resolution. Enter the numeric portion of the JIRA ticket in the JIRA # cell. This spreadsheet assumes all JIRA tickets will be associated with the XNGT (xpedx.com Next Gen Test Phase) project and assign that JIRA prefix. If the relevant JIRA ticket should be associated with another JIRA project, simply type in the entire JIRA ticket ID. (e.g. PCI Compliance might be PCI-123).
Other Considerations:
• Consider allocating dedicated space to identify predecessor Test Cases.
• Word wrap doesn't function in columns B-C because of merged cells. (Column D works fine.) We could resolve by moving TestCase#, UseCase #, etc to the far right where lower cells are unlikely to require word wrap.
• Consider a Status to identify follow-up needed. (Suspend?) Unexpected results may not indicate failure, but might justify conversation with the business, or disclose previously unforseen design considerations. Follow-up for any step might keep the overall test in a "Suspended" status. This would require complete documentation in JIRA.
Add ExecutedBY field
User Types (Roles)
External: Buyer (Can checkout, view invoices, view reports, view prices)
External: Customer Administrator (Has all Buyer privileges AND can maintain subordinate users)
User Profile Flags: Can checkout; Can view invoices online; Can view reports; Can view prices. (All are checked by default)

## Summary
Test Case Title: | Customer & User Profile Series
Test Case # | Test Case Name | Status | Date | Name of Tester
UC-82 | Confirm appropriate User Profile fields Can be READ
UC-83 | Confirm appropriate User Profile fields Can be UPDATED
TC 86.1 | Call Center: Customer Profile - Max Order Value
TC 86.2 | Call Center: Customer Profile - Min Order Value
TC 89.1 | Call Center: Create Customer Contact
92 | User Profile - Internal
93 | User Profile - External General
93.1 | User Profile - External: Active / Suspend
93.2 | User Profile - External: User Roles
93.3 | User Profile - External: PW Reset & General Info
93.4 | User Profile - External: Default Ship-To
93.5 | User Profile - External: Assigned Locations
93.6 | User Profile - External: Min/Max Order Amount
93.7 | User Profile - External: Preferred Catalog View
93.8 | User Profile - External: Preferred Catalog
93.9 | User Profile - External: Order Confirmation Address List
93.10 | User Profile - External: Receive Emails
93.11 | User Profile - External: Email Address for Invoice
93.12 | User Profile - External: Manage PO# List
93.13 | User Profile - External: Reactivated User Retains Data (This covers UC79)
|  | Number | Percent
| Total Test Cases | 20
| Passed | 0 | 0%
| Failed | 0 | 0%
| (Cannot be completely tested) Incomplete | 0 | 0%
| Remaining to Test | 20 | 100%
Complete
Incomplete
Not Started

## 82-ReadUserPrf
Test Case # |  | Test Case Name: | Call Center: Customer Profile - User Profile Fields Can Be READ (Not Edited)
Use Case # | 82 | Preconditions: | CSR is logged into Call Center.
DDD ID:
Req. # |  | Notes: | Need to Create an EXTERNAL User by first finding a customer, then adding a new user.
Step # | User Input |  | Expected Results | Actual Results / Comments | Status | Date Executed | JIRA #
1 | • Select Quick Access > Customer Search > Find Customer F9. • Organization Name starts with "PEET". • Click Search F7. |  | • Customer Search Results panel displays. |  | Not Started
2 | • Double-click the first Customer ID, and note the Customer Number at right. |  | • Customer Detail screen displays. |  | Not Started
3 | • Select Tasks > Customer > Create Customer Contact |  | • New Contact tab displays. • This should be revised to reflect latest User Profile screen designs. |  | Not Started
4 | • The following fields are displayed: FirstName; LastName; Address1/2/3; City; State/Province; Country; Zip; Zip4; PhoneNumber; FaxNumber; UserId; EmployeeID; UserType; UserAdminRole; BuyerRole; ApproverRole; ViewPricesRole; ViewReportsRole; ViewInvoicesRole; EstimatorRole; StockCheckRole; MinOrderAmount; MaxOrderAmount; UserEmailAddress; AdditionalEmailAddress; EmailAddressForInvoice; PoList; ReceiveOrderConfirmationEmailFormat; PreferredCatalog; AssignedCustLocations; DefaultShipTo; ReceiveOrderConfirmationEmailFlag; ReceiveOrderCancellationEmailFlag; ReceiveOrderUpdateEmailByCSR; ReceiveOrderShipmentEmail; ReceiveBackorderEmail; ManageQuickLinks; AcceptTandC; LastLoginDate; B2BPreferredCatalogView; |  | • All fields are displayed. • (Blue fields are not editable.) • (Red fields appear under Modify link.) |  | Not Started
5 | • In Primary User Information, enter User Name; Login; & email address. (Note: UserName is the full common name which will be associated with the UserID - this can be edited later. Login is typically the user's IP Network ID in lower case - this cannot be edited later. The entered Email address will be sent a system generated initial account password.) • Under Contact Address, click Modify link. • Populate Primary Info First & Last Name. • Select User Role = CSR • Click Apply F4 and Next F11. |  | • New User Account is created with UserName and Login Name as entered. • Contact Address info is retained and displayed. • Queue Subscriptions panel is displayed. |  | Not Started
6 | • From the Available Queues panel, select all listed Queues, and click Assign F5. |  | • All selected Queues are moved to the Assigned Queues panel. |  | Not Started
7 | • Click Confirm F8. |  | • User Management tab is closed, Confirmation msg displays in the upper right portion of the screen, and you are returned to the Quick Access tab. |  | Not Started
8 | • Select Tasks > Modify User • Click Search F7 |  | • User Management tab displays. • The above new User Account appears in the list of User Search Results. |  | Not Started
9 | • Double-click the new User Account. |  | • Details of the new User Account are displayed in several panels as follows: Primary User Information; Contact Address; Billing Address; User Roles. |  | Not Started
10 | • Confirm that the following fields are NOT editable: EmployeeID; UserType; AcceptTandC; LastLoginDate; |  | • Listed fields are not editable. |  | Not Started
Note on B1: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E6: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F6: Select from List. - Blank - Pass - Fail - Not Started
Note on G6: Enter Month / Day. Year defaults to current year unless entered.
Note on H6: Enter numeric portion of JIRA ticket.

## 83-UpdUserPrf
Test Case # |  | Test Case Name: | Call Center: Customer Profile - User Profile Fields Can Be EDITED
Use Case # | 83 | Preconditions: | CSR is logged into Call Center and navigated to an existing User Account.
DDD ID:
Req. # |  | Notes: | Need to Create an EXTERNAL User by first finding a customer, then adding a new Customer Contact.
Step # | User Input |  | Expected Results | Actual Results / Comments | Status | Date Executed | JIRA #
1 | • In CALL CENTER > User Profile > General Info section, confirm that the following fields CAN be edited: - User Status; - User Role checkboxes: UserAdminRole; BuyerRole; ApproverRole; ViewPricesRole; ViewReportsRole; ViewInvoicesRole; EstimatorRole; StockCheckRole; FirstName; LastName; email Address; Phone; Fax; Address Line 1/2/3; City; State/Province; Country; Zip; Zip4; |  | • All fields are displayed and can be edited. |  | Not Started
2 | • In CALL CENTER > User Profile > Locations section, confirm that the following fields CAN be edited: Default ShipTo Assigned Locations; |  | • All fields are displayed and can be edited. - Default ShipTo may be changed. - Assigned Locations may be Added, Deleted, Expanded and Collapsed. |  | Not Started
3 | • In CALL CENTER > User Profile > Site Settings section, confirm that the following fields CAN be edited: MinOrderAmount; MaxOrderAmount; Preferred Catalog View; Preferred Catalog; Order Confirmation Address List Receive Emails EmailAddressForInvoice; Manage PO List; |  | • All fields are displayed and can be edited as described. - Prder Confirmation Address List entries may be Added, Edited, Deleted. - Receive Emails checkboxes may be selected & deselected. Receive Order Confirmation Email is checked by Default. - Email Address for Invoice: List permits addition of New Addresses; Edit and Deletion of existing addresses. - Manage PO# List: List permits addition of New PO#; Edit and Deletion of existing POs. |  | Not Started
Note on B1: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E6: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F6: Select from List. - Blank - Pass - Fail - Not Started
Note on G6: Enter Month / Day. Year defaults to current year unless entered.
Note on H6: Enter numeric portion of JIRA ticket.

## 86-MaxOrdVal
Test Case # | 86.1 | Test Case Name: | Call Center: Customer Profile - Max Order Value
Use Case # | 86 | Preconditions: | External User and his Customer are entitled to items which can be combined to a value in excess of MaxOrdValue. External User Profile has been created and configured with a known Max Order Value.
DDD ID:
Req. # |  | Notes: | Recall that items may only be viewed / ordered if entitlement has been granted. To add an External User Account, open the customer, then select Create Customer Contact.
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | • As CSR, select a Customer and modify an existing External User account. • Note Customer Name & number at right. • Select Tasks > Manage Customer Contact. • In Customer Account section of Contact page, set Email to your own xpedx account. • Note Contact Login ID at right. |  | • Contact page displays. • Email is set to your xpedx account. |  | Not Started
2 | • On the Contact page, click the Manage User Profile hyperlink. • On the User Profile page, confirm User Type is set to External. • Designate a specific Min Order Amount (~$100.), and a larger Max Order Amount (~$500.) • Click Update User Profile |  | • User Profile page displays. • User Type = External. • Min and Max Order Amounts have been set. • Confirmation msg indicates User Profile update. |  | Not Started
3 | Log into the Website as the user who has just had their profile updated. Try and place an order where the order amount will EXCEED the maximum order amount |  | The system should prevent the order from being placed. A warning message should be displayed saying the order amount exceeds the user's amount |  | Not Started
Test Case # | 86.2 | Test Case Name: | Call Center: Customer Profile - Minimum Order Value
Use Case # | 86 | Preconditions: | External User and his Customer are entitled to items which can be combined to a value less than MainOrdValue. External User Profile has been created and configured with a known Min Order Value.
DDD ID:
Req. # |  | Notes: | Recall that items may only be viewed / ordered if entitlement has been granted. To add an External User Account, open the customer, then select Create Customer Contact.
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | • As CSR, select a Customer and modify an existing External User account. • Note Customer Name & number at right. • Select Tasks > Manage Customer Contact. • In Customer Account section of Contact page, set Email to your own xpedx account. • Note Contact Login ID at right. |  | • Contact page displays. • Email is set to your xpedx account. |  | Not Started
2 | • On the Contact page, click the Manage User Profile hyperlink. • On the User Profile page, confirm User Type is set to External. • Designate a specific Min Order Amount (~$100.), and a larger Max Order Amount (~$500.) • Click Update User Profile |  | • User Profile page displays. • User Type = External. • Min and Max Order Amounts have been set. • Confirmation msg indicates User Profile update. |  | Not Started
3 | Log into the Website as the user who has just had their profile updated. Try and place an order where the order amount will WILL NOT MEET the minimum order amount |  | The system should prevent the order from being placed. A warning message should be displayed saying the order amount does not meet the minimum order value |  | Not Started
Note on B1: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E6: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F6: Select from List. - Blank - Pass - Fail - Not Started
Note on G6: Enter Month / Day. Year defaults to current year unless entered.
Note on H6: Enter numeric portion of JIRA ticket.
Note on B11: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E16: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F16: Select from List. - Blank - Pass - Fail - Not Started
Note on G16: Enter Month / Day. Year defaults to current year unless entered.
Note on H16: Enter numeric portion of JIRA ticket.

## 88-RoleRights (hidden)
Test Case # |  | Test Case Name: | Call Center: Customer Profile - Edit Privileges are Limited to Appropriate Roles
Use Case # | 88 | Preconditions: | CSR is logged into Call Center and
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | • |  | • |  | Not Started
2 | • |  | • |  | Not Started
3 | • |  | • |  | Not Started
4 | • |  | • |  | Not Started
5 | • |  | • |  | Not Started
6 | • |  | • |  | Not Started
7 | • |  | • |  | Not Started
8 | • |  | • |  | Not Started
9 | • |  | • |  | Not Started
Note on B1: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E6: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F6: Select from List. - Blank - Pass - Fail - Not Started
Note on G6: Enter Month / Day. Year defaults to current year unless entered.
Note on H6: Enter numeric portion of JIRA ticket.

## 89-CreateCustContact
Test Case # | TC 89.1 | Test Case Name: | Call Center: Create Customer Contact
Use Case # | 89 | Preconditions: | User is logged into Call Center and has permission to create a customer contact (External User)
DDD ID:
Req. # |  | Notes: | This script should be executed while signed in as Security Admin, CSR, and Support Desk Admin. Customer Admin will not have access to Call Center, so will not use this screen.
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | • From the Master Customer record, click Create Customer Contact from the left navigation menu. |  | The New Contact tab is opened with the following fields: Customer Account section (First name, MI, Last Name, E-mail Address, Job Title, and Department) Customer Contact Information section (Evening Phone, Evening Fax, Day Phone, Day Fax, Mobile Phone) Personal Information section (Date of Birth, Spouse's Date of Birth, Wedding Anniversary) Contact Spending Limit section (Currency, Spending Limit, Approving User, and Backup Approver) Web User section (Login, Locale, Status, and User Roles) |  | Not Started
2 | On the New Contact tab, enter the following required fields: First Name Last Name E-mail Address Login User Roles Click the "Confirm" button |  | The system closes the tab and the user has been created. |  | Not Started
3 | Navigate back to the "Advanced Customer Search" and search again for the customer where the user was just created |  | The system returns the matching search criteria to the result set. |  | Not Started
4 | Find the Master Customer record and double click the record |  | The system opens the master customer record. The new user has been added to the "Contacts" tab of the Master Customer Record. |  | Not Started
Note on B2: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E7: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F7: Select from List. - Blank - Pass - Fail - Not Started
Note on G7: Enter Month / Day. Year defaults to current year unless entered.
Note on H7: Enter numeric portion of JIRA ticket.

## 92-Create Internal User
Test Case # |  | Test Case Name: | Call Center: User Profile - Create Internal User
Use Case # | 92 | Preconditions: | See Dave Dygert If fail to change conditions
DDD ID:
Req. # |  | Notes: | Sign on as xpedx Security Admin user.
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | • In CALL CENTER, sign on as Security Admin, and select Tasks > Create Internal User |  | • Internal User Creation screen displays. |  | Not Started
2 | • In the Security Admin section, populate the Network ID field with a valid xpedx Network ID. • Hit tab, or select any Authorized Division as indicated in next step below. |  | • Call Center auto-populates the following user info from LDAP server: - Employee ID (if user is an employee); - User Name (concatenated FName, MI, LName); - Email Address; - Create Date (today's date); - Last Login Date (blank until 1st login); - In Contact Information section, the Organization is populated. |  | Not Started
3 | • Select appropriate User Roles: - Select the appropriate "Team" this user will apply to. (This is how the system will define which division(s) the user should see) |  | • User Roles are selected • A team is assigned |  | Not Started
4 | • Populate all fields in Contact Information section, including - Address 1 / 2 / 3; - City, State, Country, Postal Code + Zip4; - Phone Number. • Click Save. |  | • Call Center confirmation message indicates that a New User ID has been successfully created. • An email is sent to the user's Email Address (as retrieved from LDAP.) |  | Not Started
5 | • Sign on to above User's email address and confirm receipt of User Creation email. • Open User Creation notification email and retrieve both UserID and system generated PW. |  | • New email is found which indicates a new UserID has been created, and includes a system generated password. |  | Not Started
6 | • Sign into Call Center with the UserID and password identified in the above email. |  | • New user is able to sign into Call Center. |  | Not Started
7 | • Check to see which divisions this user is able to access. |  | • User is able to access all authorized divisions, but only those which are authorized. |  | Not Started
Note on B1: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E6: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F6: Select from List. - Blank - Pass - Fail - Not Started
Note on G6: Enter Month / Day. Year defaults to current year unless entered.
Note on H6: Enter numeric portion of JIRA ticket.

## 93-UserProfExt
Test Case # |  | Test Case Name: | Call Center: User Profile - External
Use Case # | 93 | Preconditions: | User is logged into Call Center as Security Admin, CSR, or Support Desk Admin. (Execute these scripts as each of these users.)
DDD ID:
Req. # |  | Notes: | This script should be executed while signed in as Security Admin, CSR, and Support Desk Admin. Customer Admin will not have access to Call Center, so will not use this screen.
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | • From the Master Customer record, go to Modify Customer Contact (or Modify External User) screen. |  | • Profile screen displays for this external user. • UserID is populated with the user's external email address and other field values. |  | Not Started
2 | • In the General Info section, attempt to change all field values. |  | The following fields should NOT be directly editable: - UserID; - T&C Accepted, Last Login Date; - Password; (PW Reset button is available.) • The following fields should be editable: - FirstName; LastName; eMailAddress; Phone; Fax; Address Lines 1/2/3; City; State; ZipCode; Zip4; Country • User Status radio buttons may be changed. • User Type (Roles) checkboxes may be selected or de-selected. • Help icon is available for User Type (Roles). |  | Not Started
3 | • In the Locations section, attempt to edit the "Default Ship-To" address. • |  | • Default ShipTo is not directly editable from this screen, but a different Default may be selected by clicking the "Change Default" hyperlink. • |  | Not Started
4 | • In the Locations section, under Assigned Locations, attempt to Collapse and Expand the hierarchy of Locations. • |  | • The hierarchy of Assigned Locations collapses or expands at each level as expected. • |  | Not Started
5 | • Assign a new location by clicking the checkbox next to the location name. Click "Update Profile" • |  | • The selected New Location retains the checkbox as selected. • |  | Not Started
6 | • For the Location which was just assigned above, uncheck the box to remove it. Click "Update Profile" • |  | • The selected New Location has the check removed. |  | Not Started
7 | • Key values for both Min Order Amount and Max Order Amount. Use dollars and cents. • |  | • Both fields accept input. • Format accepts dollars and cents. |  | Not Started
8 | • In the Site Settings section, change the Preferred Catalog View by selecting a different radio button. • From the dropdown, specify a different value for Preferred Catalog. |  | • Preferred Catalog View permits selection of other radio buttons. • Preferred Catalog permits selection of other values from the dropdown. • Selected values are retained. |  | Not Started
9 | • In the Site Settings section, under Order Confirmation Address List, select the hyperlink to Add New Address. • Specify your own business email address in the format of firstname.lastname@ipaper.com. |  | • "Add New" hyperlink brings up a dialog to create a new address and permits saving the address. |  | Not Started
10 | • For the newly added/edited email address above, select the Delete hyperlink. At the prompt, select OK to confirm the deletion. |  | • "Delete" hyperlink prompts for confirmation before removing the selected email address. |  | Not Started
11 | • In the Site Settings section, under Receive E-Mails, confirm that "Receive Order Confirmation Email" is checked. • Deselect, then reselect the "Receive Order Confirmation Email" checkbox. • Select all remaining checkboxes. • |  | • "Receive Order Confirmation Email" was checked by default. • All other checkboxes permit selection or deselection and retain those settings.
12 | • In the Site Settings section, under Email Address for Invoice, select the hyperlink to Add New Address. • Specify your own business email address in the format of firstname.lastname@ipaper.com. |  | • "Add New" hyperlink brings up a dialog to create a new address and permits saving the address. • |  | Not Started
13 | • For the newly added email address above, select the Edit hyperlink. Change the address format to firstname.lastname@xpedx.com. |  | • "Edit" hyperlink permits changing & saving an existing email from ipaper.com to xpedx.com. • |  | Not Started
14 | • For the newly added/edited email address above, select the Delete hyperlink. At the prompt, select OK to confirm the deletion. |  | • "Delete" hyperlink prompts for confirmation before removing the selected email address. • |  | Not Started
15 | • In the Site Settings section, under Manage PO# List, select the hyperlink to Add New PO#. Specify PO# POTEST-1234. • |  | • "Add New" hyperlink brings up a dialog to create a new PO# and permits saving the PO#. |  | Not Started
16 | • For the newly added/edited email address above, select the Delete hyperlink. At the prompt, select OK to confirm the deletion. • |  | • "Delete" hyperlink prompts for confirmation before removing the selected PO#. • |  | Not Started
Test Case # | 93.1 | Test Case Name: | Call Center: User Profile - External (Active / Suspend)
Use Case # |  | Preconditions: | User is logged into Call Center as CSR; Division Admin; eBusiness Admin; or Support Desk Admin. (Cust.Adm does not use Call Center.)
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Status | Date Executed | JIRA #
1 | • Login to WEB as an External user to confirm the User account is active. |  | • Login is successful. |  | Not Started
2 | • Logon to CALL CENTER as Admin / Division Admin / eBusiness Admin; or Support Desk Admin. • Find the above WEB user. • Manage User Profile • Set User Status to "Suspend" and save user Profile. |  | • Changed profile is saved as Suspended. • |  | Not Started
3 | • Attempt a Login to WEB as the Suspended user. • |  | • Access is Denied. • |  | Not Started
4 | • In the General Info section, attempt to change all field values. |  | • Values can be updated in Call Center still. |  | Not Started
5 | • In CALL CENTER, restore User Status to Active. • |  | • Changed profile is saved as Active. • |  | Not Started
6 | • Login to WEB as restored Active user. • |  | • Login is succesful. • |  | Not Started
Test Case # | 93.2 | Test Case Name: | Call Center: User Profile - External (User Type / Roles)
Use Case # |  | Preconditions: | User is logged into Call Center as CSR; Division Admin; eBusiness Admin; or Support Desk Admin. (Cust.Adm does not use Call Center.)
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | • From the Master Customer record, go to Modify Customer Contact (or Modify External User) screen. |  | • Profile screen displays for this external user. • UserID is populated with the user's external email address and other field values. |  | Not Started
2 | In Call Center, select the "Buyer" role and update the profile. |  | The system saves the profile with the changes made. |  | Not Started
3 | Log into the Web Channel with the User ID where the changes were just made. Validate the changes have been made. |  | Based on permission – meaning if the logged in user has the permission to the role. The following permissions are associated with this role. 1. Manage orders 2. View prices 3. View catalogs 4. Order History / Reporting 5. Returns 6. Manage their own MyItems list |  | Not Started
4 | In Call Center, select the "Admin" role and clear the other roles. Update the profile. |  | The system saves the profile with the changes made. |  | Not Started
5 | Log into the Web Channel with the User ID where the changes were just made. Validate the changes have been made. |  | Based on permission – meaning if the logged in user has the permission to the role. The following permissions are associated with this role. 1. Manage Users 2. View user carts for that customer 3. View orders for that customer 4. View reports for that customer 5. Manage My Items lists 6. Manage news |  | Not Started
6 | In Call Center, select the "Approver" role and clear the other roles. Update the profile. |  | The system saves the profile with the changes made. |  | Not Started
7 | Log into the Web Channel with the User ID where the changes were just made. Validate the changes have been made. |  | Based on permission – meaning if the logged in user has the permission to the role. The following permissions are associated with this role. 1. All buyer functions as well as Manage Order for Accounts. |  | Not Started
8 | In Call Center, select the "View Invoices" role and clear the other roles. Update the profile. |  | The system saves the profile with the changes made. |  | Not Started
9 | Log into the Web Channel with the User ID where the changes were just made. Validate the changes have been made. |  | Based on permission – meaning if the logged in user has the permission to the role. The following permissions are associated with this role. 1. View invoices online |  | Not Started
10 | In Call Center, select the "View Reports" role and clear the other roles. Update the profile. |  | The system saves the profile with the changes made. |  | Not Started
11 | Log into the Web Channel with the User ID where the changes were just made. Validate the changes have been made. |  | If the View Prices flag is turned on, then check this field to either show the reporting link or not. |  | Not Started
12 | In Call Center, select the "Stock Check" role and clear the other roles. Update the profile. |  | The system saves the profile with the changes made. |  | Not Started
13 | Log into the Web Channel with the User ID where the changes were just made. Validate the changes have been made. |  | Based on permission – meaning if the logged in user has the permission to the role. The following permissions are associated with this role. This role will be checked when somebody requests a stock check and will be allowed if the user has this role. |  | Not Started
14 | In Call Center, select the "View Prices" role and clear the other roles. Update the profile. |  | The system saves the profile with the changes made. |  | Not Started
15 | Log into the Web Channel with the User ID where the changes were just made. Validate the changes have been made. |  | If this flag is turned off, we will still do tha P&A but hide the price from showing it on the UI in web channel, COM |  | Not Started
16 | In Call Center, select the "Estimator" role and clear the other roles. Update the profile. |  | The system saves the profile with the changes made. |  | Not Started
17 | Log into the Web Channel with the User ID where the changes were just made. Validate the changes have been made. |  | Based on permission – meaning if the logged in user has the permission to the role. The following permissions are associated with this role. 1. View Prices 2. View Catalogs 3. Create Cart 4. View Order History / Reporting 5. Cannot checkout |  | Not Started
Test Case # | 93.3 | Test Case Name: | Call Center: User Profile - External (Password Reset and General Info)
Use Case # |  | Preconditions: | User is logged into Call Center as CSR; Division Admin; eBusiness Admin; or Support Desk Admin. (Cust.Adm does not use Call Center.)
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Status | Date Executed | JIRA #
1 | • Login to CALL CENTER as Admin. • Select an External TEST user which you believe is unlikely to be in use by another tester. • Change that user's email address to match your own xpedx.com account. • Set Phone and Fax fields to your own. • Set Address as follows: Ad.Line1: xpedx Ad.Line2: Cincinnati Tech Center Ad.Line3: 6287 Tri-Ridge Blvd City: Loveland State: OH Zip: 45140 Zip4: 1234 Country: USA • Select the Reset Password button. |  | • PW Reset msg is displayed. • Profile changes are retained. • Email is received at your xpedx account. • That email contains an auto-generated password for the External TEST user in question. |  | Not Started
2 | • Copy the auto-generated PW from your email to Windows Notepad. • Go to WEB Channel login page and enter the UserID for the External TEST user. • Paste the auto-generated PW from Notepad to the Login screen Password field. |  | • External TEST user is successfully Logged in. • |  | Not Started
3 | • While logged into WEB as External TEST user, select Admin > My Account, and change the password back to "password". • Note contents of email address, Phone, Fax, and all address fields. • Logout and back in, using "password" to verify that this Test UserID will be accessible to other testers. |  | • Test User's password is restored to "password" • External Web user's My Account page reflects Call Center changes. |  | Not Started
4 | • Assuming you're still logged into CALL Center, refresh the User Profile screen. |  | • Last Login date reflects today's date. • |  | Not Started
Test Case # | 93.4 | Test Case Name: | Call Center: User Profile - External (Default Ship-To)
Use Case # |  | Preconditions: | User is logged into Call Center as CSR; Division Admin; eBusiness Admin; or Support Desk Admin. (Cust.Adm does not use Call Center.)
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Status | Date Executed | JIRA #
1 | • Select an External TEST user which has access to at least 2 ShipTo Addresses and which you believe is unlikely to be in use by another tester. • Log into the WEB and note the Default ShipTo address. (Capture in Results at right.) • Confirm access to multiple ShipTos by clicking the header hyperlink "Change Ship-to Address" |  | • External TEST user is successfully logged into WEB. • User has access to multiple ShipTos. • Original Default ShipTo is recorded at right. |  | Not Started
2 | • Login to CALL CENTER as Admin. • Open the user profile for the External TEST user above. • In the Locations section of the User Profile, note the Address currently set for Defaulit ShipTo. (Capture in Results at right.) • Click the hyperlink to Change Default. |  | • Initially displayed CALL CENTER Default ShipTo agrees with WEB Default ShipTo which is captured above. • Change Default Ship-To dialog is displayed. |  | Not Started
3 | • CALL CENTER: From the options displayed in the dialog, select a different Default ShipTo Address and Save it. |  | • New Default Ship-To is now displayed in this user's Call Center profile. • |  | Not Started
4 | • Log into WEB as this External Test user. • If already logged in as this user, then refresh the screen to see new Default ShipTo in header. |  | • WEB user displays a new Default ShipTo in the header. • |  | Not Started
5 | • While logged into WEB as External Test user, click the header hyperlink to Change Ship-To Address. • Select the original WEB Default Address which you noted above. • Click the link to Set Selected Address as Default. |  | • WEB user displays the original WEB Default ShipTo in the header. • |  | Not Started
6 | • Return to CALL CENTER as Admin and open the user profile for the selected External TEST user. • If already at that page, then refresh the screen. • Note the currently displayed Default Ship-To address. |  | • CALL CENTER Default ShipTo Address has been restored to the original CALL CENTER value captured above. • |  | Not Started
Test Case # | 93.5 | Test Case Name: | Call Center: User Profile - External (Assigned Locations)
Use Case # |  | Preconditions: | User is logged into Call Center as CSR; Division Admin; eBusiness Admin; or Support Desk Admin. (Cust.Adm does not use Call Center.)
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Status | Date Executed | JIRA #
1 | • Logged into CALL CENTER as CSR, identify and locate an External User. (Users should be created and exist ONLY at the Master Customer level.) • In the left NAV bar, select Customer > Manage Customer Contact. |  | • User Profile screen opens • |  | Not Started
2 | • Navigate to the Customer Assignment Tab |  | • Customer Assignment tab displays. • |  | Not Started
3 | • Select at least 2 Location(s) to which this user will have access. • Save the selections. |  | • User Profile is updated to reflect the addition of the new Locations. • The Assigned Locations appear in hierarchical format. |  | Not Started
| • In WEB, log in as the External User. • At the top of the Header page, select Change Default ShipTo Location. |  | • The Assigned Locations should appear as alternatives for Default ShipTo. (One of these may already be set as the current default.) • |  | Not Started
4 | • In CALL CENTER, identify one of the Assigned Locations to be removed from the Customer Profile. • Note the Location so it can be restored. • Update the Profile • For that Location, de-select the checkbox next to the location name. • Update profile. |  | • The checkbox is no longer selected and the user profile is saved. • |  | Not Started
5 | • In WEB, confirm deletion of the selected Assigned Location. • |  | • The selected Assigned Location is removed. • |  | Not Started
6 | • In CALL CENTER, restore the Assigned Location which was deleted above. • |  | • The selected Assigned Location is restored. • |  | Not Started
Test Case # | 93.6 | Test Case Name: | Call Center: User Profile - External (Min / Max Order Amount)
Use Case # |  | Preconditions: | User is logged into Call Center as CSR; Division Admin; eBusiness Admin; or Support Desk Admin. (Cust.Adm does not use Call Center.) External User and his Customer are entitled to items which can be combined to a value in excess of MaxOrdValue. External User Profile has been created and configured with a known Max Order Value.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | • As CSR, select a Customer and modify an existing External User account. • Note Customer Name & number at right. • Select Tasks > Manage Customer Contact. • In Customer Account section of Contact page, set Email to your own xpedx account. • Note Contact Login ID at right. |  | • Contact page displays. • Email is set to your xpedx account. |  | Not Started
2 | • On the Contact page, click the Manage User Profile hyperlink. • On the User Profile page, confirm User Type is set to External. • Designate a specific Min Order Amount (~$100.), and a larger Max Order Amount (~$500.) • Click Update User Profile |  | • User Profile page displays. • User Type = External. • Min and Max Order Amounts have been set. • Confirmation msg indicates User Profile update. |  | Not Started
3 | • Select Tasks > Order > Create Order. • Click Get Assigned Ship-Tos or Skip This Step. |  | • Draft Order screen displays. |  | Not Started
Test Case # | 93.7 | Test Case Name: | Call Center: User Profile - External (Preferred Catalog View)
Use Case # |  | Preconditions: | User is logged into Call Center as CSR; Division Admin; eBusiness Admin; or Support Desk Admin. (Cust.Adm does not use Call Center.)
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Status | Date Executed | JIRA #
1 | • Login to CALL CENTER as Admin. • Select an External TEST user which you believe is unlikely to be in use by another tester. • In Site Settings, set Preferred Catalog View to "1 Item/Row" (Full View) • Update User Profile. |  | • Call Center displays confirmation message. • |  | Not Started
2 | • Login to WEB as the above External TEST user. • Select Catalog > Paper > Bond & Writing. • Note which icon is selected and the format of displayed items. • Select Admin > My Profile > Manage Site Settings. Note Preferred Catalog View. |  | • Web Catalog displays 1 item per row. • On the line labeled as "Drag to compare", the 1st icon is highlighted & the catalog displays 1 item per row. • Manage Site Settings > Preferred Catalog View is set to "Classic View 1 item per row" |  | Not Started
3 | • In CALL CENTER, for same External TEST user, set Preferred Catalog View to "2 Items/Row. (Condensed View) • Update User Profile |  | • Call Center displays confirmation message • |  | Not Started
4 | • Login to WEB as the above External TEST user. (or Refresh page) • Select Catalog > Paper > Bond & Writing. • Note which icon is selected and the format of displayed items. • Select Admin > My Profile > Manage Site Settings. Note Preferred Catalog View. |  | • Web Catalog displays 2 items per row. • On the line labeled as "Drag to compare", the 2nd icon is highlighted. • Manage Site Settings > Preferred Catalog View is set to "Classic View 2 items per row" |  | Not Started
5 | • In CALL CENTER, for same External TEST user, set Preferred Catalog View to "4 Items/Row. (Mini View) • Update User Profile |  | • Call Center displays confirmation message • |  | Not Started
6 | • Login to WEB as the above External TEST user. (or Refresh page) • Select Catalog > Paper > Bond & Writing. • Note which icon is selected and the format of displayed items. • Select Admin > My Profile > Manage Site Settings. Note Preferred Catalog View. |  | • Web Catalog displays 4 items per row. • On the line labeled as "Drag to compare", the 3rd icon is highlighted. • Manage Site Settings > Preferred Catalog View is set to "Classic View 4 items per row" |  | Not Started
7 | • In CALL CENTER, for same External TEST user, set Preferred Catalog View to "Matrix - No images. (Paper Grid View) • Update User Profile |  | • Call Center displays confirmation message • |  | Not Started
8 | • Login to WEB as the above External TEST user. (or Refresh page) • Select Catalog > Paper > Bond & Writing. • Note which icon is selected and the format of displayed items. • Select Admin > My Profile > Manage Site Settings. Note Preferred Catalog View. |  | • Web Catalog displays 1 item per row with details of Site, Cert, Stocked, List Price, & Action per row, but NO IMAGES. • On the line labeled as "Drag to compare", the 4th icon is highlighted. • Manage Site Settings > Preferred Catalog View is set to "Matrix View No Images" |  | Not Started
Test Case # | 93.8 | Test Case Name: | Call Center: User Profile - External (Preferred Catalog)
Use Case # |  | Preconditions: | User is logged into Call Center as CSR; Division Admin; eBusiness Admin; or Support Desk Admin. (Cust.Adm does not use Call Center.)
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Status | Date Executed | JIRA #
1 | • Login to CALL CENTER as Admin. • Select an External TEST user which you believe is unlikely to be in use by another tester. • This user should have rights to see ALL catalogs. • In Site Settings section of User Profile, select "Facility Supplies" from Preferred Catalog dropdown. • Update User Profile. |  | • Call Center displays confirmation message. • |  | Not Started
2 | • Login to WEB as the above External TEST user. • Note the catalog displayed at the lower LEFT of Home page. |  | • "Facility Supply" catalog is displayed at the lower LEFT of Home page. • Fac.Sup Catagories display in bottom center. • Other 3 catalog images are displayed in a stack at the lower RIGHT. |  | Not Started
3 | • In CALL CENTER, for same External TEST user, set Preferred Catalog to "Graphics". • Update User Profile |  | • Call Center displays confirmation message. • |  | Not Started
4 | • In WEB, Refresh the page as same External Test user. • Note the catalog displayed at the lower LEFT of Home page. |  | • "Graphics" catalog is displayed at the bottom of Home page. • Graphics Catagories display in bottom center. • Other 3 catalog images are displayed in a stack at the lower RIGHT. |  | Not Started
5 | • In CALL CENTER, for same External TEST user, set Preferred Catalog to "Packaging" • Update User Profile |  | • Call Center displays confirmation message. • |  | Not Started
6 | • In WEB, Refresh the page as same External Test user. • Note the catalog displayed at the lower LEFT of Home page. |  | • "Packaging" catalog is displayed at the bottom of Home page. • Packaging Catagories display in bottom center. • Other 3 catalog images are displayed in a stack at the lower RIGHT. |  | Not Started
7 | • In CALL CENTER, for same External TEST user, set Preferred Catalog to "Paper" • Update User Profile |  | • Call Center displays confirmation message. • |  | Not Started
8 | • In WEB, Refresh the page as same External Test user. • Note the catalog displayed at the lower LEFT of Home page. |  | • "Paper" catalog is displayed at the bottom of Home page. • Paper Catagories display in bottom center. • Other 3 catalog images are displayed in a stack at the lower RIGHT. |  | Not Started
Test Case # | 93.9 | Test Case Name: | Call Center: User Profile - External (Order Confirmation Address List)
Use Case # |  | Preconditions: | User is logged into Call Center as CSR; Division Admin; eBusiness Admin; or Support Desk Admin. (Cust.Adm does not use Call Center.)
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Status | Date Executed | JIRA #
1 | • Login to CALL CENTER as Admin. • Select an External TEST user which you believe is unlikely to be in use by another tester. • In Site Settings section of User Profile, under Order Confirmation Address List, select the "Add New Address" hyperlink. • Populate "Add New Address" dialog with your own xpedx email address and Save. • Add & Save a couple of email addresses. • In the Receive Emails section of User Profile, confirm that the checkbox is selected for "Receive Order Confirmation Email". • Update User Profile. |  | • Add New Address dialog is displayed. • Your email address is added to User Profile list of addresses as a new Order Confirmation Email Address. • Call Center displays confirmation message. |  | Not Started
2 | • Login to WEB as the above External TEST user. • Submit an Order. • Check the email account identified in the step above, looking for Order Confirmation. |  | • Order is successfully submitted. • The email account identified above receives an auto-generated email message which confirms successful order placement. |  | Not Started
3 | • Log out of CALL CENTER • Log back in to CALL CENTER and return to the User Profile for the External TEST user modified above. • Confirm that Site Settings > Order Confirmation Address List > Email Addresses reflects the above Edits. • |  | • Above edits have been retained. • |  | Not Started
4 | • In CALL CENTER, under Site Settings > Order Confirmation Address List, select the Delete hyperlink for your test email address. • Confirm Deletion and Save. • Update User Profile. • |  | • Deleted email address is removed from Site Settings > Order Confirmation Address List > Email Addresses. • |  | Incomplete
Test Case # | 93.10 | Test Case Name: | Call Center: User Profile - External (Receive emails)
Use Case # |  | Preconditions: | User is logged into Call Center as CSR; Division Admin; eBusiness Admin; or Support Desk Admin. (Cust.Adm does not use Call Center.)
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Status | Date Executed | JIRA #
1 | • Login to CALL CENTER as Admin. • Select an External TEST user which you believe is unlikely to be in use by another tester. • In Site Settings section of User Profile, under Receive Emails, select all checkboxes, including the following: - Receive Order Confirmation Email; - Receive Order Cancellation Email; - Receive Order Update by CSR Email; - Receive Order ShipMent Email; - Receive Order BackOrder Email. • Add your own xpedx email address to the Order Confirmation Address List section of the User Profile. • Update User Profile. |  | • Order Confirmation checkbox is selected by default. (unless modified by previous testing) • All Checkboxes are ultimately selected. • Order Confirmation Address List includes your own xpedx email address. • |  | Not Started
2 | • Login to WEB as the above External TEST user. • Submit an Order. • Check the email account identified above, looking for Order Confirmation. |  | • Order is submitted. • Email is received confirming receipt of order. |  | Not Started
3 | • Work with Legacy team to change Order status as follows: - Update by CSR; - BackOrder; - Ship; - Cancel (the BackOrdered item) • Following each update by Legacy, check your email account to confirm receipt of an appropriate email notification. |  | • Following each update by Legacy, a corresponding email is received at your xpedx email address. • |  | Not Started
Test Case # | 93.11 | Test Case Name: | Call Center: User Profile - External (Email address for Invoice)
Use Case # |  | Preconditions: | User is logged into Call Center as CSR; Division Admin; eBusiness Admin; or Support Desk Admin. (Cust.Adm does not use Call Center.)
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | • Login to CALL CENTER as Admin. • Select an External TEST user which you believe is unlikely to be in use by another tester. • In Site Settings section of User Profile, under "Email address for Invoice" click the "Add New Address" hyperlink. • Populate "Add New Address" dialog with your own xpedx email address and Save. • Update User Profile. |  | • Add New Address dialog is displayed. • Your email address is added to User Profile list of addresses as a new Email Address for Invoice. • Call Center displays confirmation message. |  | Not Started
2 | • Login to WEB as the above External TEST user. • Submit an Order. |  | • Order is successfully submitted. |  | Not Started
3 | • Work with Legacy to have the above order marked as Invoiced. • Check your xpedx email account for an Invoice Notification email. |  | • Order is marked as Invoiced • Email Notification of Invoice is received. |  | Not Started
4 | • In CALL CENTER, under Site Settings > Email Address for Invoice, select the Edit hyperlink for the test address added above. • Change the email address & Save. • Update User Profile. |  | • Edit email address dialog displays. • Edited email address is saved to Site Settings > Email Address for Invoice > Email Addresses. • |  | Not Started
5 | • Log out of CALL CENTER • Log back in to CALL CENTER and return to the User Profile for the External TEST user modified above. • Confirm that Site Settings > Email Address for Invoice reflects the above Edits. • |  | • Above edits have been retained. • |  | Not Started
6 | • In CALL CENTER, under Site Settings > Email Address for Invoice, select the Delete hyperlink for your test email address. • Acknowledge Delete confirmation and Save. • Update User Profile. • |  | • Deleted email address is removed from Site Settings > Email Address for Invoice. • |  | Not Started
Test Case # | 93.12 | Test Case Name: | Call Center: User Profile - External (Manage PO# List)
Use Case # |  | Preconditions: | User is logged into Call Center as CSR; Division Admin; eBusiness Admin; or Support Desk Admin. (Cust.Adm does not use Call Center.)
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Status | Date Executed | JIRA #
1 | • Login to CALL CENTER as Admin. • Select an External TEST user which you believe is unlikely to be in use by another tester. • In Site Settings section of User Profile, under "Manage PO# List" Populate "Add New PO#" input field with a unique PO# and click "Add PO #". • Note the PO# at right. • Update User Profile. |  | • Add New PO# dialog is displayed. • Your unique PO# is added to Manage PO# List. |  | Not Started
2 | • Login to WEB as the above External TEST user and create an Order. • Select the above unique Test PO# for this order. • Submit the Order. |  | • PO# appears in the list of available Pos. • Order is successfully submitted. |  | Not Started
3 | • Log out of CALL CENTER • Log back in to CALL CENTER and return to the User Profile for the External TEST user modified above. • Confirm that Site Settings >Manage PO# List still reflects the above Edits. • |  | • Above edits have been retained. • |  | Not Started
4 | • In CALL CENTER, under Site Settings > Manage PO# List, select the Delete hyperlink for your unique Test PO#. • Acknowledge Delete confirmation and Save. • Update User Profile. • |  | • Deleted PO# is removed from Site Settings > Manage PO# List. • |  | Not Started
Test Case # | 93.13 | Test Case Name: | Call Center: User Profile - External (Reactivated User Retains Data)
Use Case # |  | Preconditions: | User is logged into Call Center as CSR; Division Admin; eBusiness Admin; or Support Desk Admin. (Cust.Adm does not use Call Center.)
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | • In WEB, sign on as External Buyer and Create a Cart. • View Cart contents. • Note UserID and Cart Name in Results. • Log out as this user. |  | • Cart is created. • |  | Not Started
2 | • In CALL CENTER, Suspend the above External Buyer. • |  | • Confirmation is received that the External Buyer is Suspended. • |  | Not Started
3 | • In WEB, attempt to Login as the Suspended External Buyer. • |  | • Suspended External Buyer is prevented from successful login. • |  | Not Started
4 | • In CALL CENTER, re-Activate the Suspended External Buyer • |  | • Confirmation is received that the External Buyer is Activated. • |  | Not Started
5 | • In WEB, Login as the re-Activated External Buyer. • |  | • Login is successful • |  | Not Started
6 | • In WEB as re-activated Buyer, View Carts and find the Cart created and Noted above. • Examine Cart contents. |  | • The Cart Name is found. • Cart contents are as originally created. |  | Not Started
Note on B1: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E6: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F6: Select from List. - Blank - Pass - Fail - Not Started
Note on G6: Enter Month / Day. Year defaults to current year unless entered.
Note on H6: Enter numeric portion of JIRA ticket.
Note on B26: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E31: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F31: Select from List. - Blank - Pass - Fail - Not Started
Note on G31: Enter Month / Day. Year defaults to current year unless entered.
Note on H31: Enter numeric portion of JIRA ticket.
Note on B41: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E46: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F46: Select from List. - Blank - Pass - Fail - Not Started
Note on G46: Enter Month / Day. Year defaults to current year unless entered.
Note on H46: Enter numeric portion of JIRA ticket.
Note on B67: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E72: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F72: Select from List. - Blank - Pass - Fail - Not Started
Note on G72: Enter Month / Day. Year defaults to current year unless entered.
Note on H72: Enter numeric portion of JIRA ticket.
Note on B80: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E85: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F85: Select from List. - Blank - Pass - Fail - Not Started
Note on G85: Enter Month / Day. Year defaults to current year unless entered.
Note on H85: Enter numeric portion of JIRA ticket.
Note on B95: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E100: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F100: Select from List. - Blank - Pass - Fail - Not Started
Note on G100: Enter Month / Day. Year defaults to current year unless entered.
Note on H100: Enter numeric portion of JIRA ticket.
Note on B111: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E116: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F116: Select from List. - Blank - Pass - Fail - Not Started
Note on G116: Enter Month / Day. Year defaults to current year unless entered.
Note on H116: Enter numeric portion of JIRA ticket.
Note on B123: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E128: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F128: Select from List. - Blank - Pass - Fail - Not Started
Note on G128: Enter Month / Day. Year defaults to current year unless entered.
Note on H128: Enter numeric portion of JIRA ticket.
Note on B140: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E145: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F145: Select from List. - Blank - Pass - Fail - Not Started
Note on G145: Enter Month / Day. Year defaults to current year unless entered.
Note on H145: Enter numeric portion of JIRA ticket.
Note on B157: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E162: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F162: Select from List. - Blank - Pass - Fail - Not Started
Note on G162: Enter Month / Day. Year defaults to current year unless entered.
Note on H162: Enter numeric portion of JIRA ticket.
Note on B169: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E174: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F174: Select from List. - Blank - Pass - Fail - Not Started
Note on G174: Enter Month / Day. Year defaults to current year unless entered.
Note on H174: Enter numeric portion of JIRA ticket.
Note on B181: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E186: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F186: Select from List. - Blank - Pass - Fail - Not Started
Note on G186: Enter Month / Day. Year defaults to current year unless entered.
Note on H186: Enter numeric portion of JIRA ticket.
Note on B196: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E201: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F201: Select from List. - Blank - Pass - Fail - Not Started
Note on G201: Enter Month / Day. Year defaults to current year unless entered.
Note on H201: Enter numeric portion of JIRA ticket.
Note on B208: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E213: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F213: Select from List. - Blank - Pass - Fail - Not Started
Note on G213: Enter Month / Day. Year defaults to current year unless entered.
Note on H213: Enter numeric portion of JIRA ticket.

## 0. Dropdown Values (hidden)
Pass
Fail
Incomplete
Not Started