## Instructions
Information for the PDP_Test_Scripts
The Requirements Matrix can be copied into the test scripts from the xpedx PDP document, if necessary.
This workbook includes worksheets for two test script formats - execution by steps within a test script and/or execution by individual test scripts. You can use either format or both within the same workbook. Totals will be automatically updated as expected. Formulas are built in the system as long as you copy the appropriate template #.# worksheet. Formulas will be refreshed on worksheet adds and deletes. You cannot click inside protected cells. This is to assist you in entering your information into worksheets.
Unprotected Cell Caution: Final Pass Cell | If you select a value in the Final Pass cell drop down list or clear out the cell, you will OVERLAY the formula that populates this cell with a P or PE value when the First Pass cell value is selected from it's drop down list. Formula example is: =IF(G11<>"F",G11," ")
SignOff: | -Enter the project description, which will be automatically populated on the Summary worksheet. -Enter the RPM # and USD #, which will be automatically populated in the Summary and Use Case worksheets. -Check the applicable box after your review, add your signature and date.
Summary: | The Summary list is for you to enter Use Case and Test Case numbers and Test Case summary notes. Includes a table that automatically updates the totals for the number of your test scripts and pass/fail results based on your entries. Totals will be automatically captured and summed in the protected yellow cells.
Step UC #.#: | -This is an individual test script worksheet to be used for each identified Use Case. -Copy the Step UC #.# worksheet template and paste accordingly within the worksheet tabs. -Execute each Test Case by steps within that Test Case. -Select P, PE, or F for each test script execution and the totals will be tallied in the protected yellow cells.
UC #.#: | -This is an individual test script worksheet to be used for each identified Use Case. -Copy the UC #.# worksheet template and paste accordingly within the worksheet tabs. -Execute each Test Case as appropriate. -Select P, PE, or F for each test script execution and the totals will be tallied in the protected yellow cells.
Common To Both Use Case Worksheet Formats: | -Copy worksheets as necessary after the Summary tab and before the Blank-DO NOT DELETE OR MOVE tab and re-number the worksheet tab as appropriate. -Update the cell Req / Use Case #: UC #.# for each worksheet. -Add additional test case rows as required for all Use Cases for each requirement. -To add rows use Copy & Insert Copied Cells where appropriate. (Formulas will be automatically updated). -If there is more than one test execution for a test case, record the number of times for the # of Fails of that test case -You can delete unnecessary worksheets (Step UC or UC tabs) and the total formulas will automatically update accordingly.
Step UC Example: | Displays a completed test script, Step UC #.#, that includes totals. (These totals not included in Summary worksheet).
UC Example: | Displays a completed test script, UC #.#, that includes totals. (These totals not included in Summary worksheet).

## SignOff
USD 5156778- MAX - Next Gen P&A Interface Tests- QA - July 2011 |  | RPM #: | 366398
|  | USD #: | 5156778
Sign Off
Accepted with no changes. All test cases performed as expected. Proceed with production migration.
Accepted with pre-existing exceptions. Pre-existing functionality occurred during testing.
Accepted with exceptions. Identified FAILED test cases on this results sheet must be corrected before project is considered closed, but can occur after initial code is moved. Otherwise, requested corrections for result sheet FAILED test cases are to be implemented in subsequent phase/release.
NOT ACCEPTABLE. FAILED test cases on this results sheet must be corrected before QA acceptance and production migration.
| Business Analyst |  | Date
| Project Team Lead/Manager |  | Date
Comments:

## Summary
USD 5156778- MAX - Next Gen P&A Interface Tests- QA - July 2011 | [12 empty] | RPM #: | 366398
[13 empty] | USD #: | 5156778
|  | 0 | 0 | 0 | 0 | 0 | Test Scripts | Tested | Untested | Passed | Failed | % Passed | % Passed of # Tested | # of Fails
| First Pass Totals: | 0 | 0 | 0 | 0 | 0 | 59 | 59 | 0 | 50 | 9 | 84.75% | 84.75%
| Current Totals: | 0 | 0 | 0 | 0 | 0 | 59 | 55 | 4 | 55 | 0 | 93.22% | 100% | 0
| Test Case # | [5 empty] | Test Case Summary
Data Map Tests:
Failed | 1 | [5 empty] | Vanilla test - Stock check one item and there are no failures. | [7 empty] | Tested by Team 2
Team 1 Not testing | 2 | [5 empty] | B2B Stock Check - Can be done via Call Center only. | [7 empty] | Tested by Team 2
Not Started | 3 | [5 empty] | Perform a Stock Check on a T4 Customer | [7 empty] | updated 08/03/11 - dh (cannot enter an order for T4 customers in CC at this time.
Passed | 4 | [5 empty] | Test using the customer's 1st Ship-To
Passed | 5 | [5 empty] | Test using the customer's 2nd Ship-To
Passed | 6 | [5 empty] | Test using a customer with more than 3 Ship To's and use the last Ship To
Passed | 7 | [5 empty] | Test Header Status Code 03 -Perform a test with an invalid Ship To - This should be stopped in the Web Channel and Call Center. Line Status Code of 03 would be sent from MAX if an P&A made it through.
Team 1 Not testing | 8 | [5 empty] | Test a 2 line P&A | [7 empty] | Tested by Team 2
Team 1 Not testing | 9 | [5 empty] | Test a 10 line P&A | [7 empty] | Tested by Team 2
Team 1 Not testing | 10 | [5 empty] | Test a 55 line P&A | [7 empty] | Tested by Team 2
Team 1 Not testing | 11 | [5 empty] | Test a 200 line P&A | [7 empty] | Tested by Team 2
Failed | 12 | [5 empty] | Perform a P&A for an item that was searched by customer part number (a valid customer part number exists in MAX). This customer part number also is a valid MAX item number for a different item. Confirm the P&A is sent based on the valid legacy number for the customer part number. | [7 empty] | Tested by Team 2 | `
Passed | 12 (2) | [5 empty] | Perform a P&A for an item that was searched by customer part number (a valid customer part number exists in MAX). This customer part number and MAX item are different, and the customer item # is NOT a valid MAX item # Confirm the P&A is sent based on the valid legacy number for the customer part number. | [7 empty] | Passed with exception
Passed | 12 (3) | [5 empty] | Perform a P&A for an item that was searched by customer part number (a valid customer part number exists in MAX). This customer part number is a MAX item # but not the same item as the MAX item # being tested. Confirm the P&A is sent based on the valid legacy number for the customer part number. | [7 empty] | Passed with exception
Passed | 13 | [5 empty] | Perform a P&A for an item that has a corresponding customer cross reference and the Customer UOM is not a valid MAX UOM.
Passed | 14 | [5 empty] | Perform a P&A for an item that has a corresponding customer cross reference and the Customer UOM has a conversion factor other than 1.
Passed | 15 | [5 empty] | Perform a P&A where the requested quantity is in decimals. (Call Center Only)
Passed | 16 | [5 empty] | Perform a P&A for an item that has the pricing UOM of "M". | [7 empty] | updated 8/3/11 - dh
Passed | 17 | [5 empty] | Perform a P&A for an item that has the pricing UOM of "CWT".
Team 1 Not testing | 18 | [5 empty] | Perform a P&A for an item that has the pricing UOM of "MST". | [7 empty] | Tested by Team 2
Passed | 19 | [5 empty] | Perform a P&A for an item that does not have contract pricing - bracket pricing will show. Should be an item w/ 1 bracket.
Team 1 Not testing | 20 | [5 empty] | Perform a P&A for an item that does not have contract pricing - bracket pricing will show. Should be an item w/ 3 brackets | [7 empty] | Tested by Team 2
Passed | 21 | [5 empty] | Perform a P&A for an item that does not have contract pricing - bracket pricing will show. Should be an item w/ 6 brackets (used 5 bracket - no 6 bracket available)
Team 1 Not testing | 22 | [5 empty] | Perform a test with an invalid item number - This should be stopped in the Web Channel and Call Center. Line Status Code of 01 would be sent from MAX if an invalid item made it through. | [7 empty] | Tested by Team 2
Team 1 Not testing | 23 | [5 empty] | Perform a test to get Line Status Code of 04-Overflow error (UOM/Price Conversion) Any Quantity or price calculation that's unsuccessful) (use item 2001015 and order 10,000 cartons for example) | [7 empty] | Tested by Team 2
Team 1 Not testing | 24 | [5 empty] | Perform a test to get Line Status Code of 06 - Item is suspended (Item Master) | [7 empty] | Tested by Team 2
Team 1 Not testing | 25 | [5 empty] | Perform a test to get Line Status Code of 07-Item is non-standard. In ITMSTX the IMSTDI is "N" | [7 empty] | Tested by Team 2
Team 1 Not testing | 26 | [5 empty] | Perform a test to get Line Status Code of 08 Item Balance record missing | [7 empty] | Tested by Team 2
Team 1 Not testing | 27 | [5 empty] | Perform a test to get Lines Status Code of 09 - Suspended Item Balance | [7 empty] | Tested by Team 2
Team 1 Not testing | 28 | [5 empty] | Perform a test with non-numeric requested quantity - This should be stopped in the Web Channel and Call Center. Line Status Code of 10 would be sent from MAX if an invalid requested qty made it through. | [7 empty] | Tested by Team 2
General Tests:
Team 1 Not testing | 29 | [5 empty] | Verify that entry can not be made for larger than the MAX Interface size for the following fields: Requested Quantity (10,3 = 7 whole and 3 decimals) Requested Quantity UOM (3) Item number (15) | [7 empty] | Tested by Team 2
Team 1 Not testing | 30 | [5 empty] | Perform a P&A for Direct, Indirect, Warehouse performed together | [7 empty] | Tested by Team 2
Passed | 31 | [5 empty] | Perform a stock check for a customer who has a transfer circle warehouse w/ 1Day Service (2 is listed as the number of days in the Web Alternate Transfer Circle.) Verify that the quantity available displays correctly.
Passed | 32 | [5 empty] | Perform a stock check for a customer who has a transfer circle warehouse w/ 2 Day Service (3 is listed as the number of days in the Web Alternate Transfer Circle.) Verify that the quantity available displays correctly.
Team 1 Not testing | 33 | [5 empty] | Perform a stock check for a close out item. The stock check will be return pricing and availability information the same as a non-close out item. (CL 1.0 - JIRA 400) | [7 empty] | Tested by Team 2
Team 1 Not testing | 34 | [5 empty] | In this test there will not be any transfer warehouses in the transfer circle for the ordering (primary) warehouse. Verify the quantity available displays correctly. Precondition: The ordering warehouse will be set up to not have any transfer circle warehouses only quantities available in the primary warehouse. | [7 empty] | Tested by Team 2
Passed | 35 | [5 empty] | In this test there will be 3 transfer warehouses in the transfer circle for the ordering (primary) warehouse. Verify the quantity available displays correctly.
Passed | 36 | [5 empty] | In this test there will be 16 transfer warehouses in the transfer circle for the ordering (primary) warehouse. Verify the quantity available displays correctly.
Passed | 37 | [5 empty] | Perform a P&A when the order multiple is incorrect. MAX sends the correct quantities available.
Passed | 38 | [5 empty] | Perform a P&A with no contract and no bracket pricing - List price should display for the item
Passed | 39 | [5 empty] | Perform P&A for item with rebate to make sure the rebated cost shows
Passed | 40 | [5 empty] | Perform P&A for customer who has Quantity break pricing set up in MAX but order something other than the bracket starting amount. for example: customer #60/6800068 Raff -- item #2036204 - order 2 ctn pricing is set up -- less or equal to 1 ctn = 3 ctn bracket (57.84) AND Greater than 1 ctn = 5 ctn bracket (56.19)
Passed | 41 | [5 empty] | Verify a Suspended Ship To will return P&A
Passed | 42 | [5 empty] | Perform a P&A for a Ship To that has a different primary warehouse than the Bill To. P&A results should return based on the Ship To transfer circle.
Passed | 43 | [5 empty] | Perform a P&A after the cut off times for the primary and transfer warehouses. Verify the quantities available display in the correct categories.
Passed | 44 | [5 empty] | Perform a P&A for each UOM for an item with 4 or more UOMs. - Facility Supplies - for a customer whose Pricing Warehouse is different than its Primary Warehouse.
Passed | 45 | [5 empty] | Perform a P&A for each UOM for an item with 4 or more UOMs. - Packaging - for a customer whose Pricing Warehouse is different than its Primary Warehouse. | [7 empty] | updated 8/3/11 - dh
Passed | 46 | [5 empty] | Perform a P&A for each UOM for an item with 4 or more UOMs. - Graphics - for a customer whose Pricing Warehouse is different than its Primary Warehouse.
Passed | 47 | [5 empty] | Perform a P&A for each UOM for an item with 4 or more UOMs. - Paper - for a customer whose Pricing Warehouse is different than its Primary Warehouse.
Paste above this row your Insert Copied Cells row(s)

## DataMap1
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0004010326-000 |  | 2 | Total Pass: | 0 | 0
Ship To: | Column | 90_M-0004010326-000001 |  |  | Total Fail: | 2 | 0 | 0
Test Case #: |  | Use Case Process Description: | Vanilla test - Stock check one item and there are no failures expected.
1
Role / Model / User Type / Security: |  |  | bbp001 / ship to 000001 / Password1 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Vanilla test - Stock check one item and there are no failures. - Web Channel (WC) |  |  | 2011-07-11 | F |  |  | 2384
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page | Next Gen Performs the Stock Check and Returns results. | As expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail | Pricing information displaying on Next Gen reflects MAX pricing information. | Pricing in MAX and WC are not displaying the same. WC is not rounding to the 5 decimal, and MAX is. Price in WC = 273.17240 per thousand and the price in MAX is 273.17241 per thousand.
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail & MIL | Availability information displaying on Next Gen reflects MAX availability information. | As expected
Test Case 2.0 Description: | y | Vanilla test - Stock check one item and there are no failures. - Call Center (CC) |  |  | 2011-07-11 | F |  |  | 2384
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | Pricing in MAX and CC are not displaying the same. Item cost in CC is 89.69999 and the cost in MAX is /CWT, and MAX is.89.70000/CWT
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | As expected
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 2260512 | 500 | sheet
|  | 2260512 | 4000 | sheets
|  | 2260512 | 1 | skid
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap4
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0004010326-000 |  | 2 | Total Pass: | 2 | 2
Ship To: | Column | 90_M-0004010326-000001 |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | Test using the customer's 1st Ship-To. Data displays in Next Gen as in MAX and there are no failures expected. (Bill - Verify the incoming string has the correct Ship To.)
4
Role / Model / User Type / Security: |  |  | bbp001 / ship to 000001 / Password1 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Test using the customer's 1st Ship-To. Data displays in Next Gen as in MAX for the Ship To and there are no failures expected. - Web Channel (WC) |  |  | 2011-07-11 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page | Next Gen Performs the Stock Check and Returns results. | As Expected
2.2 |  | (Bill - Verify the incoming string has the correct Ship To.) | The incoming string has the correct Ship To. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail | Availability information displaying on Next Gen reflects MAX availability information. | as Expected
Test Case 2.0 Description: | y | Test using the customer's 1st Ship-To. Data displays in Next Gen as in MAX for the Ship To and there are no failures expected. - Call Center (CC) |  |  | 2011-07-11 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
2.2 |  | (Bill - Verify the incoming string has the correct Ship To.) | The incoming string has the correct Ship To. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | as Expected
Test Case 3.0 Description: | [6 empty] | 0
Step 1
Step 2
Step 3
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 5221660 | 4 | package
|  | 5221660 | 1 | carton
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap5
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0004010326-000 |  | 2 | Total Pass: | 2 | 2
Ship To: | Column | 90_M-0004010326-000002 |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | Test using the customer's 2nd Ship-To. Data displays in Next Gen as in MAX and there are no failures expected. (Bill - Verify the incoming string has the correct Ship To.)
5
Role / Model / User Type / Security: |  |  | bbp001 / Password1 / ship to #2 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Test using the customer's 2nd Ship-To. Data displays in Next Gen as in MAX for the Ship To and there are no failures expected. - Web Channel (WC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page | Next Gen Performs the Stock Check and Returns results. | As Expected
2.2 |  | (Bill - Verify the incoming string has the correct Ship To.) | The incoming string has the correct Ship To. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Test Case 2.0 Description: | y | Test using the customer's 2nd Ship-To. Data displays in Next Gen as in MAX for the Ship To and there are no failures expected. - Call Center (CC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
2.2 |  | (Bill - Verify the incoming string has the correct Ship To.) | The incoming string has the correct Ship To. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 5376544 | 1 | Roll
|  | 5376544 | 4 | Rolls
|  | 5376544 | 5 | Cartons
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap6
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0004010326-000 |  | 2 | Total Pass: | 2 | 2
Ship To: | Column | 90_M-0004010326-000008 |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | Test using a customer with more than 3 Ship To's and use the last Ship To Data displays in Next Gen as in MAX and there are no failures expected. (Bill - Verify the incoming string has the correct Ship To.)
6
Role / Model / User Type / Security: |  |  | bbp001 / Password1 / ship to #2 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Test using a customer with more than 3 Ship To's and use the last Ship To. Data displays in Next Gen as in MAX for the Ship To and there are no failures expected. - Web Channel (WC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page & MIL | Next Gen Performs the Stock Check and Returns results. | As Expected
2.2 |  | (Bill - Verify the incoming string has the correct Ship To.) | The incoming string has the correct Ship To. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail & MIL | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail & MIL | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Test Case 2.0 Description: | y | Test using a customer with more than 3 Ship To's and use the last Ship To. Data displays in Next Gen as in MAX for the Ship To and there are no failures expected. - Call Center (CC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
2.2 |  | (Bill - Verify the incoming string has the correct Ship To.) | The incoming string has the correct Ship To. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX availability information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX pricing information. | As Expected
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 2025884 | 3 | Sleeves
|  | 2025884 | 40 | Sleeves
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap7
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0001018921-000 |  | 2 | Total Pass: | 2 | 2
Ship To: | Column | 90_M-0001018921-000222 |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | Test Header Status Code 03 -Perform a test with an invalid Ship To - This should be stopped in the Web Channel and Call Center. Line Status Code of 03 would be sent from MAX if an P&A made it through.
7
Role / Model / User Type / Security: |  |  | lpi008 / Password1 / Ship to #222 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Test Header Status Code 03 -Perform a test with an invalid Ship To - This should be stopped in the Web Channel and Call Center. Line Status Code of 03 would be sent from MAX if an P&A made it through. - Web Channel (WC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
1b |  | Delete the Ship To in MAX.
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: - Validate pricing information is NOT displayed in Web Channel on Prod Detail | Pricing information Is Not displaying on Next Gen. Message is displayed to customer to call customer service. | As Expected
Step 4 |  | Validate Availability Information: - Availability information is Not displayed in Web Channel on Prod Detail & MIL | Availability information is Not displaying on Next Gen. | As Expected
Test Case 2.0 Description: | y | Vanilla test - Stock check one item and there are no failures. - Call Center (CC) |  |  | 2011-07-12 | PE | PE
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
1b |  | Delete the Ship To in MAX.
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: - Validate pricing information is NOT displayed in Call Center | Pricing information Is Not displaying on Next Gen. Message is displayed. | As Expected
Step 4 |  | Validate Availability Information: - Availability information is Not displayed in Call Center | Availability information is Not displaying on Next Gen. | As Expected… The Call Center error message was not clear on what the exception is, would like to see more details in the description such as - Unknown Line Error - Ship to not valid
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 2200564 | 500 | sheets
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap12
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0001190060-000 |  | 2 | Total Pass: | 1 | 1
Ship To: | Column | 90_M-0001190060-000001 |  |  | Total Fail: | 1 | 0 | 0
Test Case #: |  | Use Case Process Description: | Perform a P&A for an item that was searched by customer part number (a valid customer part number exists in MAX). This customer part number also is a valid MAX item number for a different item. Confirm the P&A is sent based on the valid legacy number for the customer part number. There are no failures expected.
12
Role / Model / User Type / Security: |  |  | bps001 Password1 / Ship To 000001 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Perform a P&A for an item that was searched by customer part number (a valid customer part number exists in MAX). This customer part number also is a valid MAX item number for a different item. Confirm the P&A is sent based on the valid legacy number for the customer part number. There are no failures expected. - Web Channel (WC) |  |  | 2011-07-11 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Test Case 2.0 Description: | y | Perform a P&A for an item that was searched by customer part number (a valid customer part number exists in MAX). This customer part number also is a valid MAX item number for a different item. Confirm the P&A is sent based on the valid legacy number for the customer part number. There are no failures expected. - Call Center (CC) |  |  | 2011-07-11 | F
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | When entering a "customer part" number in Call Center it is not recognizing the item #, you must enter the xpedx part number and the customer part # in order to get data.
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information.
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information.
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 2028062 / 2028062 - MAX and Customer Part number are the same | 1 | carton
|  | 2028062 / 2028062 - MAX and Customer Part number are the same | 1 | each
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap12 (2)
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0001190060-000 |  | 2 | Total Pass: | 1 | 2
Ship To: | Column | 90_M-0001190060-000001 |  |  | Total Fail: | 1 | 0 | 0
Test Case #: |  | Use Case Process Description: | Perform a P&A for an item that was searched by customer part number (a valid customer part number exists in MAX). This customer part number and MAX item are different, and the customer item # is NOT a valid MAX item # Confirm the P&A is sent based on the valid legacy number for the customer part number.
12
Role / Model / User Type / Security: |  |  | bps001 Password1 / Ship To 000001 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Perform a P&A for an item that was searched by customer part number (a valid customer part number exists in MAX). This customer part number and MAX item are different, and the customer item # is NOT a valid MAX item # Confirm the P&A is sent based on the valid legacy number for the customer part number. - Web Channel (WC) |  |  | 2011-07-11 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Test Case 2.0 Description: | y | Perform a P&A for an item that was searched by customer part number (a valid customer part number exists in MAX). This customer part number and MAX item are different, and the customer item # is NOT a valid MAX item # Confirm the P&A is sent based on the valid legacy number for the customer part number. - Call Center (CC) |  |  | 2011-08-03 | F | PE
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | When entering a customer part number in Call Center it is not recognizing the item # (Retested on 8/3/11 - CC not consistent with UOM.) | CC not rep-populating the UOM after update, but x-ref is correct.
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | When entering a customer part number in Call Center it is not recognizing the item # (Retested on 8/3/11 - CC not consistent with UOM.) | CC not rep-populating the UOM after update, but x-ref is correct.
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | When entering a customer part number in Call Center it is not recognizing the item # (Retested on 8/3/11 - CC not consistent with UOM.) | CC not rep-populating the UOM after update, but x-ref is correct.
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 1787722 / 527046 - MAX and Customer Part number are different | 12 | Bottles
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap12 (3)
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0001190060-000 |  | 2 | Total Pass: | 1 | 1
Ship To: | Column | 90_M-0001190060-000001 |  |  | Total Fail: | 1 | 0 | 0
Test Case #: |  | Use Case Process Description: | Perform a P&A for an item that was searched by customer part number (a valid customer part number exists in MAX). This customer part number is a MAX item # but not the same item as the MAX item # being tested. Confirm the P&A is sent based on the valid legacy number for the customer part number. There are no failures expected.
12
Role / Model / User Type / Security: |  |  | bps001 Password1 / Ship To 000001 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Perform a P&A for an item that was searched by customer part number (a valid customer part number exists in MAX). This customer part number is a MAX item # but not the same item as the MAX item # being tested. Confirm the P&A is sent based on the valid legacy number for the customer part number. - Web Channel (WC) |  |  | 2011-07-11 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Test Case 2.0 Description: | y | Perform a P&A for an item that was searched by customer part number (a valid customer part number exists in MAX). This customer part number is a MAX item # but not the same item as the MAX item # being tested. Confirm the P&A is sent based on the valid legacy number for the customer part number. - Call Center (CC) |  |  | 2011-07-11 | F
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | When entering a customer part number in Call Center it is not recognizing the item #
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information.
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information.
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 2255602 MAX # / 5281576 Customer # | 5000 | sheets
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap13
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0001190060-000 |  | 2 | Total Pass: | 1 | 2
Ship To: | Column | 90_M-0001190060-000001 |  |  | Total Fail: | 1 | 0 | 0
Test Case #: |  | Use Case Process Description: | Perform a P&A for an item that has a corresponding customer cross reference and the Customer UOM is not a valid MAX UOM. There are no failures expected.
13
Role / Model / User Type / Security: |  |  | bps001 Password1 / Ship To 000001 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Perform a P&A for an item that has a corresponding customer cross reference and the Customer UOM is not a valid MAX UOM. There are no failures expected. Web Channel (WC) |  |  | 2011-07-11 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page & MIL | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail & MIL | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail & MIL | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Test Case 2.0 Description: | y | Perform a P&A for an item that has a corresponding customer cross reference and the Customer UOM is not a valid MAX UOM. There are no failures expected. - Call Center (CC) |  |  | 2011-07-11 | F | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected - Note: Cost in Call center is $28.16419 and MAX Cost is 28.16420
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | Customer #527046 / MAX #1787722 | 24 | Bottles
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap14
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0001190060-000 |  | 2 | Total Pass: | 2 | 2
Ship To: | Column | 90_M-0001190060-000001 |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | Perform a P&A for an item that has a corresponding customer cross reference and the Customer UOM has a conversion factor other than 1. There are no failures expected.
14
Role / Model / User Type / Security: |  |  | bps001 Password1 / Ship To 000001 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Perform a P&A for an item that has a corresponding customer cross reference and the Customer UOM has a conversion factor other than 1. There are no failures expected. - Web Channel (WC) |  |  | 2011-07-11 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page & MIL | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail & MIL | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail & MIL | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Test Case 2.0 Description: | y | Perform a P&A for an item that has a corresponding customer cross reference and the Customer UOM has a conversion factor other than 1. There are no failures expected. - Call Center (CC) |  |  | 2011-07-11 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 2028062 | 5 | each
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap15
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0001190060-000 |  | 1 | Total Pass: | 1 | 1
Ship To: | Column | 90_M-0001190060-000001 |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | Perform a P&A where the requested quantity is in decimals. (Call Center Only)
15
Role / Model / User Type / Security: |  |  | bps001 Password1 / Ship To 000001 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Perform a P&A where the requested quantity is in decimals. (Call Center Only) No errors are expected. |  |  | 2011-07-11 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 2002562 | 1.5 | Cartons
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap16
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 12_M-0000303739-000 |  | 2 | Total Pass: | 1 | 2
Ship To: | Column | 12_M-0000303739-000001 |  |  | Total Fail: | 1 | 0 | 0
Test Case #: |  | Use Case Process Description: | Perform a P&A for an item that has the pricing UOM of "M". There are no failures expected.
16
Role / Model / User Type / Security: |  |  | ecm001 / Password1 / ship to 000001 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Perform a P&A for an item that has the pricing UOM of "M". There are no failures expected. - Web Channel (WC) |  |  | 2011-07-11 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page & MIL | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail & MIL | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail & MIL | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Test Case 2.0 Description: | y | Perform a P&A for an item that has the pricing UOM of "M". There are no failures expected. - Call Center (CC) |  |  | 2011-07-11 | F | PE
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | the QOH field in Call Center is not wide enough to display the entire QOH. Should be 202500 sheets and we are seeing 20250 sheets in Call Center | JIRA opened for this issue.
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 2251797 | 5000 | sheets
|  | 2251797 | 2500 | sheets
|  | 2251797 | 25000 | sheets
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap17
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0004010326-000 |  | 2 | Total Pass: | 2 | 2
Ship To: | Column | 90_M-0004010326-000001 |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | Perform a P&A for an item that has the pricing UOM of "CWT". There are no failures expected.
17
Role / Model / User Type / Security: |  |  | bbp001 / Password1 / ship to #1 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Perform a P&A for an item that has the pricing UOM of "CWT". There are no failures expected. - Web Channel (WC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page & MIL | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail & MIL | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail & MIL | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Test Case 2.0 Description: | y | Perform a P&A for an item that has the pricing UOM of "CWT". There are no failures expected. - Call Center (CC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 2329383 | 1000 | sheets
|  | 2329383 | 10 | cartons
|  | 2329383 | 10000 | sets
|  | 2329383 | 2 | M sets
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap19
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0004010326-000 |  | 2 | Total Pass: | 2 | 2
Ship To: | Column | 90_M-0004010326-000001 |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | Perform a P&A for an item that does not have contract pricing - bracket pricing will show. Should be an item w/ 1 bracket. There are no failures expected.
19
Role / Model / User Type / Security: |  |  | bbp001 / Password1 / ship to #1 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Perform a P&A for an item that does not have contract pricing - bracket pricing will show. Should be an item w/ 1 bracket. There are no failures expected. - Web Channel (WC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page & MIL | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail & MIL | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail & MIL | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Test Case 2.0 Description: | y | Perform a P&A for an item that does not have contract pricing - bracket pricing will show. Should be an item w/ 1 bracket. There are no failures expected. - Call Center (CC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap21
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | input company/customer here |  | 2 | Total Pass: | 2 | 2
Ship To: | Column | input ship to here |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | Perform a P&A for an item that does not have contract pricing - bracket pricing will show. Should be an item w/ 6 brackets. There are no failures expected.
21
Role / Model / User Type / Security: |  |  | Enter UserId/Password used | Region Environment: | Firefox & IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Perform a P&A for an item that does not have contract pricing - bracket pricing will show. Should be an item w/ 6 brackets. There are no failures expected. - Web Channel (WC) |  |  | 2011-07-12 | P | P | 0
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page & MIL | Next Gen Performs the Stock Check and Returns results.
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail & MIL | Pricing information displaying on Next Gen reflects MAX pricing information.
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail & MIL | Availability information displaying on Next Gen reflects MAX availability information.
Test Case 2.0 Description: | y | Perform a P&A for an item that does not have contract pricing - bracket pricing will show. Should be an item w/ 6 brackets. There are no failures expected. - Call Center (CC) |  |  | 2011-07-12 | P | P | 0
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results.
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information.
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information.
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap31
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0001190061-000 |  | 2 | Total Pass: | 2 | 2
Ship To: | Column | 90_M-0001190061-000011 |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | Perform a stock check for a customer who has a transfer circle warehouse w/ 1 Day Service (2 is listed as the number of days in the Web Alternate Transfer Circle.) Verify that the quantity available displays correctly. There are no failures expected.
31
Role / Model / User Type / Security: |  |  | bbp001 / Password1 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Perform a stock check for a customer who has a transfer circle warehouse w/ 1 Day Service (2 is listed as the number of days in the Web Alternate Transfer Circle.) Verify that the quantity available displays correctly. There are no failures expected. - Web Channel (WC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page & MIL | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail & MIL | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail & MIL | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Test Case 2.0 Description: | y | Perform a stock check for a customer who has a transfer circle warehouse w/ 1 Day Service (2 is listed as the number of days in the Web Alternate Transfer Circle.) Verify that the quantity available displays correctly. There are no failures expected. |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 2255602 | 5 | cartons
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap32
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0001190061-000 |  | 2 | Total Pass: | 2 | 2
Ship To: | Column | 90_M-0001190061-000011 |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | Perform a stock check for a customer who has a transfer circle warehouse w/ 2 Day Service (3 is listed as the number of days in the Web Alternate Transfer Circle.) Verify that the quantity available displays correctly.
32
Role / Model / User Type / Security: |  |  | bbp001 / Password1 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Perform a stock check for a customer who has a transfer circle warehouse w/ 2 Day Service (3 is listed as the number of days in the Web Alternate Transfer Circle.) Verify that the quantity available displays correctly. There are no failures expected. - Web Channel (WC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page & MIL | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail & MIL | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail & MIL | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Test Case 2.0 Description: | y | Perform a stock check for a customer who has a transfer circle warehouse w/ 2 Day Service (3 is listed as the number of days in the Web Alternate Transfer Circle.) Verify that the quantity available displays correctly. There are no failures expected. - Call Center |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 2255602 | 25 | cartons
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap35
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0001190060-000 |  | 2 | Total Pass: | 2 | 2
Ship To: | Column | 90_M-0001190060-000001 |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | In this test there will be 3 transfer warehouses in the transfer circle for the ordering (primary) warehouse. Verify the quantity available displays correctly.
35
Role / Model / User Type / Security: |  |  | bps001/Password1 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | In this test there will be 3 transfer warehouses in the transfer circle for the ordering (primary) warehouse. Verify the quantity available displays correctly. - Web Channel (WC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page & MIL | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail & MIL | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail & MIL | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Test Case 2.0 Description: | y | In this test there will be 3 transfer warehouses in the transfer circle for the ordering (primary) warehouse. Verify the quantity available displays correctly. - Call Center |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 2042997 | 36 | roll
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap36
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0001190060-000 |  | 2 | Total Pass: | 2 | 2
Ship To: | Column | 90_M-0001190060-000001 |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | In this test there will be 13 transfer warehouses in the transfer circle for the ordering (primary) warehouse. Verify the quantity available displays correctly.
36
Role / Model / User Type / Security: |  |  | bps001/Password1 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | In this test there will be 16 transfer warehouses in the transfer circle for the ordering (primary) warehouse. Verify the quantity available displays correctly. - Web Channel (WC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page & MIL | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail & MIL | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail & MIL | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Test Case 2.0 Description: | y | In this test there will be 16 transfer warehouses in the transfer circle for the ordering (primary) warehouse. Verify the quantity available displays correctly. - Call Center |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 2042997 | 36 | Rolls
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap37
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0001018921-000 |  | 2 | Total Pass: | 2 | 2
Ship To: | Column | 90_M-0001018921-000001 |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | Perform a P&A when the order multiple is incorrect. MAX sends the correct quantities available.
38
Role / Model / User Type / Security: |  |  | lpi001 / Password1 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Perform a P&A when the order multiple is incorrect. MAX sends the correct quantities available. - Web Channel (WC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page & MIL | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail & MIL | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail & MIL | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Test Case 2.0 Description: | y | Perform a P&A when the order multiple is incorrect. MAX sends the correct quantities available. - Call Center |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | as Expected
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 5259081 | 1 | Carton
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap38
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0001018921-000 |  | 2 | Total Pass: | 2 | 2
Ship To: | Column | 90_M-0001018921-000001 |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | Perform a P&A with no contract and no bracket pricing - List price should display.
37
Role / Model / User Type / Security: |  |  | lpi001 / Password1 | Region Environment: | IE8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Perform a P&A with no contract and no bracket pricing - List price should display. Verify the quantity available displays correctly. - Web Channel (WC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page & MIL | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail & MIL | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail & MIL | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Test Case 2.0 Description: | y | In this test there will be 16 transfer warehouses in the transfer circle for the ordering (primary) warehouse. Verify the quantity available displays correctly. - Call Center |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 5259081 | 1 | Carton
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap39
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0001018921-000 |  | 2 | Total Pass: | 2 | 2
Ship To: | Column | 90_M-0001018921-000001 |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | Perform P&A for item with rebate to make sure the rebated cost shows
39
Role / Model / User Type / Security: |  |  | lpi001 / Password1 / ship to #1 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Perform P&A for item with rebate to make sure the rebated cost shows - Web Channel (WC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Test Case 2.0 Description: | y | Perform P&A for item with rebate to make sure the rebated cost shows - Call Center |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 5007726 | 5 | each
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap40
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0001018921-000 |  | 2 | Total Pass: | 2 | 2
Ship To: | Column | 90_M-0001018921-000001 |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | Perform P&A for customer who has Quantity break pricing set up in MAX but order something other than the bracket starting amount. for example: customer #60/6800068 Raff -- item #2036204 - order 2 ctn pricing is set up -- less or equal to 1 ctn = 3 ctn bracket (57.84) AND Greater than 1 ctn = 5 ctn bracket (56.19)
40
Role / Model / User Type / Security: |  |  | lpi001 / Password1 / ship to #1 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Perform P&A for customer who has Quantity break pricing set up in MAX but order something other than the bracket starting amount. for example: customer #60/6800068 Raff -- item #2036204 - order 2 ctn pricing is set up -- less or equal to 1 ctn = 3 ctn bracket (57.84) AND Greater than 1 ctn = 5 ctn bracket (56.19) - Web Channel (WC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page & MIL | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail & MIL | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail & MIL | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Test Case 2.0 Description: | y | Perform P&A for customer who has Quantity break pricing set up in MAX but order something other than the bracket starting amount. for example: customer #60/6800068 Raff -- item #2036204 - order 2 ctn pricing is set up -- less or equal to 1 ctn = 3 ctn bracket (57.84) AND Greater than 1 ctn = 5 ctn bracket (56.19) - Call Center |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 2036204 | 2 | carton
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap41
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0001190061-000 |  | 2 | Total Pass: | 2 | 2
Ship To: | Column | 90_M-0001190061-000011 |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | Verify a Suspended Ship To will return P&A
41
Role / Model / User Type / Security: |  |  | bps001 / Password1 / shipt to #11 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Verify a Suspended Ship To will return P&A - Web Channel (WC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page & MIL | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail & MIL | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail & MIL | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Test Case 2.0 Description: | y | Verify a Suspended Ship To will return P&A - Call Center |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 2255602 | 5000 | sheets
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap42
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0001190061-000 |  | 2 | Total Pass: | 2 | 2
Ship To: | Column | 90_M-0001190061-000011 |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | Perform a P&A for a Ship To that has a different primary warehouse than the Bill To. P&A results should return based on the Ship To transfer circle.
42
Role / Model / User Type / Security: |  |  | bps001 / Password1 / shipt to #11 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Perform a P&A for a Ship To that has a different primary warehouse than the Bill To. P&A results should return based on the Ship To transfer circle. - Web Channel (WC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page & MIL | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail & MIL | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail & MIL | Availability information displaying on Next Gen reflects MAX availability information. | as Expected
Test Case 2.0 Description: | y | Perform a P&A for a Ship To that has a different primary warehouse than the Bill To. P&A results should return based on the Ship To transfer circle. - Call Center |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 2255602 | 5000 | sheets
|  | 2255602 | 15000 | sheets
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap43
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0004010326-000 |  | 2 | Total Pass: | 2 | 2
Ship To: | Column | 90_M-0004010326-000001 |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | Perform a P&A after the cut off times for the primary and transfer warehouses. Verify the quantities available display in the correct categories.
43
Role / Model / User Type / Security: |  |  | bbp001 / Password1 / ship to address #1 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Perform a P&A after the cut off times for the primary and transfer warehouses. Verify the quantities available display in the correct categories. - Web Channel (WC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page & MIL | Next Gen Performs the Stock Check and Returns results.
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail & MIL | Pricing information displaying on Next Gen reflects MAX pricing information.
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail & MIL | Availability information displaying on Next Gen reflects MAX availability information.
Test Case 2.0 Description: | y | Perform a P&A after the cut off times for the primary and transfer warehouses. Verify the quantities available display in the correct categories. - Call Center |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 2255602 | 500 | sheets
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap44
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0004010326-000 |  | 2 | Total Pass: | 2 | 2
Ship To: | Column | 90_M-0004010326-000001 |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | Perform a P&A for each UOM for an item with 3or more UOMs. - Facility Supplies - for a customer whose Pricing Warehouse is different than its Primary Warehouse.
44
Role / Model / User Type / Security: |  |  | bbp001 / Password1 / ship to #1 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Perform a P&A for each UOM for an item with 4 or more UOMs. - Facility Supplies - for a customer whose Pricing Warehouse is different than its Primary Warehouse. - Web Channel (WC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Test Case 2.0 Description: | y | Perform a P&A for each UOM for an item with 4 or more UOMs. - Facility Supplies - for a customer whose Pricing Warehouse is different than its Primary Warehouse. - Call Center |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 5360851 | 300 | Pair
|  | 5360851 | 2 | Cartons
|  | 5360851 | 2 | Dozen
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap45
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0004010326-000 |  | 2 | Total Pass: | 0 | 2
Ship To: | Column | 90_M-0004010326-000001 |  |  | Total Fail: | 2 | 0 | 0
Test Case #: |  | Use Case Process Description: | Perform a P&A for each UOM for an item with 4 or more UOMs. - Packaging - for a customer whose Pricing Warehouse is different than its Primary Warehouse.
45
Role / Model / User Type / Security: |  |  | bbp001 / Password1 / ship to #1 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Perform a P&A for each UOM for an item with 4 or more UOMs. - Packaging - for a customer whose Pricing Warehouse is different than its Primary Warehouse. - Web Channel (WC) |  |  | 2011-07-12 | F | P |  | 2408
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page | Next Gen Performs the Stock Check and Returns results.
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail | Pricing information displaying on Next Gen reflects MAX pricing information. | The price on the WC is showing $0.11 per thousand for quantities below 5 cartons and $2.39 for quantities 5 cartons and above. The price in MAX is $2.39 for all quantities. This issue also exists in current xpedx.com. JIRA 2408 corrected the issue identified here - Test passes - dh 8/3/11.
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail | Availability information displaying on Next Gen reflects MAX availability information.
Test Case 2.0 Description: | y | Perform a P&A for each UOM for an item with 4 or more UOMs. - Packaging - for a customer whose Pricing Warehouse is different than its Primary Warehouse. - Call Center |  |  | 2011-07-12 | F | P |  | 2408
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results.
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | The price on the CC is showing $0.11 per thousand for quantities below 5 cartons and $2.39 for quantities 5 cartons and above. The price in MAX is $2.39 for all quantities. This issue also exists in current xpedx.com. JIRA 2408 corrected the issue identified here - Test passes - dh 8/3/11.
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information.
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 5297526 | 500 | labels
|  | 5297526 | 25 | Cartons
|  | 5297526 | 20 | Cartons
|  | 5297526 | 15 | Cartons
|  | 5297526 | 10 | Cartons
|  | 5297526 | 5 | Cartons
|  | 5297526 | 4 | Cartons
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap46
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0004010326-000 |  | 2 | Total Pass: | 2 | 2
Ship To: | Column | 90_M-0004010326-000001 |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | Perform a P&A for each UOM for an item with 4 or more UOMs. - Graphics - for a customer whose Pricing Warehouse is different than its Primary Warehouse.
46
Role / Model / User Type / Security: |  |  | bbp001 / Password1 / ship to #1 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Perform a P&A for each UOM for an item with 4 or more UOMs. - Graphics - for a customer whose Pricing Warehouse is different than its Primary Warehouse. - Web Channel (WC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Test Case 2.0 Description: | y | Perform a P&A for each UOM for an item with 4 or more UOMs. - Graphics - for a customer whose Pricing Warehouse is different than its Primary Warehouse. - Call Center |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 5077953 | 5 | Gallons
|  | 5077953 | 3 | Cartons
|  | 5077953 | 12 | Each
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## DataMap47
Test: | Hide | 5156778 - MAX-NG P&A QA test scripts |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
Co#/Customer #: | This | 90_M-0004010326-000 |  | 2 | Total Pass: | 2 | 2
Ship To: | Column | 90_M-0004010326-000001 |  |  | Total Fail: | 0 | 0 | 0
Test Case #: |  | Use Case Process Description: | Perform a P&A for each UOM for an item with 4 or more UOMs. - Paper - for a customer whose Pricing Warehouse is different than its Primary Warehouse.
47
Role / Model / User Type / Security: |  |  | bbp001 / Password1 / ship to #1 | Region Environment: | IE 8 - to T3 in MAX
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Perform a P&A for each UOM for an item with 4 or more UOMs. - Paper - for a customer whose Pricing Warehouse is different than its Primary Warehouse. - Web Channel (WC) |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below | N/A | N/A
Step 2 |  | In Next Gen - WC perform the stock check on Product Detail Page | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in Web Channel on Prod Detail & MIL | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in Web Channel on Prod Detail & MIL | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Test Case 2.0 Description: | y | Perform a P&A for each UOM for an item with 4 or more UOMs. - Paper - for a customer whose Pricing Warehouse is different than its Primary Warehouse. - Call Center |  |  | 2011-07-12 | P | P
Step 1 |  | Record Data: Enter the Company/Customer in row 1 Enter UserId/Password used in row 6 List Item#(s), Qty, UOM below . | N/A | N/A
Step 2 |  | In Next Gen - perform the stock check in Call Center (Basic P&A Call) | Next Gen Performs the Stock Check and Returns results. | As Expected
Step 3 |  | Validate Pricing Information: -Determine the correct price in MAX (OEPRC9, 11 & OEMAIN 26) - Validate all pricing information displayed in CC | Pricing information displaying on Next Gen reflects MAX pricing information. | As Expected
Step 4 |  | Validate Availability Information: -Determine the correct availability in MAX (OEMAIN 26) - Validate all availability information displayed in CC | Availability information displaying on Next Gen reflects MAX availability information. | As Expected
Paste above this row your Insert Copied Cells row(s)
|  | Item Number(s) used: | Requested Quantity: | Requested UOM:
|  | 2329383 | 1000 | sheets
|  | 2329383 | 10 | cartons
|  | 2329383 | 10000 | sets
|  | 2329383 | 2 | M sets
2329383
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## Step UC #.#
RPM #: | Hide | 366398 |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
USD #: | This | 5156778 |  | 0 | Total Pass: | 0 | 0
| Column |  |  |  | Total Fail: | 0 | 0 | 0
Req / Use Case #: |  | Use Case Process Description:
UC #.#
Role / Model / User Type / Security: |  |  |  | Region Environment:
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | [6 empty] | 0
Step 1
Step 2
Step 3
Test Case 2.0 Description: | [6 empty] | 0
Step 1
Step 2
Step 3
Test Case 3.0 Description: | [6 empty] | 0
Step 1
Step 2
Step 3
Paste above this row your Insert Copied Cells row(s)
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## UC #.#
RPM #: | DUMMY COLUMN | 366398 |  | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
USD #: | Hide This | 5156778 |  | 0 | Total Pass: | 0 | 0
| Column |  |  |  | Total Fail: | 0 | 0 | 0
Req / Use Case #: |  | Use Case Process Description:
UC #.#
Role / Model / User Type / Security: |  |  |  | Region Environment:
Test Case # |  | Test Case Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
T1.1 | [6 empty] | 0
T1.2 | [6 empty] | 0
T1.3 | [6 empty] | 0
T1.4 | [6 empty] | 0
T1.5 | [6 empty] | 0
T1.6 | [6 empty] | 0
Paste above this row your Insert Copied Cells row(s)
Note on B1: William Smeltz: Keeps cell numbers in formulas consistent between Step UC and UC worksheets
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## Blank-DO NOT DELETE OR MOVE
DO NOT DELETE OR MOVE THIS WORKSHEET. THANK YOU.

## Step UC Example
RPM #: | Hide | 654321 | Step UC Example | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
USD #: | This | 7654321 |  | 3 | Total Pass: | 2 | 3
| Column |  |  |  | Total Fail: | 1 | 0 | 2
Req / Use Case #: |  | Use Case Process Description: | Verify the user id and their password.
UC 1.0
Role / Model / User Type / Security: |  |  | Customer | Region Environment: | Staging
|  | Step Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
Test Case 1.0 Description: | y | Enter accurate user id and inaccurate password |  |  | 08/10/10 - F 08/11/10 - F 08/12/10 - P | F | P | 2
Step 1 |  | Access the landing page via URL xxx | Landing page displays with fields for user id and password | F - Received page not found error.
Step 2 |  | User enters accurate userid and press Tab key | Cursor moves and displays in password field | F - Cursor stayed in user id field.
Step 3 |  | User enters inaccurate password | Landing page redisplays with error message XXX and cursor placed in password field | As expected
Test Case 1.1 Description: | y | Enter inaccurate user id and accurate password |  |  | 2010-08-10 | PE | PE
Step 1 |  | Access the landing page via URL xxx | Landing page displays with fields for user id and password | As expected
Step 2 |  | User enter inaccurate user id and press <Enter> | Landing page redisplays with error message XXX and cursor placed in user id field | As expected - but different error message
Test Case 2.0 Description: | y | Enter accurate user id and expired password |  |  | 2010-08-10 | P | P
Step 1 |  | Access the landing page via URL xxx | Landing page displays with fields for user id and password | As expected
Step 2 |  | User enters accurate userid and expired password | Landing page redisplayes with error message XXX and cursor placed in password field | As expected
Paste above this row your Insert Copied Cells row(s)
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.

## UC Example
RPM #: | DUMMY COLUMN | 654321 | UC Example | TOTAL UC TEST CASES |  | First Pass | Final Pass | # of Fails
USD #: | Hide This | 7654321 |  | 2 | Total Pass: | 1 | 2
| Column |  |  |  | Total Fail: | 1 | 0 | 2
Req / Use Case #: |  | Use Case Process Description: | This test will verify that fields 3, 3a and 4 from the data map are populated correctly. These fields are consistent for every transaction in the P&A string. The fields are Environment ID, Customer Environment ID, and Company.
UC 1.0
Role / Model / User Type / Security: |  |  | Customer | Region Environment: | Staging
Test Case # |  | Test Case Description Test Input | Acceptance Criteria Test Output | Actual Results Comments | Date Executed | First Pass | Final Pass | # of Fails | JIRA #
T1.1 |  | Perform stock check in migration for an interactive (web) customer. Review the data string or whatever wM has that we can look at | Data in field 3,3a and 4 should be: the letter A followed by a space followed by AM then XX. This should be consistent for every P&A transaction | 1. Field 3a had letter X 2. Field 3 had letter Z 3. As expected | 1. 06/15/2010 2. 06/16/2010 3. 06/17/2010 | F | P | 2
T1.2 |  | Perform stock check in migration for a batch (B2B) customer. Review the data string or whatever wM has that we can look at | Data in field 3,3a and 4 should be: the letter A followed by a space followed by AM then XX. This should be consistent for every P& A transaction. |  | 2010-06-15 | PE | PE
Paste above this row your Insert Copied Cells row(s)
Note on B1: William Smeltz: Keeps cell numbers in formulas consistent between Step UC and UC worksheets
Note on H7: xpedx IT Processes & Tools: BE CAREFUL! These cells includes Unprotected Formulas that automatically populates a value if not "F" in the cell to the left.