## Summary
| Test Case Title: | Browsing Catalog | IE8 |  |  |  | FireFox 3.x |  |  |  | Safari |  |  |  | Saalfeld (IE8) |  |  |  | Bukley Dunton (IE8) |  |  |  | Canada (IE8)
| Test Case # | Test Case Name | Status | Day | Date | Name of Tester | Status | Day | Date | Name of Tester | Status | Day | Date | Name of Tester | Status | Day | Date | Name of Tester | Status | Day | Date | Name of Tester | Status | Day | Date | Name of Tester
| Tab 1. | C1-C2 Catalog Landing Page
| 1 | Catalog Landing Page: C1 - C2 | Fail | 1 | 2011-07-11 | Ryan | Fail | 3 | 2011-07-13 | Ryan | Fail | 5 | 2011-07-15 | Ryan |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 7 | 2011-07-19 | Cindy
| 2 | Catalog Landing Page - Anonymous: C1 - C2 | Fail | 1 | 2011-07-11 | Cindy | Fail | 3 | 2011-07-13 | Cindy | Fail | 5 | 2011-07-15 | Cindy |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 7 | 2011-07-19 | Cindy
| Tab 2. | C1-C2 Expanded
| 3 | Product Categories: C1 - C2 (Expanded) | Fail | 1 | 2011-07-11 | Ryan | Fail | 3 | 2011-07-13 | Ryan | Fail | 5 | 2011-07-15 | Ryan |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 7 | 2011-07-19 | Cindy
| 4 | Product Categories - Anonymous: C1 - C2 (Expanded) | Fail | 1 | 2011-07-11 | Cindy | Fail | 3 | 2011-07-13 | Cindy | Fail | 5 | 2011-07-15 | Cindy |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 7 | 2011-07-19 | Cindy
| Tab 3. | C2-C3 Categories
| 5 | Product Categories - B2B Grid View: C2 - C3 | Fail | 1 | 2011-07-11 | Ryan | Fail | 3 | 2011-07-13 | Ryan | Fail | 5 | 2011-07-15 | Ryan |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 7 | 2011-07-19 | Cindy
| 6 | Product Categories - B2C Full View: C2 - C3 | Pass | 2 | 2011-07-12 | Ryan | Pass | 4 | 2011-07-14 | Ryan | Pass | 5 | 2011-07-15 | Ryan |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 7 | 2011-07-19 | Cindy
| 7 | Product Categories - B2C Full View: C2 - C3 My Price & Availability | Pass | 2 | 2011-07-12 | Ryan | Pass | 4 | 2011-07-14 | Ryan | Pass | 5 | 2011-07-15 | Ryan |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 7 | 2011-07-19 | Cindy
| 8 | Product Categories - B2C Full View: C2 - C3 Update My Price & Availability | Pass | 2 | 2011-07-12 | Ryan | Pass | 4 | 2011-07-14 | Ryan | Pass | 5 | 2011-07-15 | Ryan |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 7 | 2011-07-19 | Cindy
| 9 | Product Categories - B2C Full View: C2 - C3 User without 'View Price' permission | Pass | 2 | 2011-07-12 | Cindy | Pass | 4 | 2011-07-14 | Cindy | Pass | 5 | 2011-07-15 | Cindy |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 7 | 2011-07-19 | Cindy
| 10 | Product Categories - B2C Condensed View: C2 - C3 | Pass | 2 | 2011-07-12 | Ryan | Pass | 4 | 2011-07-14 | Ryan | Pass | 5 | 2011-07-15 | Ryan |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 7 | 2011-07-19 | Cindy
| 11 | Product Categories - B2C Mini View: C2 - C3 | Pass | 2 | 2011-07-12 | Ryan | Pass | 4 | 2011-07-14 | Ryan | Pass | 5 | 2011-07-15 | Ryan |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 7 | 2011-07-19 | Cindy
| 12 | Product Categories - B2B Grid View - Anonymous: C2 - C3 | Fail | 1 | 2011-07-11 | Cindy | Fail | 1 | 2011-07-14 | Cindy | Fail | 5 | 2011-07-15 | Cindy |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 7 | 2011-07-19 | Cindy
| 13 | Product Categories - B2C Full View - Anonymous: C2 - C3 | Pass | 2 | 2011-07-12 | Cindy | Pass | 4 | 2011-07-14 | Cindy | Pass | 5 | 2011-07-15 | Cindy |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 7 | 2011-07-19 | Cindy
| 14 | Product Categories - B2C Condensed View - Anonymous: C2 - C3 | Fail | 2 | 2011-07-12 | Cindy | Fail | 4 | 2011-07-14 | Cindy | Fail | 5 | 2011-07-15 | Cindy |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 7 | 2011-07-19 | Cindy
| 15 | Product Categories - B2C Mini View - Anonymous: C2 - C3 | Fail | 2 | 2011-07-12 | Cindy | Fail | 4 | 2011-07-14 | Cindy | Fail | 5 | 2011-07-15 | Cindy |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 7 | 2011-07-19 | Cindy
| Tab 4. | C3-C4 Categories
| 16 | Product Categories - B2B Grid View: C3 - C4 | Fail | 1 | 2011-07-11 | Ryan | Fail | 3 | 2011-07-13 | Ryan | Fail | 5 | 2011-07-15 | Ryan |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 8 | 2011-07-20 | Cindy
| 17 | Product Categories - B2C Full View: C3 - C4 | Pass | 2 | 2011-07-12 | Ryan | Pass | 4 | 2011-07-14 | Ryan | Pass | 5 | 2011-07-15 | Ryan |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 8 | 2011-07-20 | Cindy
| 18 | Product Categories - B2C Full View: C3 - C4 My Price & Availability | Pass | 2 | 2011-07-12 | Ryan | Pass | 4 | 2011-07-14 | Ryan | Pass | 5 | 2011-07-15 | Ryan |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 8 | 2011-07-20 | Cindy
| 19 | Product Categories - B2C Full View: C3 - C4 Update My Price & Availability | Pass | 2 | 2011-07-12 | Ryan | Pass | 4 | 2011-07-14 | Ryan | Pass | 5 | 2011-07-15 | Ryan |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 8 | 2011-07-20 | Cindy
| 20 | Product Categories - B2C Full View: C3 - C4 User without 'View Price' permission | Pass | 2 | 2011-07-12 | Cindy | Pass | 4 | 2011-07-14 | Cindy | Pass | 5 | 2011-07-15 | Cindy |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 8 | 2011-07-20 | Cindy
| 21 | Product Categories - B2C Condensed View: C3 - C4 | Pass | 2 | 2011-07-12 | Ryan | Pass | 4 | 2011-07-14 | Ryan | Pass | 5 | 2011-07-15 | Ryan |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 8 | 2011-07-20 | Cindy
| 22 | Product Categories - B2C Mini View: C3 - C4 | Pass | 2 | 2011-07-12 | Ryan | Pass | 4 | 2011-07-14 | Ryan | Pass | 5 | 2011-07-15 | Ryan |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 8 | 2011-07-20 | Cindy
| 23 | Product Categories - B2B Grid View - Anonymous: C3 - C4 | Fail | 2 | 2011-07-12 | Cindy | Fail | 4 | 2011-07-14 | Cindy | Fail | 5 | 2011-07-15 | Cindy |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 8 | 2011-07-20 | Cindy
| 24 | Product Categories - B2C Full View - Anonymous: C3 - C4 | Pass | 2 | 2011-07-12 | Cindy | Pass | 4 | 2011-07-14 | Cindy | Pass | 5 | 2011-07-15 | Cindy |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 8 | 2011-07-20 | Cindy
| 25 | Product Categories - B2C Condensed View - Anonymous: C3 - C4 | Fail | 2 | 2011-07-12 | Cindy | Fail | 4 | 2011-07-14 | Cindy | Fail | 5 | 2011-07-15 | Cindy |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 8 | 2011-07-20 | Cindy
| 26 | Product Categories - B2C Mini View - Anonymous: C3 - C4 | Fail | 2 | 2011-07-12 | Cindy | Fail | 4 | 2011-07-14 | Cindy | Fail | 5 | 2011-07-15 | Cindy |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 8 | 2011-07-20 | Cindy
| Tab 5. | C4 Categories
| 27 | Product Categories - B2B Grid View: C4 | Fail | 1 | 2011-07-11 | Ryan | Fail | 3 | 2011-07-13 | Ryan | Fail | 5 | 2011-07-15 | Ryan |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 8 | 2011-07-20 | Cindy
| 28 | Product Categories - B2C Full View: C4 | Pass | 2 | 2011-07-12 | Ryan | Pass | 4 | 2011-07-14 | Ryan | Pass | 5 | 2011-07-15 | Ryan |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 8 | 2011-07-20 | Cindy
| 29 | Product Categories - B2C Full View: C3 - C4 My Price & Availability | Pass | 2 | 2011-07-12 | Ryan | Pass | 4 | 2011-07-14 | Ryan | Pass | 5 | 2011-07-15 | Ryan |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 8 | 2011-07-20 | Cindy
| 30 | Product Categories - B2C Full View: C3 - C4 Update My Price & Availability | Pass | 2 | 2011-07-12 | Ryan | Pass | 4 | 2011-07-14 | Ryan | Pass | 5 | 2011-07-15 | Ryan |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 8 | 2011-07-20 | Cindy
| 31 | Product Categories - B2C Full View: C3 - C4 User without 'View Price' permission | Pass | 2 | 2011-07-12 | Cindy | Pass | 4 | 2011-07-14 | Cindy | Pass | 5 | 2011-07-15 | Cindy |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 8 | 2011-07-20 | Cindy
| 32 | Product Categories - B2C Condensed View: C4 | Pass | 2 | 2011-07-12 | Ryan | Pass | 4 | 2011-07-14 | Ryan | Pass | 5 | 2011-07-15 | Ryan |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 8 | 2011-07-20 | Cindy
| 33 | Product Categories - B2C Mini View: C4 | Pass | 2 | 2011-07-12 | Ryan | Pass | 4 | 2011-07-14 | Ryan | Pass | 5 | 2011-07-15 | Ryan |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 8 | 2011-07-20 | Cindy
| 34 | Product Categories - B2B Grid View - Anonymous: C4 | Fail | 2 | 2011-07-12 | Cindy | Fail | 4 | 2011-07-14 | Cindy | Fail | 5 | 2011-07-15 | Cindy |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 8 | 2011-07-20 | Cindy
| 35 | Product Categories - B2C Full View - Anonymous: C4 | Pass | 2 | 2011-07-12 | Cindy | Pass | 4 | 2011-07-14 | Cindy | Pass | 5 | 2011-07-15 | Cindy |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 8 | 2011-07-20 | Cindy
| 36 | Product Categories - B2C Condensed View - Anonymous: C4 | Fail | 2 | 2011-07-12 | Cindy | Fail | 4 | 2011-07-14 | Cindy | Fail | 5 | 2011-07-15 | Cindy |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 8 | 2011-07-20 | Cindy
| 37 | Product Categories - B2C Mini View - Anonymous: C4 | Fail | 2 | 2011-07-12 | Cindy | Fail | 4 | 2011-07-14 | Cindy | Fail | 5 | 2011-07-15 | Cindy |  | 6 | 2011-07-18 | Ryan |  | 6 | 2011-07-18 | Cindy |  | 8 | 2011-07-20 | Cindy
| Tab 6. | Product Detail
| 38 | Product Detail Page | Fail | 1 | 2011-07-11 | Renee | Fail | 5 | 2011-07-15 | Renee | Fail | 3 | 2011-07-13 | Renee |  | 7 | 2011-07-19 | Ryan |  | 7 | 2011-07-19 | Cindy |  | 8 | 2011-07-20 | Cindy
| 39 | Product Detail Page - Update My Price & Availability | Pass | 1 | 2011-07-11 | Renee | Pass | 5 | 2011-07-15 | Renee | Pass | 3 | 2011-07-13 | Renee |  | 7 | 2011-07-19 | Ryan |  | 7 | 2011-07-19 | Cindy |  | 8 | 2011-07-20 | Cindy
| 40 | Product Detail Page - User without 'View Price' permission | Pass | 2 | 2011-07-12 | Renee | Pass | 5 | 2011-07-15 | Renee | Pass | 4 | 2011-07-14 | Renee |  | 7 | 2011-07-19 | Ryan |  | 7 | 2011-07-19 | Cindy |  | 8 | 2011-07-20 | Cindy
| 41 | Product Detail Page - Replacement Item Functionality | Fail | 1 | 2011-07-11 | Renee | Fail | 5 | 2011-07-15 | Renee | Fail | 3 | 2011-07-13 | Renee |  | 7 | 2011-07-19 | Ryan |  | 7 | 2011-07-19 | Cindy |  | 8 | 2011-07-20 | Cindy
| 42 | Product Detail Page - Up-Sell Item Functionality | Fail | 2 | 2011-07-12 | Renee | Fail | 5 | 2011-07-15 | Renee | Fail | 4 | 2011-07-14 | Renee |  | 7 | 2011-07-19 | Ryan |  | 7 | 2011-07-19 | Cindy |  | 8 | 2011-07-20 | Cindy
| 43 | Product Detail Page - Alternate Item Functionality | Fail | 2 | 2011-07-12 | Renee | Fail | 5 | 2011-07-15 | Renee | Fail | 4 | 2011-07-14 | Renee |  | 7 | 2011-07-19 | Ryan |  | 7 | 2011-07-19 | Cindy |  | 8 | 2011-07-20 | Cindy
| 44 | Product Detail Page - Cross-sell Item Functionality | Fail | 2 | 2011-07-12 | Renee | Fail | 5 | 2011-07-15 | Renee | Fail | 4 | 2011-07-14 | Renee |  | 7 | 2011-07-19 | Ryan |  | 7 | 2011-07-19 | Cindy |  | 8 | 2011-07-20 | Cindy
| 45 | Product Detail Page - Add to My Items | Pass | 1 | 2011-07-11 | Renee | Pass | 5 | 2011-07-15 | Renee | Pass | 3 | 2011-07-13 | Renee |  | 7 | 2011-07-19 | Ryan |  | 7 | 2011-07-19 | Cindy |  | 8 | 2011-07-20 | Cindy
| 46 | Product Detail Page - Anonymous | Fail | 1 | 2011-07-11 | Renee | Fail | 5 | 2011-07-15 | Renee | Fail | 3 | 2011-07-13 | Renee |  | 7 | 2011-07-19 | Ryan |  | 7 | 2011-07-19 | Cindy |  | 8 | 2011-07-20 | Cindy
| Tab 7. | Other
| 47 | Compare Items - Registered/Anonymous user | Fail | 2 | 2011-07-12 | Renee | Fail | 5 | 2011-07-15 | Renee | Fail | 3 | 2011-07-13 | Renee |  | 7 | 2011-07-19 | Ryan |  | 7 | 2011-07-19 | Cindy |  | 8 | 2011-07-20 | Cindy
| 48 | Search Catalog - Registered/Anonymous user | Fail | 2 | 2011-07-12 | Renee | Fail | 5 | 2011-07-15 | Renee | Fail | 3 | 2011-07-13 | Renee |  | 7 | 2011-07-19 | Ryan |  | 7 | 2011-07-19 | Cindy |  | 8 | 2011-07-20 | Cindy
s | 49 | Search within results - Registered/Anonymous user | Pass | 3 | 2011-07-13 | Renee | Pass | 5 | 2011-07-15 | Renee | Pass | 4 | 2011-07-14 | Renee |  | 7 | 2011-07-19 | Ryan |  | 7 | 2011-07-19 | Cindy |  | 8 | 2011-07-20 | Cindy
| 50 | Search within results: Non-stock/Stock item - Registered user | Pass | 3 | 2011-07-13 | Renee | Pass | 5 | 2011-07-15 | Renee | Pass | 4 | 2011-07-14 | Renee |  | 7 | 2011-07-19 | Ryan |  | 7 | 2011-07-19 | Cindy |  | 8 | 2011-07-20 | Cindy
| Tab 8. | Search Scenarios
| 51 | Search Combinations | Pass | 2, 3 | 2011-07-13 | Renee | Pass | 5 | 2011-07-15 | Renee | Pass | 3, 4 | 2011-07-14 | Renee |  | 7 | 2011-07-19 | Ryan |  | 7 | 2011-07-19 | Cindy |  | 8 | 2011-07-20 | Cindy
|  |  | Number |  | Percent |  | Number |  | Percent |  | Number |  | Percent |  | Number |  | Percent |  | Number |  | Percent |  | Number |  | Percent
|  | Total Test Cases | 51 |  |  |  | 51 |  |  |  | 51 |  |  |  | 51 |  |  |  | 51 |  |  |  | 51
|  | Passed | 27 |  | 52.94% |  | 27 |  | 52.94% |  | 27 |  | 52.94% |  | 0 |  | 0% |  | 0 |  | 0% |  | 0 |  | 0%
|  | Failed | 24 |  | 47.06% |  | 24 |  | 47.06% |  | 24 |  | 47.06% |  | 0 |  | 0% |  | 0 |  | 0% |  | 0 |  | 0%
|  | Remaining to Test | 0 |  | 0% |  | 0 |  | 0% |  | 0 |  | 0% |  | 51 |  | 100% |  | 51 |  | 100% |  | 51 |  | 100%

## Instructions
Coming Soon….
Naming Conventions
How to use Summary Tab
How to Use Test Case Tab
Test Case Tab - Using the Table
HEADER: Populate header information including Use Case, DDD, and Requirement info to provide traceability. Also be sure to identify any required PreConditions such as test cases which should already have been completed before starting the current test case. Notes may be used for any instructions which may be relevant to the tester.
STEP #:
USER INPUT:
EXPECTED RESULTS:
ACTUAL RESULTS / COMMENTS:
PASS / FAIL:
DATE EXECUTED:
JIRA #: Any significant failure should be documented in JIRA. "Significant" may be characterized as " ". Any departure from the expected result must be captured in the Actual Results / Comments field, but full details of "Significant" failures must be documented in JIRA for appropriate follow-up and assignment for resolution. Enter the numeric portion of the JIRA ticket in the JIRA # cell. This spreadsheet assumes all JIRA tickets will be associated with the XNGT (xpedx.com Next Gen Test Phase) project and assign that JIRA prefix. If the relevant JIRA ticket should be associated with another JIRA project, simply type in the entire JIRA ticket ID. (e.g. PCI Compliance might be PCI-123).
Other Considerations:
• Consider allocating dedicated space to identify predecessor Test Cases.
• Word wrap doesn't function in columns B-C because of merged cells. (Column D works fine.) We could resolve by moving TestCase#, UseCase #, etc to the far right where lower cells are unlikely to require word wrap.
• Consider a Status to identify follow-up needed. (Suspend?) Unexpected results may not indicate failure, but might justify conversation with the business, or disclose previously unforseen design considerations. Follow-up for any step might keep the overall test in a "Suspended" status. This would require complete documentation in JIRA.
Add ExecutedBY field
User Types (Roles)
External: Buyer (Can checkout, view invoices, view reports, view prices)
External: Customer Administrator (Has all Buyer privileges AND can maintain subordinate users)
User Profile Flags: Can checkout; Can view invoices online; Can view reports; Can view prices. (All are checked by default)

## 1. C1-C2
Test Case # | 1 | Test Case Name: | Catalog Landing Page: C1 - C2 |  | Tester Name:
Use Case # |  | Preconditions: | Customer Admin/Customer Buyer is logged in and has navigated to the Home page.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Mouse over on the Catalog link on the site navigation bar |  | • Drop down catalog categories of 4 or less appear for selection • Categories are displayed in alphabetical order
2 | Click on the Catalog link on the site navigation bar |  | The Catalog home page is displayed
3 | Validate the Catalog home page - Left column section |  | • Breadcrumb: My Selection: Catalog • 'Search within Results' within Results search functionality is available on the left top section • 'Search normally stocked items only' check box is available to search stocked items below 'Search within Results' function. By default, the checkbox will be unchecked. • 'Product Categories' section is available underneath the above checkbox with C1 categories (of 4 or less). Categories are displayed in alphabetical order and total number of items for each category. This section can expand/collapse using the '+/-' link or clicking on anywhere on the header name. By default, the section will be in expand mode.
4 | Validate the Catalog home page - Middle column section |  | • Section for each of the C1 categories highlights the 10 5 (or less) C2 categories (based on the load from content directory - it could be be the first 10 5 in alphabetical) • C2 category image and description (with a link) is displayed for all 4 or less C1 categories • 'View All Facility Supplies', 'View All Graphics', 'View All Packaging', and 'View All Paper' links are displayed in each category section to expand and display the selected C1 category list on a separate page.
5 | Validate the Catalog home page - Right column section |  | Advertisement' section is displayed below the promotion section with image, link, and descriptions.
6 | Click on the 'Advertisement' section |  | A separate browser will be displayed for advertisement to adjuggler url.
7 | Click on any one of the ontology names, for example 'Other Products', in the 'Product Type' Narrow By section to ensure the page retrieves the items by the selected option. Validate to ensure the items are correct and the columns of information are displayed by the appropriate template. |  | The item results displays the items in grid view using 'default' template ( for columns of information) for 'Other Products' ontology.
Test Case # | 2 | Test Case Name: | Catalog Landing Page - Anonymous: C1 - C2
Use Case # |  | Preconditions: | Annonymous user has navigated to the xpedx loging page.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | From the login page, once the customer has browsed through one of the category (i.e Paper), the customer will be able to access the Catalog Landing page from the breadcrumb/my selection (i.e Catalog / Bond & Writing x / Premium cotton. Validate the Catalog Landing page. |  | The Expected Result should be the same as Test Script # 1, steps 3 - 6, except with the following exceptions: • 'Search normally stocked items only' function is not available • Note, header page will be validated as part of the "Miscellaneous" packet
Note on B2: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E7: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F7: Select from List. - Blank - Pass - Fail - Not Started
Note on G7: Enter Month / Day. Year defaults to current year unless entered.
Note on H7: Enter numeric portion of JIRA ticket.
Note on B17: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E22: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F22: Select from List. - Blank - Pass - Fail - Not Started
Note on G22: Enter Month / Day. Year defaults to current year unless entered.
Note on H22: Enter numeric portion of JIRA ticket.

## 2. C1-C2 Expanded
Test Case # | 3 | Test Case Name: | Product Categories: C1 - C2 (Expanded)
Use Case # |  | Preconditions: | Customer Admin/Buyer is logged in and has navigated to the Catalog Landing page.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Click on the 'View All Facility Supplies Products' link from the Catalog Landing page |  | The Facility Supplies section is expanded to display all C2 categories in the next page.
1a | Alternate Flow: Click on the 'Catalog' from the site navigation bar and then click on the 'Facilities Supplies' (C1) category from the 'Product Categories' section. |  | Expected results same as step1 above.
1b | Alternate Flow: Click on the 'Catalog' from the site navigation bar. Then click on the 'Facilities Supplies' from the drop down. |  | Expected results same as step1 above.
2 | Validate the Facilities Supplies home page - Left column section |  | • Breadcrumb: My Selection: Catalog / Faciliites Supplies • 'Search within Results' within Results search functionality is available on the left top section • 'Search normally stocked items only' check box is available to search stocked items below 'Search within Results' function. By default, the checkbox will be unchecked. • 'Product Categories' section is available underneath the above checkbox with C2 categories. By default there will be 8 or less C2 categories displayed. Additional categories will be available to view via the scroll bar. Categories are displayed in alphabetical order and total number of items for each category. This section can expand/collapse using the '+/-' link or clicking on anywhere on the header name. By default, the section will be in expand mode. • The 'Product Type', 'Brand' and 'Mfg' sections to further narrow the search are displayed underneath the Product categories section with scrollable list. Attribute values in each narrow by section is displayed in alphabetical order. Up to 8 attribute values will be displayed by default in this section and this section can expand/collpased using the '+/-' link or clicking on anywhere on the header name. By default, the section will be in collapse mode.
3 | Validate the Catalog home page - Middle column section |  | • The Facility Supplies section is expanded to display all C2 categories and none of the other C1 categories are displayed • C2 category image and description (with a link) is displayed for all C2 categories
4 | Validate the Catalog home page - Right column section |  | 'Advertisement' section is displayed below the promotion section with image, link, and descriptions.
5 | Validate all the rest of the C1 categories 'View All…' links as described in step 1. |  | Respectively expected results is same as steps 1 - 4.
6 | Click on the 'Advertisement' section |  | A separate browser will be displayed for advertisement to adjuggler url.
7 | Click on any one of the ontology names, for example 'Chemicals', in the 'Product Type' Narrow By section to ensure the page retrieves the items by the selected option. Validate to ensure the items are correct and the columns of information are displayed by the appropriate template. |  | The item results displays the items in grid view using 'default' template ( for columns of information) for 'Other Products' ontology.
Test Case # | 4 | Test Case Name: | Product Categories - Anonymous: C1 - C2 (Expanded)
Use Case # |  | Preconditions: | Annonymous user has navigated to the xpedx loging page.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Click on 'Facilities Supplies' category button, for example and Validate the Facilities Supplies home page. |  | Expected Result is the same as described in Test Script 3.00 steps 2 - 7, except with the following exceptions: • 'Search normally stocked items only' check box is not available • Note, header page will be validated as part of the "Miscellaneous" packet
Note on B2: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E7: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F7: Select from List. - Blank - Pass - Fail - Not Started
Note on G7: Enter Month / Day. Year defaults to current year unless entered.
Note on H7: Enter numeric portion of JIRA ticket.
Note on B20: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E25: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F25: Select from List. - Blank - Pass - Fail - Not Started
Note on G25: Enter Month / Day. Year defaults to current year unless entered.
Note on H25: Enter numeric portion of JIRA ticket.

## 3. C2-C3
Test Case # | 5 | Test Case Name: | Product Categories - B2B Grid View: C2 - C3
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Click on the 'Catalog' from the site navigation bar and then click on the 'Paper' (C1) category from the 'Product Categories' section. |  | Expected Results same as in the step 1, Test Case # 3.00, except it is for Paper category.
2 | Click on the 'Bond & Writing' (C2) category from the drop-down list under 'Paper' category. And validate the catalog page view. |  | • Breadcrumb: My Selection: Catalog / Paper x / Bond & Writing • 'Search within Results' within Results search functionality is available on the left top section • 'Search normally stocked items only' check box is available to search stocked items below 'Search within Results' function. By default, the checkbox will be unchecked. • 'Product Categories' section reveals the next (C3) level of categories. By default there will be 8 or less C3 categories displayed. Additional categories will be available to view via the scroll bar. Categories are displayed in alphabetical order and total number of items for each category. This section can expand/collapse using the '+/-' link or clicking on anywhere on the header name. By default, the section will be in expand mode. • 'Narrow By' section default to a different narrow by attribute(s) (i.e. Brand, Mfg, Enviornment, Size, Basis Weight, Mwt, Color, and Caliper) which is applicable for 'C2 category. Attribute values in each narrow by section is displayed in alphabetical order. Up to 8 attributes will be displayed by default in this section and this section can expand/collpased using the '+/-' link or clicking on anywhere on the header name. By default, the section will be in collapse mode. • 'Drag to Compare' function is displayed in the left-hand corner above the page formatting section
2b |  |  | • 'Catalog view' functions (to switch to B2B or B2C view) is displayed in the right-hand corner above the page formatting section. 'Full View, 'Condensed View', 'Mini View', followed by 'Grid view' icons are displayed. • 'Sort by:' function is displayed to the left of the Show # of items function on the top and bottom of the page • 'Show:' # of items per page function is displayed above and below the Item results section. Items are listed in Grid view (or different view depending on the setup in the user profile) with 20 25 items per page by default • Number of total items results for the selected category is displayed to the right of the Sort by on the top and bottom of the page • Pagination function is displayed to the right of the item number results on the top and bottom of the page • 'Drag to Compare Items' function is displayed in the left-hand corner above the page formatting section • Promotions and Advertisement section is displayed on the top of the Item results section or above the show and sort by bar.
3 | Select the fourth view for 'Paper Grid View' out of the four list views on the top-right side of the page |  | The item view page changes to display items in table/grid format
4 | Validate the B2B Grid view |  | • 'Description' column displays Short Description (up to 200 characters) and Enviornment friendly icon is with short description as hyperlink. When cursor is hover over the description, the description should not be underlined. • 'M' for stocked status column is displayed with blank (for Stocked) or 'M' (for Non Stocked) item availability status • 'xpedx Item #:' (upto 7 characters) is displayed after the description. • 'Size' (up to 115 characters), and 'Color' (up to 110 characters) columns are displayed after the 'M' column. Note, columns after 'M' can vary by the ontology setup. Below are some of the other columns which can be displayed after the 'M' column: • For Bags, 'Capacity' (up to 143 characters) • For Equipment, 'Model (up to 75 characters) • For Facsupply, 'Material' (up to 75 characters) and 'Form' (up to 130 characters) • For Packaging, 'Gauge' • For Paper, 'Mwt'(up to 7 characters), 'Basis Wt' (up to 5 characters), and 'List Price' with UOM information is displayed with upto 3 different list price.
5 | Click on the 'Description' link for any item. Also, Item # should be a link which is in development currently. |  | The item detail page is displayed with the following Breadcrumb. Breadcrumb: Back / (Item number)
6 | Click on the 'Back' link from the breadcrumb above |  | The default catalog page view is returned for Bond & Writing
7 | Click on 'Show:' 25 per page drop down |  | The drop down with 20, 40, 60, for example, per page is displayed. Note, this list can be different if it is changed. By default, 20 items per page will be displayed.
8 | Click on 'Sort By:' to sort |  | Drop down list appears with ability to sort by Item #, Description, Relevancy and Environment Certification options in ascending and descending order. By default, the items will be sorted by relevancy.
9 | Validate all the 'Sort By:' options sort in ascending order and descending order |  | The data is sorted by the selected 'Sort By:' option
10 | Validate the 'Pagination' by selecting different page options to ensure those pages retreive successfully. For example, select page 4. |  | The selected page number is displayed with the next set of data. As default, the pagination is displayed as "Previous 1 2 3 4 Next".
11 | Click on the 'Promotions' to ensure Promotion pages can be retreived successfully and then return to the current page |  | The selected promotion detail page is retreived. Please see the test scripts for Promotions for further information.
12 | Click on the 'Advertisement' to ensure appropriate Advertisement pages can be retreived successfully and then return to the current page |  | The selected advertisement page is retreived. Please see the test scripts for Advertisement for further information.
13 | Click on any one of the values (i.e white under 'Brand' narrow by) in the 'Narrow By' section to ensure the page retrieves the items by the selected option. Validate to ensure the items are correct and the columns of information are displayed by the appropriate template. |  | The item results displays the items for the selected value in grid view and columns of information with the applicable template.
14 | Click and drag item to the 'Drag to Compare Items' function on the top of the page. Continue to add more items to compare and validate the # of items results next to the 'Drage to compare' label. (Please see the additional test scritps for Drag to Compare functionality.) |  | The item is copied over to the Compare page and displays '1 Items'. If more items are added, the number will change for the # of items added to compare. Can click on entire item row in the grid view to drag the item to the 'Drag to compare' section.
Test Case # | 6 | Test Case Name: | Product Categories - B2C Full View: C2 - C3
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page. • Customer is setup with B2B view in the Customer Profile
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Continue from Test Case # 5.00 above. Select the first view for 'Full View' out of the four list views on the top-right side of the page |  | The item view page changes to display one item per row
2 | Validate the B2C Full view |  | • Image is displayed in the far left side. If there is no image, 'image not on file' image will be displayed • Short Description is displayed first to the right of the image in blue as hyperlink to product detail page. Full description (up to 200 characters) is displayed. • Long Description of item attributes is displayed in bullets in blue as hyperlink to product detail page. Up to 5 bullets of information can be displayed. When placing a cursor over any bullet with large long description, a tool-tip is displayed. • 'xpedx/brand Item #:' and 'Mfg. Item #:' and/or 'Mpc Item #:' is displayed below the long description. Up to two item #s can be displayed. • Enviornment indicator (leaf icon) is displayed next to the xpedx/brand item #. • Stocked status of 'Mill / Mfg. Item - Additional charges may apply.' is displayed in red for non-stocked item, if applicable. (This information is pinned to the page regardless of how many item #s are displayed above.) • 'Qty' text box and UOM drop-down with default UOM is displayed. • 'My Price & Availability' link and 'Add to Cart' button is displayed under the Qty and UOM drop-down.
3 | Follow the steps in the above test script # 5.00, steps 6 - 14 |  | Expected results same as defined in test script # 5.00, steps 6 - 14.
4 | Click on the 'Add to Cart' button |  | A warning message in red is displayed below the Add to Cart button a the line level, for example: "Qty is required field."
5 | Enter a non-numeric value in the Qty text field. Then click on the 'Add to Cart' button |  | A warning message in red is displayed below the 'Add to Cart' button at the line level, for example: "Please enter a numeric value."
6 | Enter a zero value in the Qty text field. Then click on the 'Add to Cart' button |  | A warning message in red is displayed below the 'Add to Cart' button at the line level, for example: "Quantity must be greater than 0."
7 | Enter a valid numeric value in the Qty text field. Then click on the 'Add to Cart' button |  | The item is added to cart and can be validated on the header page (under cart & mini-cart drop-down). A confirmation message in blue is displayed below the Add to Cart button a the line level, for example: "Item has been successfully added to cart." The Qty for the given item is refreshed to blank. The P & A section remains expanded if it was already expanded before clicking on the 'Add to Cart'.
Test Case # | 7 | Test Case Name: | Product Categories - B2C Full View: My Price & Availability
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page. • Customer is setup with B2B view in the Customer Profile
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Continue from Test Case # 6.00 above. Select the first view for 'Full View' out of the four list views on the top-right side of the page |  | The item view page changes to display one item per row
2 | Click on the My Price & Availability |  | Availability, My Bracket Pricing (USD), and Price (USD) information is expanded below the 'My Price & Availability' link.
3 | Validate the Availability information |  | • Availability information is displayed in the following format: (Note, availability UOM is displayed per the requested UOM): --- Availability ---------------------------------- Total Available: 225,000,000 Lids Next Day: 5,000 2+ Days: 20,000 2,500 available today at Cincinnati, OH -'Immediate' should list the number of items that requires 0 lead days. It also should list the Division name. -'Next Day' should list the number of items that requires 0 or 1 lead days. -'2+Days' should list the number of items that requires 2+Days . -'Total Quantity Available' available should be displayed with total number from Next Day and 2+Days
4 | Validate the Bracket Pricing information, if applicable |  | Bracket Pricing information and header is displayed in the following format, if applicable. If Bracket Pricing information is not applicable, both the header and detail is not displayed. (Note, my bracket pricing UOM is displayed per the requested UOM.) ---- My Bracket Pricing (USD) ------------ 1 Lid - $35.38 / Lid 10 Lid - $325.38 / Lid 20 Lid - $3,325.38 / Lid 30 Lid - $335,555.38 / Lid
5 | Validate the My Price information |  | Price information is displayed in the following format, next to the Bracket Pricing section. (Note, the first and second price is unit price and third is requested price. The second price will display only for Paper items. Also, the my price are displayed in 5 decimals and extended price is displayed in 2 decimals.) ---Price (USD)--------------- My Price: $999,999,999.00000 / Carton $999,999,999.00000 / Lid $999,999,999.00000 / Lid Extended Price: $999,999,999.00
Test Case # | 8 | Test Case Name: | Product Categories - B2C Full View: Update My Price & Availability
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page. • Customer is setup with B2B view in the Customer Profile
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Continue from Test Case # 7.00 above. Enter a non-numeric value in the Qty text field. Then click on the 'My Price & Availability' link |  | A warning message is displayed in red at the line level, for example: "Please enter a numeric value."
2 | Enter a zero value in the Qty text field. Then click on the 'Add to Cart' button |  | A warning message in red is displayed below the 'Add to Cart' button at the line level, for example: "Quantity must be greater than 0."
3 | Enter a valid numeric value in the Qty text field and change the UOM from the drop-down. And click on the My Price & Availability |  | Availability, My Bracket Pricing (USD), and Price (USD) information is updated based on the Qty and UOM entered.
4 | Validate the Availability information |  | • Availability information is displayed in the following format: (Note, availability UOM is displayed per the requested UOM): --- Availability ---------------------------------- Total Available: 225,000,000 Lids Next Day: 5,000 2+ Days: 20,000 2,500 available today at Cincinnati, OH
5 | Validate the Bracket Pricing information, if applicable |  | Bracket Pricing information and header is displayed in the following format, if applicable. If Bracket Pricing information is not applicable, both the header and detail is not displayed. (Note, my bracket pricing UOM is displayed per the requested UOM.) ---- My Bracket Pricing (USD) ------------ 1 Lid - $35.38 / Lid 10 Lid - $325.38 / Lid 20 Lid - $3,325.38 / Lid 30 Lid - $335,555.38 / Lid
6 | Validate the My Price information |  | Price information is displayed in the following format, next to the Bracket Pricing section. (Note, the first and second price is unit price and third is requested price. The second price will display only for Paper items. Also, the my price are displayed in 5 decimals and extended price is displayed in 2 decimals.) ---Price (USD)--------------- My Price: $999,999,999.00000 / Carton $999,999,999.00000 / Lid $999,999,999.00000 / Lid Extended Price: $999,999,999.00
7 | Click on the 'Add to Cart' button |  | The item is added to cart and can be validated on the header page (under cart & mini-cart drop-down). A confirmation message in blue is displayed below the Add to Cart button a the line level, for example: "Item has been successfully added to cart." The Qty for the given item is refreshed to blank. The P & A section remains expanded if it was already expanded before clicking on the 'Add to Cart'.
Test Case # | 9 | Test Case Name: | Product Categories - B2C Full View: User without 'View Price' permission
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page. • Customer is setup with B2B view in the Customer Profile
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Continue with step 3 from the Case # 8.00 above.
2 | Validate the Availability information |  | • Availability information is displayed in the following format: (Note, availability UOM is displayed per the requested UOM): --- Availability ---------------------------------- Total Available: 225,000,000 Lids Next Day: 5,000 2+ Days: 20,000 2,500 available today at Cincinnati, OH
3 | Validate the Bracket Pricing information, if applicable |  | Bracket Pricing information (including the header) is not displayed to the user.
4 | Validate the My Price information |  | Price information (including the header) is not displayed to the user. The 'Price (USD)' header should display, but not the "My Price" and "Extended Price" headers.
Test Case # | 10 | Test Case Name: | Product Categories - B2C Condensed View: C2 - C3
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page. • Customer is setup with B2B view in the Customer Profile
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Continue from Test Script # 8.00 above. Select the second page view for 'Condensed View' out of the four list views on the top-right side of the page |  | The item view page changes to display two items per row
2 | Validate the B2C Condensed view |  | • Image is displayed in the far left side. If there is no image, 'no image found' image will be displayed • Short Description (up to 200 characters, but only two lines of description) is displayed first to the right of the image. When placing a cursor over the short description, full short description is displayed in the tool-tip. • Long Description of item attributes is displayed in bullets underneath the short description. Up to 5 bullets of information can be displayed. When placing a cursor over any bullet with large long description, a tool-tip is displayed. • 'xpedx/brand Item #:' and 'Mfg. Item #:' and/or 'Mpc Item #:' is displayed below the image. Up to two item #s can be displayed. • Enviornment indicator (leaf icon) is displayed next to the xpedx/brand item #. • Stocked status of 'Mill / Mfg. Item' is displayed (in black) for non-stocked item, if applicable. (This information is pinned to the page regardless of how many item #s are displayed above.) • 'Qty' text box and UOM drop-down with default UOM is displayed. • 'Add to Cart' button is displayed under the UOM drop-down.
3 | Follow the steps in the above Test Script # 5.00, steps 6 - 16. (Note, Price & Availability functionality does not apply for the condensed view.) |  | Expected results same as defined in Test Script # 5.00, steps 6 - 16.
4 | Click on the 'Add to Cart' button |  | A warning message in red is displayed below the Add to Cart button a the line level, for example: "Qty is required field."
5 | Enter a non-numeric value in the Qty text field. Then click on the 'Add to Cart' button |  | A warning message in red is displayed below the 'Add to Cart' button at the line level, for example: "Please enter a numeric value."
6 | Enter a zero value in the Qty text field. Then click on the 'Add to Cart' button |  | A warning message in red is displayed below the 'Add to Cart' button at the line level, for example: "Quantity must be greater than 0."
7 | Enter a valid numeric value in the Qty text field. Then click on the 'Add to Cart' button |  | The item is added to cart and can be validated on the header page (under cart & mini-cart drop-down). A confirmation message in blue is displayed below the Add to Cart button a the line level, for example: "Item has been successfully added to cart." The Qty for the given item is refreshed to blank. The P & A section remains expanded if it was already expanded before clicking on the 'Add to Cart'.
Test Case # | 11 | Test Case Name: | Product Categories - B2C Mini View: C2 - C3
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page. • Customer is setup with B2B view in the Customer Profile
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Continue from Test Case # 10.00 above. Select the third page view for 'Mini View' out of the four list views on the top-right side of the page |  | The item view page changes to display four items per row
2 | Validate the B2C Mini view |  | • Image is displayed first and centered aligned in the Item results section. If there is no image, 'no image found' image will be displayed • Short Description (up to 200 characters, but only two lines of description) is displayed underneath the image. When placing a cursor over the short description, full short description is displayed in the tool-tip. • 'xpedx/brand Item #:' and 'Mfg. Item #:' and/or 'Mpc Item #:' is centered aligned and displayed below the short description. Up to two item #s can be displayed. • Enviornment indicator (leaf icon) is displayed next to the xpedx/brand item #. • Stocked status of 'Mill / Mfg. Item' is displayed centered aligned (in black) for non-stocked item, if applicable. (This information is pinned to the page regardless of how many item #s are displayed above.) • 'Qty' text box and UOM drop-down with default UOM (from the pricebook load) is centered aligned and displayed underneath the stocked status. • 'Add to Cart' button is centered aligned and displayed under the UOM drop-down
3 | Follow the steps in the above test script # 5.00, steps 6 - 16 (Note, Price & Availability functionality does not apply for the mini view.) |  | Expected results same as defined in Test Script # 5.00, steps 6 - 16.
4 | Click on the 'Add to Cart' button |  | A warning message in red is displayed below the Add to Cart button a the line level, for example: "Qty is required field."
5 | Enter a non-numeric value in the Qty text field. Then click on the 'Add to Cart' button |  | A warning message in red is displayed below the 'Add to Cart' button at the line level, for example: "Please enter a numeric value."
6 | Enter a zero value in the Qty text field. Then click on the 'Add to Cart' button |  | A warning message in red is displayed below the 'Add to Cart' button at the line level, for example: "Quantity must be greater than 0."
7 | Enter a valid numeric value in the Qty text field. Then click on the 'Add to Cart' button |  | The item is added to cart and can be validated on the header page (under cart & mini-cart drop-down). A confirmation message in blue is displayed below the Add to Cart button a the line level, for example: "Item has been successfully added to cart." The Qty for the given item is refreshed to blank. The P & A section remains expanded if it was already expanded before clicking on the 'Add to Cart'.
Test Case # | 12 | Test Case Name: | Product Categories - B2B Grid View - Anonymous: C2 - C3
Use Case # |  | Preconditions: | Annonymous user has navigated to the xpedx loging page.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Click on the 'Paper' (C1) category from the login page. |  | Expected Results same as in the step # 1, Test Case # 4.00, except it is for Paper category.
2 | Click on the 'Bond & Writing' (C2) category from the drop-down list under 'Paper' category. And validate the B2B grid view. |  | The Expected Result should be the same as Test Case # 5.00, except with the following exceptions: • 'Show normally stocked items only' check box is not available • Stocked status column of 'M' is not displayed • List Price column is not displayed • Note, header page will be validated as part of the "Miscellaneous" packet
Test Case # | 13 | Test Case Name: | Product Categories - B2C Full View - Anonymous: C2 - C3
Use Case # |  | Preconditions: | Annonymous user has navigated to the xpedx loging page.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Continue from Test Case # 12.00 above. Select the first view for 'Full View' out of the four list views on the top-right side of the page. And validate the B2C Full view. |  | The Expected Result should be the same as Test Case # 6.00, except with the following exceptions: • 'Show normally stocked items only' check box is not available • Stocked status of 'Mill / Mfg. Item - Additional charges may apply.' is not displayed • Qty, UOM drop-down, My Price & Availability, and Add to cart options are not displayed • Note, header page will be validated as part of the "Miscellaneous" packet
Test Case # | 14 | Test Case Name: | Product Categories - B2C Condensed View - Anonymous: C2 - C3
Use Case # |  | Preconditions: | Annonymous user has navigated to the xpedx loging page.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Continue from Test Script # 13.00 above. Select the second page view for 'Condensed View' out of the four list views on the top-right side of the page. And validate the B2C Condensed view. |  | The Expected Result should be the same as Test Case # 10.00, except with the following exceptions: • 'Show normally stocked items only' check box is not available • Stocked status of 'Mill / Mfg. Item' is not displayed • Qty, UOM drop-down, and Add to cart options are not displayed • Note, header page will be validated as part of the "Miscellaneous" packet Should the Mfg. Item # always display for Anonymous? Confirmed the “Mfg. item “ will not display for anonymous user as it currently does not show in staging. And per our conversation with Steve, that if it displays then we should keep it but if it doesn’t then we are okay as well.
Test Case # | 15 | Test Case Name: | Product Categories - B2C Mini View - Anonymous: C2 - C3
Use Case # |  | Preconditions: | Annonymous user has navigated to the xpedx loging page.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Continue from Test Case # 14.00 above. Select the third page view for 'Mini View' out of the four list views on the top-right side of the page. And validate the B2C Mini view. |  | The Expected Result should be the same as Test Case # 11.00, except with the following exceptions: • 'Show normally stocked items only' check box is not available • Stocked status of 'Mill / Mfg. Item' is not displayed • Qty, UOM drop-down, and Add to cart options are not displayed • Note, header page will be validated as part of the "Miscellaneous" packet
Note on B2: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E7: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F7: Select from List. - Blank - Pass - Fail - Not Started
Note on G7: Enter Month / Day. Year defaults to current year unless entered.
Note on H7: Enter numeric portion of JIRA ticket.
Note on B25: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E30: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F30: Select from List. - Blank - Pass - Fail - Not Started
Note on G30: Enter Month / Day. Year defaults to current year unless entered.
Note on H30: Enter numeric portion of JIRA ticket.
Note on B40: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E45: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F45: Select from List. - Blank - Pass - Fail - Not Started
Note on G45: Enter Month / Day. Year defaults to current year unless entered.
Note on H45: Enter numeric portion of JIRA ticket.
Note on B53: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E58: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F58: Select from List. - Blank - Pass - Fail - Not Started
Note on G58: Enter Month / Day. Year defaults to current year unless entered.
Note on H58: Enter numeric portion of JIRA ticket.
Note on B68: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E73: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F73: Select from List. - Blank - Pass - Fail - Not Started
Note on G73: Enter Month / Day. Year defaults to current year unless entered.
Note on H73: Enter numeric portion of JIRA ticket.
Note on B80: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E85: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F85: Select from List. - Blank - Pass - Fail - Not Started
Note on G85: Enter Month / Day. Year defaults to current year unless entered.
Note on H85: Enter numeric portion of JIRA ticket.
Note on B95: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E100: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F100: Select from List. - Blank - Pass - Fail - Not Started
Note on G100: Enter Month / Day. Year defaults to current year unless entered.
Note on H100: Enter numeric portion of JIRA ticket.
Note on B110: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E115: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F115: Select from List. - Blank - Pass - Fail - Not Started
Note on G115: Enter Month / Day. Year defaults to current year unless entered.
Note on H115: Enter numeric portion of JIRA ticket.
Note on B120: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E125: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F125: Select from List. - Blank - Pass - Fail - Not Started
Note on G125: Enter Month / Day. Year defaults to current year unless entered.
Note on H125: Enter numeric portion of JIRA ticket.
Note on B129: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E134: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F134: Select from List. - Blank - Pass - Fail - Not Started
Note on G134: Enter Month / Day. Year defaults to current year unless entered.
Note on H134: Enter numeric portion of JIRA ticket.
Note on B138: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E143: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F143: Select from List. - Blank - Pass - Fail - Not Started
Note on G143: Enter Month / Day. Year defaults to current year unless entered.
Note on H143: Enter numeric portion of JIRA ticket.

## 4. C3-C4
Test Case # | 16 | Test Case Name: | Product Categories - B2B Grid View: C3 - C4
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page. • Customer is setup with B2B view in the Customer Profile
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Click on the 'Catalog' from the site navigation bar and then click on the 'Paper' (C1) category from the 'Browse Categories' section. |  | Expected Results same as in the step # 1, Test Case # 3.00, except it is for Paper category.
2 | Click on the 'Bond & Writing' (C2) category from the drop-down list under 'Paper' category. |  | Expected Results same as in the step # 2, Test Case # 5.00
3 | Click on the 'Premium Cotton' (C3) category from the drop-down list under 'Bond & Writing' category. And validate the catalog page view. |  | • Breadcrumb: My Selection: Catalog / Paper x / Bond & Writing x / Premium Cotton • By setup on the customer profile, the B2B view catalog page is displayed. All the functionalities remain the same as defined in the Test Script # 7.00, except for the following is updated: • 'Prodcut Categories' section reveals the next (C4) level of categories. • 'Narrow By' section default to a different narrow by attribute(s) (i.e. Brand, Mfg, Size, Basis Weight, Mwt, Color, and Caliper) which is applicable for 'C3' category. • Number of total items results is updated for the 'Premium Cotton' category or the selected category.
4 | Select the fourth view for 'Grid View' out of the four list views on the top-right side of the page, if the Grid view is not selected. |  | The item view page changes to display items in table/grid format
5 | Validate the B2B Grid view |  | Expected Results same as in the step # 5, Test Case # 5.00 (except items will be related to 'Premium Cotton' (C3) category)
6 | Follow the rest of the steps, starting with step # 6 in Test Case # 5.00 |  | Expected Results same as in the Test Case # 5.00
Test Case # | 17 | Test Case Name: | Product Categories - B2C Full View: C3 - C4
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page. • Customer is setup with B2B view in the Customer Profile
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Follow the steps in Test Case # 6.00 and Validate the B2C Full view. |  | Expected Results same as Test Case # 6.00, except items will be related to 'Premium Cotton' (C3) category
Test Case # | 18 | Test Case Name: | Product Categories - B2C Full View: C3 - C4 My Price & Availability
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page. • Customer is setup with B2B view in the Customer Profile
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Follow the steps in Test Case # 7.00 and Validate the B2C Full view. |  | Expected Results same as Test Case # 7.00, except items will be related to 'Premium Cotton' (C3) category
Test Case # | 19 | Test Case Name: | Product Categories - B2C Full View: C3 - C4 Update My Price & Availability
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page. • Customer is setup with B2B view in the Customer Profile
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Follow the steps in Test Case # 8.00 and Validate the B2C Full view. |  | Expected Results same as Test Case # 8.00, except items will be related to 'Premium Cotton' (C3) category
Test Case # | 20 | Test Case Name: | Product Categories - B2C Full View: C3 - C4 User without 'View Price' permission
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page. • Customer is setup with B2B view in the Customer Profile
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Follow the steps in Test Case # 9.00 and Validate the B2C Full view. |  | Expected Results same as Test Case # 9.00, except items will be related to 'Premium Cotton' (C3) category
Test Case # | 21 | Test Case Name: | Product Categories - B2C Condensed View: C3 - C4
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page. • Customer is setup with B2B view in the Customer Profile
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Follow the steps in Test Case # 10.00 and Validate the B2C Full view. |  | Expected Results same as Test Case # 10.00, except items will be related to 'Premium Cotton' (C3) category
Test Case # | 22 | Test Case Name: | Product Categories - B2C Mini View: C3 - C4
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page. • Customer is setup with B2B view in the Customer Profile
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Follow the steps in Test Case # 11.00 and Validate the B2C Full view. |  | Expected Results same as Test Case # 11.00, except items will be related to 'Premium Cotton' (C3) category
Test Case # | 23 | Test Case Name: | Product Categories - B2B Grid View - Anonymous: C3 - C4
Use Case # |  | Preconditions: | Annonymous user has navigated to the xpedx loging page.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Click on the 'Paper' (C1) category from the login page. |  | Expected Results same as in the step # 1, Test Case # 4.00, except it is for Paper category.
2 | Click on the 'Bond & Writing' (C2) category from the drop-down list under 'Paper' category. And validate the B2B grid view. |  | The Expected Result should be the same as Test Case # 12.00
3 | Click on the 'Premium Cotton' (C3) category from the drop-down list under 'Bond & Writing' category. Select the fourth view for 'Grid View' out of the four list views on the top-right side of the page, if the Grid view is not selected. And validate the B2B grid view. |  | Expected Results same as Test Case # 12.00, except items will be related to 'Premium Cotton' (C3) category
Test Case # | 24 | Test Case Name: | Product Categories - B2C Full View - Anonymous: C3 - C4
Use Case # |  | Preconditions: | Annonymous user has navigated to the xpedx loging page.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Continue from Test Case # 23.00 above. Select the first view for 'Full View' out of the four list views on the top-right side of the page. And validate the B2C Full view. |  | Expected Results same as Test Case # 13.00, except items will be related to 'Premium Cotton' (C3) category
Test Case # | 25 | Test Case Name: | Product Categories - B2C Condensed View - Anonymous: C3 - C4
Use Case # |  | Preconditions: | Annonymous user has navigated to the xpedx loging page.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Continue from Test Case # 24.00 above. Select the second view for 'Condensed View' out of the four list views on the top-right side of the page. And validate the B2C Condensed view. |  | Expected Results same as Test Case # 14.00, except items will be related to 'Premium Cotton' (C3) category
Test Case # | 26 | Test Case Name: | Product Categories - B2C Mini View - Anonymous: C3 - C4
Use Case # |  | Preconditions: | Annonymous user has navigated to the xpedx loging page.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Continue from Test Case # 25.00 above. Select the third view for 'Mini View' out of the four list views on the top-right side of the page. And validate the B2C Mini view. |  | Expected Results same as Test Case # 15.00, except items will be related to 'Premium Cotton' (C3) category
Note on B2: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E7: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F7: Select from List. - Blank - Pass - Fail - Not Started
Note on G7: Enter Month / Day. Year defaults to current year unless entered.
Note on H7: Enter numeric portion of JIRA ticket.
Note on B16: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E21: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F21: Select from List. - Blank - Pass - Fail - Not Started
Note on G21: Enter Month / Day. Year defaults to current year unless entered.
Note on H21: Enter numeric portion of JIRA ticket.
Note on B25: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E30: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F30: Select from List. - Blank - Pass - Fail - Not Started
Note on G30: Enter Month / Day. Year defaults to current year unless entered.
Note on H30: Enter numeric portion of JIRA ticket.
Note on B34: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E39: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F39: Select from List. - Blank - Pass - Fail - Not Started
Note on G39: Enter Month / Day. Year defaults to current year unless entered.
Note on H39: Enter numeric portion of JIRA ticket.
Note on B43: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E48: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F48: Select from List. - Blank - Pass - Fail - Not Started
Note on G48: Enter Month / Day. Year defaults to current year unless entered.
Note on H48: Enter numeric portion of JIRA ticket.
Note on B52: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E57: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F57: Select from List. - Blank - Pass - Fail - Not Started
Note on G57: Enter Month / Day. Year defaults to current year unless entered.
Note on H57: Enter numeric portion of JIRA ticket.
Note on B61: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E66: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F66: Select from List. - Blank - Pass - Fail - Not Started
Note on G66: Enter Month / Day. Year defaults to current year unless entered.
Note on H66: Enter numeric portion of JIRA ticket.
Note on B70: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E75: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F75: Select from List. - Blank - Pass - Fail - Not Started
Note on G75: Enter Month / Day. Year defaults to current year unless entered.
Note on H75: Enter numeric portion of JIRA ticket.
Note on B81: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E86: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F86: Select from List. - Blank - Pass - Fail - Not Started
Note on G86: Enter Month / Day. Year defaults to current year unless entered.
Note on H86: Enter numeric portion of JIRA ticket.
Note on B90: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E95: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F95: Select from List. - Blank - Pass - Fail - Not Started
Note on G95: Enter Month / Day. Year defaults to current year unless entered.
Note on H95: Enter numeric portion of JIRA ticket.
Note on B99: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E104: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F104: Select from List. - Blank - Pass - Fail - Not Started
Note on G104: Enter Month / Day. Year defaults to current year unless entered.
Note on H104: Enter numeric portion of JIRA ticket.

## 5. C4
Test Case # | 27 | Test Case Name: | Product Categories - B2B View: C4
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page. • Customer is setup with B2B view in the Customer Profile
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Click on the 'Catalog' from the site navigation bar and then click on the 'Paper' (C1) category from the 'Browse Categories' section. |  | Expected Results same as in the step # 1, Test Case # 3.00, except it is for Paper category.
2 | Click on the 'Bond & Writing' (C2) category from the drop-down list under 'Paper' category. |  | Expected Results same as in the step # 2, Test Case # 5.00
| Click on the 'Classic Cotton' (C3) category from the drop-down list under 'Bond & Writing' category. |  | Expected Results same as in the step # 3, Test Case # 16.00
3 | Click on the '100%' (C4) category from the drop-down list under 'Premium Cotton' category. And validate the catalog page view. |  | • Breadcrumb: My Selection: Catalog / Paper x / Bond & Writing x / Premium Cotton x / 100% • By setup on the customer profile, the B2B view catalog page is displayed. All the functionalities remain the same as defined in the Test Script # 7.00, except for the following is updated: • 'Prodcut Categories' section shows no other level of categories. • 'Narrow By' section default to a different narrow by attribute(s) (i.e. Brand, Mfg, Size, Basis Weight, Mwt, Color, and Caliper) which is applicable for 'C3' category. • Number of total items results is updated for the '100 %' category or the selected category.
4 | Select the fourth view for 'Grid View' out of the four list views on the top-right side of the page, if the Grid view is not selected. |  | The item view page changes to display items in table/grid format
5 | Validate the B2B Grid view |  | Expected Results same as in the step # 5, Test Case # 5.00 (except items will be related to '100 %' (C3) category)
6 | Follow the rest of the steps, starting with step # 6 in Test Case # 5.00 |  | Expected Results same as in the Test Case # 5.00
Test Case # | 28 | Test Case Name: | Product Categories - B2C Full View: C4
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page. • Customer is setup with B2B view in the Customer Profile
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
| Follow the steps in Test Case # 6.00 and Validate the B2C Full view. |  | Expected Results same as Test Case # 6.00, except items will be related to '100%' (C3) category
Test Case # | 29 | Test Case Name: | Product Categories - B2C Full View: C3 - C4 My Price & Availability
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page. • Customer is setup with B2B view in the Customer Profile
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Follow the steps in Test Case # 7.00 and Validate the B2C Full view. |  | Expected Results same as Test Case # 7.00, except items will be related to '100%' (C3) category
Test Case # | 30 | Test Case Name: | Product Categories - B2C Full View: C3 - C4 Update My Price & Availability
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page. • Customer is setup with B2B view in the Customer Profile
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Follow the steps in Test Case # 8.00 and Validate the B2C Full view. |  | Expected Results same as Test Case # 8.00, except items will be related to '100%' (C3) category
Test Case # | 31 | Test Case Name: | Product Categories - B2C Full View: C3 - C4 User without 'View Price' permission
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page. • Customer is setup with B2B view in the Customer Profile
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Follow the steps in Test Case # 9.00 and Validate the B2C Full view. |  | Expected Results same as Test Case # 9.00, except items will be related to '100%' (C3) category
Test Case # | 32 | Test Case Name: | Product Categories - B2C Condensed View: C4
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page. • Customer is setup with B2B view in the Customer Profile
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Follow the steps in Test Case # 10.00 and Validate the B2C Full view. |  | Expected Results same as Test Case # 10.00, except items will be related to '100%' (C3) category
Test Case # | 33 | Test Case Name: | Product Categories - B2C Mini View: C4
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page. • Customer is setup with B2B view in the Customer Profile
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Follow the steps in Test Case # 11.00 and Validate the B2C Full view. |  | Expected Results same as Test Case # 11.00, except items will be related to '100%' (C3) category
Test Case # | 34 | Test Case Name: | Product Categories - B2B View - Anonymous: C4
Use Case # |  | Preconditions: | Annonymous user has navigated to the xpedx loging page.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Click on the 'Paper' (C1) category from the login page. |  | Expected Results same as in the step # 1, Test Case # 4.00, except it is for Paper category.
2 | Click on the 'Bond & Writing' (C2) category from the drop-down list under 'Paper' category. And validate the B2B grid view. |  | The Expected Result should be the same as Test Case # 12.00
3 | Click on the 'Premium Cotton' (C3) category from the drop-down list under 'Bond & Writing' category. |  | Expected Results same as Test Case # 12.00, except items will be related to 'Premium Cotton' (C3) category
4 | Click on the '100%' (C4) category from the drop-down list under 'Premium Cotton' category. Select the fourth view for 'Grid View' out of the four list views on the top-right side of the page, if the Grid view is not selected. And validate the B2B grid view. |  | Expected Results same as Test Case # 12.00, except items will be related to '`100%' (C3) category
Test Case # | 35 | Test Case Name: | Browse Categories - B2C Full View - Anonymous: C4
Use Case # |  | Preconditions: | Annonymous user has navigated to the xpedx loging page.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Continue from Test Case # 34.00 above. Select the first view for 'Full View' out of the four list views on the top-right side of the page. And validate the B2C Full view. |  | Expected Results same as Test Case # 13.00, except items will be related to 'Premium Cotton' (C3) category
Test Case # | 36 | Test Case Name: | Browse Categories - B2C Condensed View - Anonymous: C4
Use Case # |  | Preconditions: | Annonymous user has navigated to the xpedx loging page.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Continue from Test Case # 35.00 above. Select the second view for 'Condensed view' out of the four list views on the top-right side of the page. And validate the B2C Condensed view. |  | Expected Results same as Test Case # 14.00, except items will be related to 'Premium Cotton' (C3) category
Test Case # | 37 | Test Case Name: | Browse Categories - B2C Mini View - Anonymous: C3 - C4
Use Case # |  | Preconditions: | Annonymous user has navigated to the xpedx loging page.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Continue from Test Case # 36.00 above. Select the third view for 'Mini view' out of the four list views on the top-right side of the page. And validate the B2C Mini view. |  | Expected Results same as Test Case # 14.00, except items will be related to 'Premium Cotton' (C3) category
Note on B2: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E7: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F7: Select from List. - Blank - Pass - Fail - Not Started
Note on G7: Enter Month / Day. Year defaults to current year unless entered.
Note on H7: Enter numeric portion of JIRA ticket.
Note on B17: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E22: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F22: Select from List. - Blank - Pass - Fail - Not Started
Note on G22: Enter Month / Day. Year defaults to current year unless entered.
Note on H22: Enter numeric portion of JIRA ticket.
Note on B26: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E31: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F31: Select from List. - Blank - Pass - Fail - Not Started
Note on G31: Enter Month / Day. Year defaults to current year unless entered.
Note on H31: Enter numeric portion of JIRA ticket.
Note on B35: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E40: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F40: Select from List. - Blank - Pass - Fail - Not Started
Note on G40: Enter Month / Day. Year defaults to current year unless entered.
Note on H40: Enter numeric portion of JIRA ticket.
Note on B44: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E49: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F49: Select from List. - Blank - Pass - Fail - Not Started
Note on G49: Enter Month / Day. Year defaults to current year unless entered.
Note on H49: Enter numeric portion of JIRA ticket.
Note on B53: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E58: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F58: Select from List. - Blank - Pass - Fail - Not Started
Note on G58: Enter Month / Day. Year defaults to current year unless entered.
Note on H58: Enter numeric portion of JIRA ticket.
Note on B62: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E67: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F67: Select from List. - Blank - Pass - Fail - Not Started
Note on G67: Enter Month / Day. Year defaults to current year unless entered.
Note on H67: Enter numeric portion of JIRA ticket.
Note on B71: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E76: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F76: Select from List. - Blank - Pass - Fail - Not Started
Note on G76: Enter Month / Day. Year defaults to current year unless entered.
Note on H76: Enter numeric portion of JIRA ticket.
Note on B84: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E89: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F89: Select from List. - Blank - Pass - Fail - Not Started
Note on G89: Enter Month / Day. Year defaults to current year unless entered.
Note on H89: Enter numeric portion of JIRA ticket.
Note on B93: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E98: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F98: Select from List. - Blank - Pass - Fail - Not Started
Note on G98: Enter Month / Day. Year defaults to current year unless entered.
Note on H98: Enter numeric portion of JIRA ticket.
Note on B102: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E107: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F107: Select from List. - Blank - Pass - Fail - Not Started
Note on G107: Enter Month / Day. Year defaults to current year unless entered.
Note on H107: Enter numeric portion of JIRA ticket.

## 6. Product Detail
Test Case # | 38 | Test Case Name: | Product Detail Page
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Catalog page.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Follow Test Case # 5.00, step 1 and 2. |  | Bond & Writing' items are displayed in the items results section
2 | Click on any one Item Short/Long Description |  | Product detail screen should display
3 | Validate the product detail page |  | Breadcrumb: Back / (Item #) • Image (150 X 150 pixels) is displayed in the far left side. If there is no image, 'Image not on file' image will be displayed • Short Description (up to 260 characters) is displayed first to the right of the image in black. • Long Description of item attributes is displayed in bullets in black. Up to 5 bullets of information can be displayed. • Sell Text Description (up to 2000 characters) is displayed underneath the long description. By default, only one row of information is displayed and the rest of the description (of up to 2000 characters) can be viewed by '[Expand]' hyperlink. • 'xpedx/brand Item #:' and 'Mfg. Item #:' and/or 'Mpc Item #:' is displayed below the long description. Up to two item #s can be displayed. • Enviornment indicator (leaf icon) is displayed next to the xpedx/brand item #. • Replacement Item message is displayed in red with the Item(s) as hyperlink. "This item has been replaced. Select item: item A, item B, item C, item D, item E"
4 | Click on the 'Expand' hyperlink next to the sell text description |  | Full sell text description is displayed and the information below the sell text is moved down.
5 | Click on the 'Collapse' hyperlink next to the sell text description |  | Sell text description is collapsed and defaulted back to one row of information. The information below the sell text is pushed up.
6 | Validate the cross-sell, up-sell, and alternate item information, if available |  | • You might also consider section is displayed on the right side of the page for up-sell and alternate items. Up total of 5 items can be displayed for both up-sell and alternate items. If there are no up-sell or alternate items available, then you might also consider section (including the header) will not be displayed. • Popular accessories section is displayed on the right side of the page (underneath the You might also consider section) for cross-sell items. Up total of 5 items can be displayed for cross-sell items. If there are no cross-sell items available, then popular accessories section (including the header) will not be displayed. Note, total of up to 5 items for cross-sell, up-sell, alternate can be displayed for a given item.
7 | Validate the Availability tab information |  | • Availability tab is displayed by default • Availability information is displayed in the following format: (Note, availability UOM is displayed per the requested UOM): --- Availability ---------------------------------- Total Available: 225,000,000 Lids Next Day: 5,000 2+ Days: 20,000 2,500 available today at Cincinnati, OH -'Immediate' should list the number of items that requires 0 lead days. It also should list the Division name. -'Next Day' should list the number of items that requires 0 or 1 lead days. -'2+Days' should list the number of items that requires 2+Days . -'Total Quantity Available' available should be displayed with total number from Next Day and 2+Days
8 | Click and validate the Specifications tab information |  | • 'Specifications' tab is displayed with the specification and details column of information. • The product attributes information is displayed in a grid view and only the product attributes which has value are displayed. Any attributes with null value are not displayed on the screen.
9 | Click on the 'Reques Sample' hyperlink in blue |  | The request sample modal is displayed. Please refer to the request sample test scripts under the 'Services' functional area packet.
10 | Click on the 'MSDS' hyperlink in blue |  | Depending on the item, a pdf file or MSDS site is displayed in a separate page/browser.
11 | Validate the action fields to the right of the tab information |  | • 'Qty' text box and 'UOM' drop-down with default UOM is displayed. • Customer defined fields (can be upto 2 fields and are optional fields) are displayed underneath the Qty and UOM fields. • 'My Price & Availability' hyperlink (in blue), 'Add to My Items' and 'Add to Cart' button is displayed underneath the customer defined fields. • Stocked status of 'Mill / Mfg. Item - Addition al charges may apply.' is displayed in red for non-stocked item, if applicable.
12 | Validate the My Price information |  | Price information is displayed in the following format, underneath the action buttons or non-stocked status. (Note, the first and second price is unit price and third is requested price. The second price will display only for Paper items. Also, the my price are displayed in 5 decimals and extended price is displayed in 2 decimals.) My Price (USD): $999,999,999.00000 / Carton $999,999,999.00000 / Lid $999,999,999.00000 / Lid Extended Price (USD): $999,999,999.00
13 | Validate the Cost information, if applicable |  | Cost information is only displayed for Sales Rep user type. If applicable, the cost information is dispayed in the following format, with 'Show' and 'Hide' hyperlink. Cost (USD): $999,999,999.00000 / Lid
14 | Validate the Bracket Pricing information, if applicable |  | Bracket Pricing information and header is displayed in the following format, if applicable. If Bracket Pricing information is not applicable, both the header and detail is not displayed. (Note, my bracket pricing UOM is displayed per the requested UOM.) My Bracket Pricing (USD: 1 Lid - $35.38 / Lid 10 Lid - $325.38 / Lid 20 Lid - $3,325.38 / Lid 30 Lid - $335,555.38 / Lid
15 | Click on the 'Add to Cart' button |  | A warning message in red is displayed below the Add to Cart button a the line level, for example: "Qty is required field."
16 | Enter a non-numeric value in the Qty text field. Then click on the 'Add to Cart' button |  | A warning message in red is displayed below the 'Add to Cart' button at the line level, for example: "Please enter a numeric value."
17 | Enter a zero value in the Qty text field. Then click on the 'Add to Cart' button |  | A warning message in red is displayed below the 'Add to Cart' button at the line level, for example: "Quantity must be greater than 0."
18 | Enter a value in the Qty text field with qty that is less than the order multiple qty. (i.e enter 1000 qty if the item must be oredered in 18,000 qty). Then click on the 'Add to Cart' button. |  | A warning message in red is displayed below the 'Add to Cart' button at the line level, for example: "A minimum qty must be entered. Please re-enter."
Test Case # | 39 | Test Case Name: | Product Detail Page: Update My Price & Availability
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page. • Customer is setup with B2B view in the Customer Profile
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Continue from the above Test Script # 38.
2 | Enter a valid numeric value in the Qty text field and change the UOM from the drop-down. And click on the My Price & Availability |  | Availability, My Bracket Pricing (USD), and Price (USD) information is updated based on the Qty and UOM entered.
3 | Validate the Availability information |  | • Availability information is displayed in the following format: (Note, availability UOM is displayed per the requested UOM): --- Availability ---------------------------------- Total Available: 225,000,000 Lids Next Day: 5,000 2+ Days: 20,000 2,500 available today at Cincinnati, OH
4 | Validate the Bracket Pricing information, if applicable |  | Bracket Pricing information and header is displayed in the following format, if applicable. If Bracket Pricing information is not applicable, both the header and detail is not displayed. (Note, my bracket pricing UOM is displayed per the requested UOM.) ---- My Bracket Pricing (USD) ------------ 1 Lid - $35.38 / Lid 10 Lid - $325.38 / Lid 20 Lid - $3,325.38 / Lid 30 Lid - $335,555.38 / Lid
5 | Validate the My Price information |  | Price information is displayed in the following format, next to the Bracket Pricing section. (Note, the first and second price is unit price and third is requested price. The second price will display only for Paper items. Also, the my price are displayed in 5 decimals and extended price is displayed in 2 decimals.) ---Price (USD)--------------- My Price: $999,999,999.00000 / Carton $999,999,999.00000 / Lid $999,999,999.00000 / Lid Extended Price: $999,999,999.00
6 | Enter a valid numeric value in the Qty text field. Then click on the 'Add to Cart' button |  | The item is added to cart and can be validated on the header page (under cart & mini-cart drop-down). A confirmation message in blue is displayed below the Add to Cart button a the line level, for example: "Item has been successfully added to cart." The Qty for the given item is refreshed to blank. The P & A section is collapsed.
Test Case # | 40 | Test Case Name: | Product Detail Page: User without 'View Price' permission
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Home page. • Customer is setup with B2B view in the Customer Profile
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Continue with step 3 from the Test Script 38.00 above.
2 | Validate the Availability information |  | • Availability information is displayed in the following format: (Note, availability UOM is displayed per the requested UOM): --- Availability ---------------------------------- Total Available: 225,000,000 Lids Next Day: 5,000 2+ Days: 20,000 2,500 available today at Cincinnati, OH
3 | Validate the Bracket Pricing information, if applicable |  | Bracket Pricing information (including the header) is not displayed to the user.
4 | Validate the My Price & Extended Price information |  | My Price and Extended Price information (including the header) is not displayed to the user.
Test Case # | 41 | Test Case Name: | Product Detail Page - Replacement Item Functionality
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Catalog page. • Customer User is at any category level from C2 - C4
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Validate the Replacement Item functionality |  | • Replacement Item message is displayed in red with the Item(s) as hyperlink. "This item has been replaced. Select item: item A, item B, item C, item D, item E" • Replacement Item message with the item # will only appear if replacement item(s) is available for the given item. • Up to 5 replacement item # can be available
2 | Click on the 'Item #' hyperlink for any one replacement item |  | Product detail page for the up-sell item is displayed.
3 | Click on the 'back' link from the product detail page of the up-sell item |  | Previous product detail page is displayed
Test Case # | 42 | Test Case Name: | Product Detail Page - Up-Sell Item Functionality
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Catalog page. • Customer User is at any category level from C2 - C4 • Product Detail must have an up-sell item
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Validate the "You might also consider" section for up-sell item. |  | • Item Image is displayed first. If there is no image, 'no image found' image will be displayed. (Although, all up-sell items should have product image.) • Short Description is displayed under the image. • Show Details button is displayed underneath the short description.
2 | Click on the 'Show Details' button |  | Product detail page for the up-sell item is displayed.
3 | Click on the 'back' link from the product detail page of the up-sell item |  | Previous product detail page is displayed
Test Case # | 43 | Test Case Name: | Product Detail Page - Alternate Item Functionality
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Catalog page. • Customer User is at any category level from C2 - C4
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Validate the "You might also consider" section for alternate item. |  | • Item Image is displayed first. If there is no image, 'no image found' image will be displayed. (Although, all up-sell items should have product image.) • Short Description is displayed under the image. • Show Details button is displayed underneath the short description.
2 | Click on the 'Show Details' button |  | Product detail page for the alternate item is displayed.
3 | Click on the 'back' link from the product detail page of the alternate item |  | Previous product detail page is displayed
Test Case # | 44 | Test Case Name: | Product Detail Page - Cross-sell Item Functionality
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Catalog page. • Customer User is at any category level from C2 - C4
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Validate the "Popular Accessories" section for cross-sell item. |  | • Item Image is displayed first. If there is no image, 'no image found' image will be displayed. (Although, all up-sell items should have product image.) • Short Description is displayed under the image. • Show Details button is displayed underneath the short description.
2 | Click on the 'Show Details' button |  | Product detail page for the cross-sell item is displayed.
3 | Click on the 'back' link from the product detail page of the cross sell item |  | Previous product detail page is displayed
Test Case # | 45 | Test Case Name: | Product Detail Page - Add to My Items
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer is logged in and has navigated to the Catalog page. • Customer User is at any category level from C2 - C4
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Click on 'Add to My Items' button |  | Select My Items List modal is displayed with option to add to an existing personal list or to create a new list. Up to 10 personal list should be displayed. If there are more than 10 personal list, they can be viewed by scrolling down on the scroll bar. • Create New list is displayed in blue with hyperlink at the bottom of the modal. • Cancel and Apply buttons are displayed to the right of the create a new list hyperlink.
2 | Click on one or more of the personal list radio button and then click on 'Apply' button |  | The item is add to the selected personal list(s). The modal is closed and returns to Item detail page. On the item detail page under the 'Add to My Items' button, a confirmation message of "Item has been added to the list(s)" is displayed in blue.
3 | Click on 'Add to My Items' button again |  | Select My Items List modal is displayed again.
4 | Click on 'Cancel' button |  | The modal is closed and returns to Item detail page.
5 | Click on 'Add to My Items' button again |  | Select My Items List modal is displayed again.
6 | Click on 'Apply' button |  | A warning message of "You must select at least one list from above." is displayed in red.
7 | Click on 'Create New List' hyperlink |  | New My Items List modal is displayed to create a new list. Note, the new my Items list modal functionality works the same way as defined in the MIL packet. The rest of the steps are copied from the MIL test scripts. User should be able to see Create My Items List dialog box with Name and Description text fields with Personal and Shared radio button. Save and Cancel buttons should also be displayed.
8 | User selects Personal radio button and clicks on Save button. |  | The user should be able to see a validation message "Name is required" in Red below the line of Modal title and the Name text field should be highlighted and display "Required Field" in Red
9 | User selects Personal radio button, enters Name and Description |  | Name text field should only allow 35 chanracters and should not wrap. Description text field should only allow 255 characters and should wrap.
10 | User clicks on Save button. |  | User should be able to see the list is created with Name and Description and user on the MIL edit page. The modal is closed and returns to Item detail page. On the item detail page under the 'Add to My Items' button, a confirmation message of "Item has been added to the list(s)" is displayed in blue.
11 | User Clicks on Create New List hyperlink again |  | User should be able to see Create My Items List dialog box with Name and Description text fields with Personal and Shared radio buttons. Save and Cancel buttons should also be displayed.
12 | User selects Shared radio button |  | User should be able to see the check box Edit by Admin users only next to the Shared radio button.
13 | User Clicks on Save Button |  | The user should be able to see a validation message "Name is required" in Red below the line of Modal title and the Name text field should be highlighted and display "Required Field" in Red
14 | User enters Name and Description |  | Name text field should only allow 35 chanracters and should not wrap. Description text field should only allow 255 characters and should wrap.
15 | User selects Shared radio button |  | User should be able to see following Customer hirearchy in a panel- Customer (SAP): Name (Number) Bill-To: "Account without suffix" Name, Address1, City, ST, zip Ship-To: Suffix, Name, Address1, City, ST zip Example: Metro Graphics (0000098550) > 90-2101135 Metro Graphics DBA, Flash Printing, Charlotte, NC 28205 >> 000001 Metro Grapics, 1119 Clement Ave, Charlotte, NC 28205 >> 000002 Metro Grapics Compass, 1119 Clement Ave, Charlotte, NC 28205 Scroll bar should only be available inside the panel. Save and Cancel Buttons should be outside of this panel. User should not be able to see the + and - sign to expand and collapse at the Ship to level. This hirearchy should match the customer assignment for this.
16 | User checks the check box at Bill to level (account). |  | All the Ship tos belonging to this Bill to should be checked. Note - The assumption is one of the Ship to is Admin and another one is Buyer.
17 | User clicks Save Button |  | The list should be created and should be shared for all checked addresses. The modal is closed and returns to Item detail page. On the item detail page under the 'Add to My Items' button, a confirmation message of "Item has been added to the list(s)" is displayed in blue.
Test Case # | 46 | Test Case Name: | Product Detail Page - Anonymous
9 |  | Preconditions: | Annonymous user has navigated to the xpedx loging page.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Click on any one Item Short/Long Description from any of the C2 - C4 category level |  | Product detail screen should display
2 | Validate the product detail page |  | The Expected Result should be the same as Test Case # 38.00 and 41.00 - 44.00, except with the following exceptions: • Note, header page and ship for banner will be validated as part of the "Miscellaneous" packet • 'Show normally stocked items only' check box is not available • Qty, UOM drop-down, My Price & Availability, Add to cart, and Customer Defined fields options are not displayed • Stocked status of 'Mill / Mfg. Item - Additional charges may apply.' is not displayed • My Price, Extended Price, Cost, My Bracket Pricing information is not displayed • Availability tab and Request Sample hyperlink is not displayed
Note on B2: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E7: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F7: Select from List. - Blank - Pass - Fail - Not Started
Note on G7: Enter Month / Day. Year defaults to current year unless entered.
Note on H7: Enter numeric portion of JIRA ticket.
Note on B28: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E33: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F33: Select from List. - Blank - Pass - Fail - Not Started
Note on G33: Enter Month / Day. Year defaults to current year unless entered.
Note on H33: Enter numeric portion of JIRA ticket.
Note on B42: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E47: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F47: Select from List. - Blank - Pass - Fail - Not Started
Note on G47: Enter Month / Day. Year defaults to current year unless entered.
Note on H47: Enter numeric portion of JIRA ticket.
Note on B54: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E59: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F59: Select from List. - Blank - Pass - Fail - Not Started
Note on G59: Enter Month / Day. Year defaults to current year unless entered.
Note on H59: Enter numeric portion of JIRA ticket.
Note on B65: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E70: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F70: Select from List. - Blank - Pass - Fail - Not Started
Note on G70: Enter Month / Day. Year defaults to current year unless entered.
Note on H70: Enter numeric portion of JIRA ticket.
Note on B76: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E81: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F81: Select from List. - Blank - Pass - Fail - Not Started
Note on G81: Enter Month / Day. Year defaults to current year unless entered.
Note on H81: Enter numeric portion of JIRA ticket.
Note on B87: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E92: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F92: Select from List. - Blank - Pass - Fail - Not Started
Note on G92: Enter Month / Day. Year defaults to current year unless entered.
Note on H92: Enter numeric portion of JIRA ticket.
Note on B98: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E103: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F103: Select from List. - Blank - Pass - Fail - Not Started
Note on G103: Enter Month / Day. Year defaults to current year unless entered.
Note on H103: Enter numeric portion of JIRA ticket.
Note on B123: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E128: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F128: Select from List. - Blank - Pass - Fail - Not Started
Note on G128: Enter Month / Day. Year defaults to current year unless entered.
Note on H128: Enter numeric portion of JIRA ticket.

## 7. Other
Test Case # | 47 | Test Case Name: | Compare Items - Registered/Anonymous user
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer and Anonymous user has navigated to the Catalog page. • Customer User is at any category level from C2 - C4
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Click and drag item to the 'Drag to Compare Items' function on the top of the page. Continue to add more items to compare and validate the # of items results. (Note, this function can be tested for any category level page from C2 - C4 and from any of the Narrow By selection as defined in the some of the other test scripts.) |  | The item is copied over to the Compare page and displays 1 items. If more items are added, the number will change for the # of items added to compare. |  | Fail
2 | Click on the 'Compare Items' link and validate the compage page |  | • Breadcrumb: Back / Compare Items • System displays Compare Item page with the selected items. Note, the system will not allow you to click on the compare page unless more than one item is added. A pop-up alert box is displayed with message and 'OK' button. Msg: At least two items required for Product comparison. • Items are displayed in the same format as B2C Mini view with majority of the functionalities that is available on the category page • Shopping for banner is displayed on the top of the page above the Breadcrumb. This will be tested as part of the "Miscellaneous' packet. • Remove hyperlink is displayed first for each item • Image is displayed underneath the Remove link and centered aligned in the Item results section. If there is no image, 'no image found' image will be displayed • 'xpedx/brand Item #:' and 'Mfg. Item #:' and/or 'Mpc Item #:' is centered aligned and displayed below the image. Up to two item #s can be displayed. • Enviornment indicator (leaf icon) is displayed next to the xpedx/brand item #. • Short Description (up to 200 characters) is displayed underneath the item #s. • Show Differences button is displayed by default to hide attributes that are not applicable to the selected items.
3 | Validate the product specification section |  | • Each product attribute is displayed in a row with the value for each item added in column format. • Attribute name is displayed in the left column followed by the value stored for each item. If the value is not applicable for a given item, a dash/- line is displayed. • If the value does not exist for all the items displayed, then the given attribute is not displayed in the product specification section. • The page will continue to expand automatically depending on the # of attributes applicable. A scroll bar will be available to the left to view additional attributes at the bottom of the page. • Similarily, there are no limits on how many # of items can be added to the compare page and the page will continue to expand to the right depending on the # of items added. A scroll bar will be available at the bottom of the screen to view additional items. | dash is not showing, but was requested to add as part of the wish list | Pass
4 | Click on 'Show Differences' button |  | • All the attributes in the product specification section which has different value for each of the item is displayed at the bottom of the page. Any attributes values which values are the same across all the items is hidden/ not displayed.
5 | Click on 'Show All' button |  | • All the attributes in the product specification section applicable for each of the item is displayed at the bottom of the page again.
6 | Click on 'Remove' button for a given item |  | • The entire column (with the attributes at the bottom of the page) is removed for the given item.
Test Case # | 48 | Test Case Name: | Search Catalog - Registered/Anonymous user
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer and Anonymous user has navigated to the xpedx login or home page.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Enter any of the attributes or scenarios (from the column A in the Search tab ) in the Search Catalog text box on the top/header of the page. |  | The "Search Catalog" text inside the text box is disappeared and the entered text is displayed.
2 | Click on the 'search' icon or enter the 'Enter' key on the keyboard. |  | The items with the matching results from the entire catalog are displayed in either of the four view (depending on which view is setup in the user profile). If there is a one to one match on the item #, then item detail page is displayed.
Test Case # | 49 | Test Case Name: | Search within results - Registered/Anonymous user
Use Case # |  | Preconditions: | • Customer Admin/Customer Buyer and Anonymous user has navigated to the xpedx login or home page.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Click on the Catalog link on the site navigation bar |  | The Catalog home page is displayed
2 | Enter any of the attributes or scenarios (from the column A in the Search tab ) in the Search within results text box above the Product Categories navigation bar on the left of the page. |  | The "Search within results" text inside the text box is disappeared and the entered text is displayed.
3 | Click on the 'search' icon or enter the 'Enter' key on the keyboard. |  | • The items with the matching results from the entire catalog are displayed in either of the four view (depending on which view is setup in the user profile). If there is a one to one match on the item #, then item detail page is displayed. • Note, the search within results function will narrow the search within the breadcrumb/my selection instead of searching from the entire catalog, unless the search was executed at the Catalog landing page.
Test Case # | 50 | Test Case Name: | Search within results: Stocked/Non-stock Items (Registered user only)
Use Case # |  | Preconditions: | Customer Admin/Customer Buyer is logged in and has navigated to the Home page.
DDD ID:
Req. # |  | Notes:
Step # | User Input |  | Expected Results | Actual Results / Comments | Pass/Fail | Date Executed | JIRA #
1 | Click on the Catalog link on the site navigation bar |  | The Catalog home page is displayed
2 | Enter any of the attributes or scenarios (from the column A in the Search tab ) in the Search within results text box above the Product Categories navigation bar on the left of the page. |  | The "Search within results" text inside the text box is disappeared and the entered text is displayed.
3 | Check the checkbox for 'Search normally stocked items only' to search for only stocked items. |  | The checkbox is checked and the entered text above is displayed.
3 | Click on the 'search' icon or enter the 'Enter' key on the keyboard. |  | • The system displays only the 'Stocked' items in the item results section. The items with the matching results are displayed in either of the four view (depending on which view is setup in the user profile). If there is a one to one match on the item #, then item detail page is displayed. • Note, the search within results function will narrow the search within the breadcrumb/my selection instead of searching from the entire catalog, unless the search was executed at the Catalog landing page.
4 | Uncheck the checkbox for 'Show normally stocked items only' to search for both stocked and non-stocked items. |  | The system displays both 'Stocked' and 'Non-stocked' categories/items in the category/item results section
5 | Click on the Catalog link on the site navigation bar |  | The Catalog home page is displayed and the checkbox for "Search for normally stocked items" remains checked. The checkbox will remain check through the session until the user logout.
6 | Enter any of the attributes or scenarios (from the column A in the Search tab ) in the Search within results text box above the Product Categories navigation bar on the left of the page. |  | The "Search within results" text inside the text box is disappeared and the entered text is displayed.
7 | Uncheck the checkbox for 'Search normally stocked items only' to search for only stocked items. |  | The checkbox is unchecked and the entered text above is displayed.
8 | Click on the 'search' icon or enter the 'Enter' key on the keyboard. |  | • The system displays 'Stocked' and 'Non-stocked' items in the item results section. The items with the matching results are displayed in either of the four view (depending on which view is setup in the user profile). If there is a one to one match on the item #, then item detail page is displayed. • Note, the search within results function will narrow the search within the breadcrumb/my selection instead of searching from the entire catalog, unless the search was executed at the Catalog landing page.
Note on B2: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E7: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F7: Select from List. - Blank - Pass - Fail - Not Started
Note on G7: Enter Month / Day. Year defaults to current year unless entered.
Note on H7: Enter numeric portion of JIRA ticket.
Note on B16: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E21: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F21: Select from List. - Blank - Pass - Fail - Not Started
Note on G21: Enter Month / Day. Year defaults to current year unless entered.
Note on H21: Enter numeric portion of JIRA ticket.
Note on B26: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E31: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F31: Select from List. - Blank - Pass - Fail - Not Started
Note on G31: Enter Month / Day. Year defaults to current year unless entered.
Note on H31: Enter numeric portion of JIRA ticket.
Note on B36: Test Status: RED if any Fail WHITE if any Not Started GREEN if any Pass and no Fail & No Not Started
Note on E41: Indicate whether results comply with expectations or describe exceptions with sufficient detail to permit replication.
Note on F41: Select from List. - Blank - Pass - Fail - Not Started
Note on G41: Enter Month / Day. Year defaults to current year unless entered.
Note on H41: Enter numeric portion of JIRA ticket.

## 0. Dropdown Values (hidden)
Pass
Fail
Not Started

## 8. Search
Attributes/Scenarios | SC | SR (C1) | SR (C2) | SR (C3) | SR (C4) | SR (C1) - Stocked | SR (C2) - Stocked | SR (C3) - Stocked | SR (C4) - Stocked | SC/SR > NB (C1) | SC/SR > NB (C2) | SC/SR > NB (C3) | SC/SR > NB (C4) | SC/SR > NB (C1) - Stocked | SC/SR > NB (C2) - Stocked | SC/SR > NB (C3) - Stocked | SC/SR > NB (C4) - Stocked
xpedx Item # | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Product Name | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Product Description | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Mfg. Item # | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Mfg. Name | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Mfg. Item Description | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Customer Item # | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
Other Attributes flagged from Content Directory | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X | X
upper/lowercase:
White | X | X
Wh ite | X | X
White Paper | X | X
White Bright | X | X
wh* | X | X
wh | X | X
wh paper | X | X
white pa | X | X
(Any other per business choice) | X | X
** SC = Search Catalog
***SR = Search within Results
****NB = Narrow By