## SWC
JIRA Defect # | Priority | Severity | Start Date | Expected Dev Complete Date | Actual Dev Complete Date | Closed Date | Hrs Spend to Reproduce and Analyze | Hrs Spend to Fix | Hrs Spent to Test | Status | Assigned To | Defect Brief | Regression Areas | Action Taken By Developer | Files Updated | Code Reviewed
1650 | High |  | 2011-08-16 | 2011-08-18 |  |  | 2 | 0.5 | 0.5 | Dev testing Pending | Jagadeesh | Session Timeout and Blank Item Detail Page | MIL, Catalog | If item is not entitled showed the users the message | XPEDXAnonItemDetails.jsp | None
1402 | High |  | 2011-08-17 | 2011-08-18 |  |  | 1 | 2 | 0.5 | Dev testing Pending | Jagadeesh | Performance in MIL | MIL | Used Complex Query where it can be used | XPEDXWCUtils.java,XPEDXMyItemsDetailsAction.java | None
2629 | High | 1 | 2011-08-12 | 2011-08-12 | 2011-08-12 | NA | 4 Hours 30 Minutes | 30 Minutes | 2 Hours | In Progress | Vaibhav -> Troy | User Profile Quick Links issues | User Profile | Already fixed on Friday, but functionality again broken as Troy made some changes, tested today on Dev and figured out by history, informed to Troy to fix it now. | XPEDXUserProfile.jsp | Radha
2654 | Medium | 1 | 2011-08-17 | 2011-08-17 | 2011-08-17 | NA | 2 Hours 30 Minutes | 2 Hours 30 Minutes | 1 Hour | In Progress | Vaibhav | Attempts to publish an article with a duplicate name takes user to unskinned System Error page. | Admin -> News Articles | Passing all available article names, and checking in JS even before going to Preview page. If article name is duplicate then returning on same page with proper error messages. | XPEDXNewArticle.jsp, XPEDXArticleData.jsp
2648 | High | 3 | 16/08/2011 | 19/08/2011 |  |  | 0.5 | 4 |  | In Progress | Amar Jyoti | Minimum Order Charge Fails in WC. WC should have added a $25.00 Minimum Order Charge (MAX &05). The line/description is in WC and on the MAX order, but there is no extended price on either. | Order Placement | ExtnAdjUnitPrice field was not getting populated since it was a new field which we send to legacy.17/08/2011 I tested Unit Price is not going to legacy and because of that price is coming 0 . So looking in to the issue. | XPXCreateSpecialChargeLineAPI | Radha
2384 | High | 1 | 16/08/2011 |  |  |  | 2 |  |  | Assigned to testers for logs | Donnette Hawly | C is not calculating 5 decimal pricing correctly on price/Thousand MAX is sending 273.17241/Thousand for price on item 2260512. | P & A and Order Placement | None | None | None
2639 | High | 3 | 16/08/2011 |  |  |  | 3 |  |  | Assigned to testers for logs | Donnette Hawly | WC displaying the wrong User ID on OM page, Web Conf Detail, & Order Detail - see attached document for Web Conf 110810E9940060 / 757815700 (in MAX 90-78157). | WC - Order Packet 2 | None | None | None
2644 | Critical | 1 | 16/08/2011 | 19/08/2011 |  |  | 4 |  |  | In Progress | Amar Jyoti | OM2 - WC sending lines in Edit Order OP to MAX with no line numbers. | MCF - OP/OU | Changing the Applypendingchanges to ResetPendingChanges | XPEDXOrderPlaceAction | None
2631 | High | 3 | 16/08/2011 |  |  |  | 0.5 | 0.5 |  | Verified the code and assigned to testers | Bill Smeltz | Readiness-Misc-IE/Firefox Signon Page Category Images Missing - First Time In | WC - Misc | Verified the code and assigned to testers | None | None
2657 | High | 3 | 17/08/2011 | 18/08/2011 |  |  | 0.5 | 0.5 |  | Fixed | Amar Jyoti | The value 'null' is actually displayed in list box after the last remaining item is deleted and page is Saved. | WC - Services | added condition for null | XPEDXSaveUserInfo.java | Radha

## COM
JIRA Defect # | Priority | Severity | Start Date | Expected Dev Complete Date | Actual Dev Complete Date | Closed Date | Hrs Spend to Reproduce and Analyze | Hrs Spend to Fix | Hrs Spent to Test | Status | Assigned To | Defect Brief | Regression Areas | Action Taken By Developer | Files Updated | Fix Reviewd
2645 | Medium | 1 | 16-08-2011 | 16-08-2011 | 16-08-2011 |  | 2 | 2 | 4 | Fixed | Sunil | CC-Business Rule | Order Creation & Edit | Analyzed & fixing
2582 | Critical |  | 2011-12-08 | 17/8/2011 |  |  | 2 | 4 | 5 | Testing Pending | Veeru | Prevent edit of the order in CC (CR) |  | Analyzed & fixed | Header panel& Lines PanelBehavior |  | Commented these CR (2581,2591)Changes - as back-end Systems are not yet ready for Integration testing
2591 | critical |  | 16/9/2011 | 17/8/2011 |  |  | 1 | 2 | 4 | Testing Pending | Veeru | Showing the Extended Quantity on the FO's |  | Analyzed & fixed | orderLine panel
2589 | critical |  | 2011-12-08 | 17/08/2011 |  |  | 2 | 4 | 2 | In Progress | Sunil | Changes to handle OP Response Timeout Issues |  | Analyzed & fixing | OrderHeaderPanel,OrderSearchWizardExtnBehaviour,
2010 | Medium |  | 13/8/2011 | 18/8/2011 |  |  | 4 | 0 | 0 | In progress | Krithika | Understanding the Create Order and Edit Order Flow |  | Analyzing
2661 | Medium | 3 | 17/08/2011 | 17/08/2011 | 17/08/2011 |  | 2 | 2 | 1 | Fixed | Manas | MIL Delete List Does not Delete List until Log out/ log in MIL | It will delete the Item list and will refresh the screen. | Analyzed & fixed | XPXMyItemsSearchListScreen
1771 | Medium | 5 | 17/08/2011 | 17/08/2011 | 17/08/2011 |  | 1 | 0 | 1 | Assigned Back | Manas | Ship To Address format change |  | Analyzed and attached screenshot.

## MCF-B2B
JIRA Defect # | Priority | Severity | Start Date | Expected Dev Complete Date | Actual Dev Complete Date | Closed Date | Hrs Spend to Reproduce and Analyze | Hrs Spend to Fix | Hrs Spent to Test | Status | Assigned To | Defect Brief | Regression Areas | Action Taken By Developer | Files Updated | Fix Reviewd
2646 | High |  | 16/08/2011 | 16/08/2011 | 16/08/2011 |  |  | 0.5 |  | Fixed | Staney | Request for Master configuration change.
2644 | Critical |  | 16/08/2011 | 17/08/2011 |  |  | 7 |  |  | In progress | Staney | Exception occurs when adding a new line to an existing order