## SWC
JIRA Defect # | Priority | Severity | Start Date | Expected Dev Complete Date | Actual Dev Complete Date | Closed Date | Hrs Spend to Reproduce and Analyze | Hrs Spend to Fix | Hrs Spent to Test | Status | Assigned To | Defect Brief | Regression Areas | Action Taken By Developer | Files Updated | Code Reviewed
2486 | Medium | 1 | 2011-08-17 | 2011-08-17 | 2011-08-17 |  | 1 | 2 | 1 | Fixed and checked in CVS | Ragini | Sales rep url consists with word xpedx | WC-Sales REP | Added a sales rep login mapping in web.xml | web.xml, XPEDXHomeStruts.xml | Ragini/Radha
2109 | High | 2 | 2011-08-16 | 2011-08-17 | 2011-08-17 |  | 1 |  | 2 | Assigned back to reporter | Ragini | Password reset | WC-Password Reset | Not an issue. Tested in DEV and assigned back to reporter with proper comments | NA | NA
2632 | Critical | 3 | 2011-08-12 | 2011-08-12 | 2011-08-16 | 2011-08-17 |  |  | 1 | Completed | Ragini | Sales rep - Other than xpedx users, it was showing xpedx logout page | WC-Sales REP
2632 | Medium | 3 | 2011-08-16 | 2011-08-16 | 2011-08-17 |  | 2 | 2 | 4 | Fixed and checked in CVS | Shilpa N R | Mini Cart - UI Issue on mini cart qty update | WC - Order Packet 2 | Analyzed that it was throwing error only for 1 item in mini cart.Added a check for enter key in XPEDXMinicart.jsp | XPEDXMiniCart.jsp , swc.js | Ragini
2647 | Medium | 1 | 2011-08-16 | 2011-08-16 | 2011-08-16 | 2011-08-17 |  |  | 1 | Completed | Ramya UR | WC QA Resources - NEWS - News can be written, previewed, & published without prompting for dates | WC-Manage News | Tested on Dev and scheduled for staging | XPEDXNewArticle.jsp
2662 | High | 5 | 2011-08-17 | 2011-08-17 | 2011-08-17 |  | 3 | 2 | 1 | Fixed and Checked in CVS | Ramya UR | WC QA Services Admin - Manage News - Unable to edit FIRST news article | WC-Manage News | removed the a href id on the article name | XPEDXArticleData.jsp | Will be reviewed by Ragini
2035 | High | 1 | 2011-08-16 | 2011-08-16 | 2011-08-17 |  |  | 6 |  | Checked in | Sumit Rangdal | Services-IE/Firefox News Article page Created news article not published to customer organization. | WC - Admin | Analyzed & fixing | XPEDXArticleData.jsp | Ragini
2664 | High | 5 | 2011-08-17 | 2011-08-18 |  |  | 2 |  |  | Partially Fixed/ In Progress | Sumit Rangdal | OM2 - Approval button is not labeled correctly and Approver buttons (Reject Order and Approve Order) are missing on Web Confirmation Detail page. | WC - OM2 | Analyzed & fixing
1650 | High |  | 2011-08-16 | 2011-08-18 |  |  | 2 | 0.5 | 0.5 | Dev testing Pending | Jagadeesh | Session Timeout and Blank Item Detail Page | MIL, Catalog | If item is not entitled showed the users the message | XPEDXAnonItemDetails.jsp | None
1402 | High |  | 2011-08-17 | 2011-08-18 |  |  | 1 | 2 | 0.5 | Dev testing Pending | Jagadeesh | Performance in MIL | MIL | Used Complex Query where it can be used | XPEDXWCUtils.java,XPEDXMyItemsDetailsAction.java | None
2629 | High | 1 | 2011-08-12 | 2011-08-12 | 2011-08-12 | NA | 4 Hours 30 Minutes | 30 Minutes | 2 Hours | In Progress | Vaibhav -> Troy | User Profile Quick Links issues | User Profile | Already fixed on Friday, but functionality again broken as Troy made some changes, tested today on Dev and figured out by history, informed to Troy to fix it now. | XPEDXUserProfile.jsp | Radha
2654 | Medium | 1 | 2011-08-17 | 2011-08-17 | 2011-08-17 | NA | 2 Hours 30 Minutes | 2 Hours 30 Minutes | 1 Hour | In Progress | Vaibhav | Attempts to publish an article with a duplicate name takes user to unskinned System Error page. | Admin -> News Articles | Passing all available article names, and checking in JS even before going to Preview page. If article name is duplicate then returning on same page with proper error messages. | XPEDXNewArticle.jsp, XPEDXArticleData.jsp
2648 | High | 3 | 16/08/2011 | 19/08/2011 |  |  | 0.5 | 4 |  | In Progress | Amar Jyoti | Minimum Order Charge Fails in WC. WC should have added a $25.00 Minimum Order Charge (MAX &05). The line/description is in WC and on the MAX order, but there is no extended price on either. | Order Placement | ExtnAdjUnitPrice field was not getting populated since it was a new field which we send to legacy.17/08/2011 I tested Unit Price is not going to legacy and because of that price is coming 0 . So looking in to the issue. | XPXCreateSpecialChargeLineAPI | Radha
2384 | High | 1 | 16/08/2011 |  |  |  | 2 |  |  | Assigned to testers for logs | Amar Jyoti | C is not calculating 5 decimal pricing correctly on price/Thousand MAX is sending 273.17241/Thousand for price on item 2260512. | P & A and Order Placement | None | None | None
2639 | High | 3 | 16/08/2011 |  |  |  | 3 |  |  | Assigned to testers for logs | Amar Jyoti | WC displaying the wrong User ID on OM page, Web Conf Detail, & Order Detail - see attached document for Web Conf 110810E9940060 / 757815700 (in MAX 90-78157). | WC - Order Packet 2 | None | None | None
2644 | Critical | 1 | 16/08/2011 | 19/08/2011 |  |  | 4 |  |  | In Progress | Amar Jyoti | OM2 - WC sending lines in Edit Order OP to MAX with no line numbers. | MCF - OP/OU | Changing the Applypendingchanges to ResetPendingChanges | XPEDXOrderPlaceAction | None
2631 | High | 3 | 16/08/2011 |  |  |  | 0.5 | 0.5 |  | Verified the code and assigned to testers | Amar Jyoti | Readiness-Misc-IE/Firefox Signon Page Category Images Missing - First Time In | WC - Misc | Verified the code and assigned to testers | None | None
2657 | High | 3 | 17/08/2011 | 18/08/2011 |  |  | 0.5 | 0.5 |  | Fixed | Amar Jyoti | The value 'null' is actually displayed in list box after the last remaining item is deleted and page is Saved. | WC - Services | added condition for null | XPEDXSaveUserInfo.java | Radha
Note : Completed means Scheduled and assigned to TROY

## COM
JIRA Defect # | Priority | Severity | Start Date | Expected Dev Complete Date | Actual Dev Complete Date | Closed Date | Hrs Spend to Reproduce and Analyze | Hrs Spend to Fix | Hrs Spent to Test | Status | Assigned To | Defect Brief | Regression Areas | Action Taken By Developer | Files Updated | Fix Reviewd

## MCF-B2B
JIRA Defect # | Priority | Severity | Start Date | Expected Dev Complete Date | Actual Dev Complete Date | Closed Date | Hrs Spend to Reproduce and Analyze | Hrs Spend to Fix | Hrs Spent to Test | Status | Assigned To | Defect Brief | Regression Areas | Action Taken By Developer | Files Updated | Fix Reviewd