## Misc
| Hours | In Scope BR1 |  | Effort | Effort (Man Days)
1. Sign In Page (Promotion): It should be based on storefront. Html file name convention <Storefront>_SignInPage_Promo.html / The development is in the lines of what we did for the other promo areas on catalog pages. | 6 |  | 6 | 210 | 26.25 | 1 jpeg/store front - 6 Promo alone - 10 Promo/storefront - 16
2. Sign In Page: Storefront specifc store images and links. (See requirements doc for more details). Hardcoded image names and links. | 6 |  | 6 |  |  | Hardcoded - 6 Dynamic - 16
3. Sign In Page: Submit form at the time of enter key for logging in the user | 0 |  | 0
4. Sign In Page: Disable Esc key for Terms & Access modal. The user should not be able to by pass. In order to show or not to show the T&A modal, the user needs to be identified. In order to keep them on the sign in page, we need to analyze and come back with a solution. We should just have Accept button on the modal, what is the purpose of the Cancel button? Also make sure the date timestamp is captured and not just the login date. | 24 | wait | 0
4. Sign In Page: Terms & Access modal - keep the current flow, except prevent the user from closing the modal until he/she accepts the Terms & Access | 6
5. Sign In Page: Register - opens modal | 6 | wait | 0 |  |  | Keep as page instead of modal
6. Sign In Page (about us): Storefront specific links to marketing site in a new browser. | 6 |  | 6
7. Sign In Page (MSDS): MSDS - hyperlink to to msdsonfile.com in a new browser. | 0 |  | 0 |  |  | Will be part of HTML
8. Sign In Page (Social Media): Social media icon - hyperlink to facebook.com/xpedx, twitter.com/xpedx and youtube.com/xpedx. This applies to xpedx storefront only. For other storefronts, we don't show the icons. | 4 | wait | 0
9. Sign In Page (sign out): Show Thank you message after sign-out. | 6 | wait | 0
10. Sign In Page: Check for browser type and display message if the browser type is not supporeed. (Is this Sterling or HP?) | 0 |  | 0 |  |  | Message content need to be corrected
11. Sign In Page: Set session timeout to 5hours | 0 |  | 0 |  |  | OOTB 30 or 1hr?
12. Sign In Page: Display Storefront name on browser and Image for the identity information on the browser. | 8 |  | 8 |  |  | Only storefront name - no image; no page title
13. Forgot Password - Just keep it OOTB. Configure from email to 'ebusiness@<brand>.com' | 0 |  | 0 |  |  | keep as eBusiness@ipaper.com
14.Forgot Password: On Cancel take the user back to the sign in page | 0 |  | 0
15. Register Form: On submit, copy of the email is sent to the requesteor and ebusiness@<brand>.com inbox | 0 |  | 0 |  |  | keep as eBusiness@ipaper.com
16. Register Form: On Cancel take the user back to the sign in page | 4 | wait | 0
17. Contact Us: For logged in user and anonymous user. New functionality | 24 | HIGH | 24
18. Terms of Access: This is only for logged in user right, if the user is not logged in then what do we show. Please clarify??? GT & SB: Always show T&A (before or after sign-in) | 0 |  | 0 |  |  | Keep as it is in stg
19. Home Page: Welcome Message, fetch the First and Last name of the user and display it. Display the ship to name. | 4 |  | 4
20. Home Page: Fetch the Location Id for the ship to customer and display it with the ship to name, customer number (for e.g, 30-12345-001) and address. | 6 | wait | 0 |  |  | Location ID is currently not inplemented
21. Home Page: Help: Opens a page (added to Resources packet) in new browser disabling address bar, etc. This will be static and will be included in the HTML file itself. | 0 |  | 0 |  |  | Address via HTML
22. Home Page: Put a link at the top 'Add to your existing order'. Upon clicking it takes the users to the orders search page and list all the orders which are in OPEN status. Do we need to look at other status too when modifications are allowed for an order. Looking into other statuses and conditions would be complex, for simplicity we can leave it to just filter orders with status OPEN. Please confirm. Also, do we need to hide the order status drop down. SB: Just OPEN status | 12 | HIGH | 12
23. Home Page: Show a link for pending approval orders for the user. The link should show up only for users who has approval role. The link should filter orders which are pending approval. | 12 | MEDIUM | 12
24. Quick Add: Takes to shopping cart with Quick Add section expanded; If no active cart, create one based on the default cart creation logic. | 32 | HIGH | 32 |  |  | 8.0 has the functionality and 9.0 does not have - Pawan to confirm
25.Cart information: Mask $ amount if view price role is unchecked; Down arrow icon next to it - clicking on it, display a dropdown menu, which links to cart mangement screen | 8 | HIGH | 8
26. Home Page (<Storefront> News): Last five (posted date) titles are displayed. View all shows if there are more than five articles. View all links to the <Storefront> section in news landing page (should be part of the javascript delivered as part of html). | 8 | wait | 0 |  |  | Keep as current Linking to customer vs storefront should be part of html
27. Home Page (<Storefront> News): Clicking on a particular news title opens the article in modal. Title is truncated with … if it does not fit in one line.(this should be html, may be we should put char limit); Make sure storefront name is dynamically pulled. | 4 |  | 4 |  |  | Handle via HTML
28.Home Page (Customer News): Last five (posted date) titles are displayed. View all shows if there are more than five articles. View all links to the customer section in news landing page(should be part of the javascript delivered as part of html). | 8 | wait | 0 |  |  | Keep as current Linking to customer vs storefront should be part of html
29.Home Page (Customer News): Clicking on a particular news title opens the article in modal. Title is truncated with … if it does not fit in one line(this should be html, may be we should put char limit). If there are no customer news, display 'How to post Customer News?' article; which will be a link to a static content. | 12 | wait | 0 |  |  | Keep as page instead of modal
30. Promotion (Home Page): Check what value are we getting in the customer load. Functionality to remain as implemented. Default to HomePage_Promo.html (if not found) , please test | 4 | wait | 0 |  |  | Responsibility is on eLiz
31. Promotion (C3 Catalog): Change division value from Ship from to customer division. Default to Catalog_Promo.html (if not found), please test | 0 |  | 0 |  |  | Steve to explain to Liz
0
32. Storefront: Emails, are there going to be different template for different storefronts???? How drastically do they differ from each other. | 0 |  | 0 |  |  | TBD
33. Storefront(Help, Advertisement): Currently they are HP activities, do you want them to take care of it. | 0 |  | 0 |  |  | TBD
34. Storefront(Product Categories): Did not understand the requirement?? | 0 | wait | 0 |  |  | Discuss with Deanna
35. Storefront(Promotion):This is only for Sign in Page, no home or catalog page. | 0 | wait | 0
36. Storefront(Print Page): Currently they are HP activities, do you want them to take care of it. | 0 | LOW | 0 |  |  | TBD - low priority
37. Storefront( Printable Catalogs & Estimating Files): These are at the division level and currently divisions can have multiple brands. | 0 | Call Center CR | 0
38. Storefronts(Register/Forgot Email): How is it storefront specific? | 0 | Back to 32 | 0
39. Storefront: What is system emails? | 0 | Back to 32 | 0
40. Storefront (xpedx item #): Make sure to replace the xpedx item # with brand item # across the site. | 32 |  | 32 |  |  | TBD
41. Storefront: Talk about Bulkley Dunton |  |  | 0
HTML: Sign In, Home, Forgot Password (step1, 2 and confirmation), Register Form, Contact Us, Quick Add menu | 56 |  | 56
Note on B24: IBM_ADMIN: The estimate can change based on the clarification

## Punchout
| Hours | In Scope BR1 |  | Effort | Effort (Man Days) | Comments
1. Punchout: Rename 'Sign Out' link to 'Cancel Shopping' on the header. | 4 |  | 4 | 44 | 5.5
2. Punchout: Remove the 'Help' link on the header. | 4 | Low | 4
3. Punchout: '- Clicking on 'Cancel Shopping' will open a confirmation pop-up of Yes/No to leave the site. - Pop-up message with 'Yes' & 'No' buttons: Are you sure you want to leave this page? If inactive, your current cart will automatically be purged in 7 days. - Action Buttons: Clicking on 'Yes' will save the cart for 7 days and return the user to their own procurement system. Clicking on 'No' will allow them to remain on the current page. | 0 |  | 0 |  |  | This was part of the original requirement, so the effort needs to be consumed by us.
4. Punchout: Remove 'Order Management', 'Resources' and 'My Account' (aka Admin) tabs from the site navigation bar. However, note the users can get to quick links, news articles landing page, and articles through home page. | 16 |  | 16
5. Punchout: Shopping cart or Mini cart check out to prompt a confirmation pop-up of Yes/No to leave the site. - Pop-up message with 'Yes' & 'No' buttons: Are you sure you want to leave this page? If inactive, your current cart will automatically be purged in 7 days. - Action Buttons: Clicking on 'Yes' will save the cart for 7 days and return the user to their own procurement system. Clicking on 'No' will allow them to remain on the current page. Lets review what is out of the box | 0 |  | 0 |  |  | This was part of the original requirement, so the effort needs to be consumed by us.
6. Punchout: Disable Minimum / Maximum / Small Order fee rule. | 8 |  | 8
7. Punchout: Disable 'Add to an existing order' or 'Pending order' message on the header. | 4 |  | 4
0
HTML: Confirmation modal for Cancel Shopping and Checkout. | 8 |  | 8

## Sales Rep
| Hours | In Scope BR1 |  | Effort | Effort (Man Days)
1. Sales Rep: Sign In - refer to tab 'Screen Shot'. Keep what has been already developed. Just see if the image can be removed. | 0 |  | 0 | 20 | 2.5 | Assumption: Easily removable image… if not, need to estimate
2. Sales Rep: Forgot password - will show tool tip when mouse is hover over this label. (Content TBD - 'Username and Password is your network Id.'). Keep it as is. No change | 0 |  | 0
3. Sales Rep: After authentication… search works like google search. See screen shot below. - Show data as user types (ex: show 'smith' when user types smi) - Display 'contains' once user clicks on search button (ex: John Smith) | 12 | wait | 0
4. Sales Rep: Web Channel Admin screen - Sales Rep dummy IDs need to be hidden from Admin ('manage other users') | 8 |  | 8
5. Sales Rep: For sales rep's my profile, just show them the Site Preferences tab and allow them to edit the data only for that page. Hide the rest of the tabs. | 12 |  | 12
6. Sales Rep: For sales rep, do we show the other options in the admin hover, other than My Profile. | 0 |  | 0