## MyItemsList
Original Item # represents the item number given in MyItems List - Estimate_BugherPriority.docx
1.My Items menu: Truncate the name of the list to show first 15 characters and then 3 dots (...) and a space and number in the list with parenthesis. (2hrs)
Original Item # | 3
Developer: | Arvind
Peer Tester: | Vaibhav
Estimate (in days):
Start Date:
End Date:
Assumptions and Limitations:
Test Cases:
Scenarios | Developer test cases | Peer test cases
2. My Items Landing Page: Filter By (pending discussion) (2 days)
Original Item # | 4
Developer: | Smitha
Peer Tester: | Amar
Estimate (in days):
Start Date:
End Date:
Assumptions and Limitations:
Test Cases:
Scenarios | Developer test cases | Peer test cases
3. My Items Landing Page: Default sorting of the list by ' Last Modified Date' (3hrs)
Original Item # | 5
Developer: | Amar
Peer Tester: | Jagz
Estimate (in days):
Start Date:
End Date:
Assumptions and Limitations:
Test Cases:
Scenarios | Developer test cases | Peer test cases
4. My Items Landing Page: Actions - (1 day)
Original Item # | 7
Developer: | Jagz
Peer Tester: | Smitha
Estimate (in days):
Start Date:
End Date:
Assumptions and Limitations:
Test Cases:
Scenarios | Developer test cases | Peer test cases
5. MIL Non-Edit Page: Add to cart functionality need to coded for individual item in the list. (2days)
Original Item # | 11
Developer: | Amar
Peer Tester: | Krithika
Estimate (in days):
Start Date:
End Date:
Assumptions and Limitations:
Test Cases:
Scenarios | Developer test cases | Peer test cases
6. MIL Non-Edit Page: Check Availability functionality need to coded for individual item in the list. (1.5days)
Original Item # | 12
Developer: | Amar
Peer Tester: | Krithika
Estimate (in days):
Start Date:
End Date:
Assumptions and Limitations:
Test Cases:
Scenarios | Developer test cases | Peer test cases
7. MIL Non-Edit Page: Show Bracket Pricing And Extended price. (0.5days)
Original Item # | 13
Developer: | Amar
Peer Tester: | Krithika
Estimate (in days):
Start Date:
End Date:
Assumptions and Limitations:
Test Cases:
Scenarios | Developer test cases | Peer test cases
8. MIL Edit Page: Add the Line PO field in the quick add. (0.5days)
Original Item # | 13
Developer: | Arvind
Peer Tester: | Krithika
Estimate (in days):
Start Date:
End Date:
Assumptions and Limitations:
Test Cases:
Scenarios | Developer test cases | Peer test cases
9. Error Messages - All pages (2 day)
Original Item # | 17
Developer: | Vaibhav
Peer Tester: | Smitha
Estimate (in days):
Start Date:
End Date:
Assumptions and Limitations:
Test Cases:
Scenarios | Developer test cases | Peer test cases
10. Share Modal: Buyer user no sharing checkbox. (3hrs)
Original Item # | 18
Developer: | Vaibhav
Peer Tester: | Smitha
Estimate (in days):
Start Date:
End Date:
Assumptions and Limitations:
Test Cases:
Scenarios | Developer test cases | Peer test cases
11. Share Modal: Pass argument and populate the correct label on the top based on the action. (1 day)
Original Item # | 19
Developer: | Vaibhav
Peer Tester: | Smitha
Estimate (in days):
Start Date:
End Date:
Assumptions and Limitations:
Test Cases:
Scenarios | Developer test cases | Peer test cases
12. Replacement Modal: View message on the non-edit message. Edit mode apply the replacement functionality, open the modal and keep the current functionality. (1 day)
Original Item # | 20
Developer: | Krithika
Peer Tester: | Arvind
Estimate (in days):
Start Date:
End Date:
Assumptions and Limitations:
Test Cases:
Scenarios | Developer test cases | Peer test cases